COUNTY GOVERNMENT OF KIAMBU

COUNTY ANNUAL DEVELOPMENT PLAN

2018-2019

APRIL 2018

Vision

To be the most recognized, modernized and well organized county with equal opportunities and high standards of living for all.

Mission

To improve the standard of living and welfare of our citizens, by promoting effective governance structures, providing quality services through public participation, equitable distribution of resources and fiscal responsibility.

Goal

Provision of efficient and effective service delivery for enhanced governance and accountability.

Our Core values

- Visionary

- Transparency

- Accountability

- Teamwork

- Inclusiveness

- Respect

TABLE OF CONTENTS

LIST OF TABLES	vi

LIST OF MAPS/FIGURES	ix

ABBREVIATIONS AND ACRONYMS	x

GLOSSARY OF COMMONLY USED TERMS	xi

FOREWORD	xii

ACKNOWLEDGEMENT	xiii

EXECUTIVE SUMMARY	xiv

LEGAL BASIS FOR THE PREPARATION OF THE ADP AND THE LINK WITH CIDP AND THE BUDGET	xv

CHAPTER ONE: INTRODUCTION	1

1.1 Overview of the County	1

1.1.1 Position and Size	1

1.1.2 Administrative and Political Units	2

1.1.2.1 Administrative Subdivision	2

1.1.2.2 Political units	4

1.1.3. Demographic Features	4

1.1.3.1. Population size and composition	4

1.1.3.2. Population density and distribution	5

1.1.4 Infrastructure Development	6

1.1.4.1. Roads and Rail Network	6

1.1.4.2. Information, Communication Technology	6

1.1.4.3. Energy access	6

1.2 Annual Development Plan Linkage with County Integrated Development Plan (CIDP)	7

1.3 Preparation process of the Annual Development Plan	7

CHAPTER TWO: REVIEW OF THE IMPLEMENTATION OF THE PREVIOUS ADP	8

2.1 Introduction	8

2.2. Sector/ Sub-sector Achievements in the Previous Financial Year	8

2.2.1 County Assembly	8

2.2.2 County Executive	11

2.2.3 County Public Service Board	14

2.2.4 Finance, ICT and Economic Planning	18

2.2.5 Administration and Public Service	26

2.2.6 Agriculture, Crop Production, Irrigation & Marketing	33

2.2.7 Water, Environment, Energy and Natural Resources	42

2.2.8 Health Services	51

2.2.9 Education, Culture & Social Services	63

2.2.10 Youth and Sports	67

2.2.11 Lands, Physical Planning & Housing	70

2.2.12 Trade, Tourism, Co-operative and Enterprise Development	74

2.2.13 Roads, Transport, Public Works and Utilities	82

2.2.14 Livestock, Fisheries and Marketing	87

2.3 Payments of Grants, Benefits and Subsidies	96

2.4 Challenges experienced during implementation of the previous ADP	97

2.5 Lessons learnt and recommendations	97

CHAPTER THREE: COUNTY STRATEGIC PRIORITIES, PROGRAMMES AND PROJECTS	99

3.1 Introduction	99

3.2 Sector / Subsector Capital and Non Capital Projects for 2018/2019 FY	99

3.2.1 County Assembly	99

3.2.2 County Executive	102

3.2.3 County Public Service Board	106

3.2.4 Finance, ICT and Economic Planning	109

3.2.5 Administration, Public Service and Communication	120

3.2.6 Agriculture, Crop Production and Irrigation	136

3.2.7 Water, Environment, Energy and Natural Resources	151

3.2.8 Health Services	169

3.2.9 Education, Youth, Sports, Culture and Social Services	203

3.2.10 Youth Affairs, Sports, Gender and Culture	213

3.2.11 Lands, Physical Planning and Housing	223

3.2.12 Trade, Tourism, Industry and Co-operative	230

3.2.13 Roads, Transport and Public Works	241

3.2.14 Livestock, Fisheries and Marketing	248

3.3 Payments of Grants, Benefits and Subsidies	264

CHAPTER FOUR: RESOURCE ALLOCATION	265

4.0 Resource allocation criteria	265

4.1 Proposed budget by programme	265

4.2 Proposed budget by sector/ sub-sector	267

4.3 Financial and Economic Environment	267

CHAPTER FIVE: MONITORING AND EVALUATION	269

5.1 Institutional Framework for Monitoring and Evaluation in Kiambu County	269

5.2 Data collection, Analysis and Reporting mechanisms	270

5.3 Monitoring and Evaluation Performance Indicators	270

# LIST OF TABLES

Table 1:  Area by Sub-county and ward	3

Table 2: County’s Electoral Wards by Constituency	4

Table 3 : Population Projections by Age Cohort	4

Table 4: Population distribution and density by Sub-county	5

Table 5: County Assembly Programmes	9

Table 6: Performance of Capital Projects for County Assembly	10

Table 7: Performance of Non-Capital Projects for County Assembly	11

Table 8: County Executive Programmes	12

Table 9: Performance of Non-Capital Projects for County Executive	13

Table 10: County Public Service Board Programmes	15

Table 11: Performance of Non-Capital Projects for County Public Service Board	16

Table 12: Finance, ICT & Economic Planning Programmes	19

Table 13:  Performance of Non-Capital Projects for Finance, ICT & Economic Planning	22

Table 14: Administration and Public Service Programmes	28

Table 15: Performance of Capital Projects for Administration and Public Service	31

Table 16: Performance of Non capital projects for Administration and Public Service	32

Table 17: Agriculture, Crop Production, Irrigation & Marketing Programmes	34

Table 18: Performance of Capital Projects for Agriculture, Crop Production, Irrigation & Marketing	38

Table 19: Performance of Non-Capital Projects for Agriculture, Crop Production, Irrigation & Marketing	40

Table 20: Water, Environment, Energy and Natural Resources Programmes	42

Table 21: Performance of Capital Projects for Water, Environment, Energy & Natural Resources	47

Table 22: Performance of Non-Capital Projects for Water, Environment, Energy & Natural Resources	50

Table 23: Health Services Programmes	52

Table 24: Performance of Capital Projects for Health Services	54

Table 25: Performance of Non-Capital Projects for Health Services	62

Table 26: Education, Culture & Social Services Programmes	64

Table 27: Performance of Capital Projects for Education, Culture, & Social Services	65

Table 28: Performance of Non-Capital Projects for Education, Culture, & Social Services	66

Table 29: Youths and Sports Programmes	67

Table 30: Performance of Capital Projects for Youths and Sports	69

Table 31: Performance of Non-Capital Projects for Youths and Sports	69

Table 32: Lands, Physical Planning and Housing Programmes	71

Table 33: Trade, Tourism, Co-operative and Enterprise Development Programmes	75

Table 34: Performance of Capital Projects for Trade, Tourism, Co-operative & Enterprise Development	78

Table 35: Performance of Non-Capital Projects for Trade, Tourism, Co-operative & Enterprise Development	80

Table 36: Roads, Transport, Public Works & Utilities Programmes	83

Table 37: Performance of Capital Projects for Roads, Transport, Public Works and Utilities	85

Table 38: Performance of Non capital Projects for Roads, Transport, Public Works and Utilities	87

Table 39: Summary of Livestock, Fisheries and Marketing Programmes	88

Table 40: Performance of Capital Projects for Livestock, Fisheries and Marketing	92

Table 41: Performance of Non-Capital Projects for Livestock, Fisheries and Marketing	95

Table 42:  Payments of Grants, Benefits and Subsidies	96

Table 43: County Assembly Capital projects for the FY 2018/2019	100

Table 44: County Assembly Non-Capital Projects for FY 2018/19	101

Table 45: County Executive Non-Capital Projects for FY 2018/19	104

Table 46: County Public Service Board Non-Capital Projects for FY 2018/19	108

Table 47: Finance, ICT and Economic Planning Capital Projects for FY 2018/19	113

Table 48: Finance, ICT and Economic Planning Non-Capital Projects for FY 2018/19	114

Table 49: Administration, Public Service & Communication Capital projects for the FY 2018/2019	125

Table 50: Administration, Public Service & Communication Non Capital projects for the FY 2018/2019	126

Table 51: Agriculture, Crop Production & Irrigation Capital projects for the FY 2018/2019	141

Table 52: Agriculture, Crop Production & Irrigation Non Capital projects for the FY 2018/2019	144

Table 53: Water, Environment, Energy & Natural Resources Capital projects for the FY 2018/2019	158

Table 54: Health Services Capital projects for the 2018/19 FY	176

Table 55: Health Services Non-Capital Projects 2018/19 FY	192

Table 56: Education, Youths, Sports, Culture & Social Services Capital projects for the FY 2018/19	207

Table 57: Education, Youths, Sports, Culture & Social Services Non Capital projects for the FY 2018/19	209

Table 58: Youths Affairs, Sports, Gender & Culture capital projects for the FY 2018/19	216

Table 59: Youth Affairs, Sports, Gender and Culture non-capital projects for the FY 2018/19	220

Table 60: Lands, Physical Planning & Housing Capital projects for the 2018/19FY	224

Table 61: Lands, Physical Planning & Housing non capital projects for the 2018/19FY	228

Table 62: Trade, Tourism, Industry and Co-operative capital projects for the 2018/19FY	235

Table 63: Trade, Tourism, Industry and Co-operative Non-Capital Projects FY 2018/19	240

Table 64: Roads, Transport and Public Works capital projects for the 2018/19FY	243

Table 65: Livestock, Fisheries & Marketing capital projects for the 2018/19FY	253

Table 66: Livestock, Fisheries & Marketing non capital projects for the 2018/19	262

Table 67: Payments of Grants, Benefits and Subsidies	264

Table 68: Summary of proposed budget by programme	265

Table 69 : Summary of proposed budget by sector/sub-sector	267

Table 70: Risks, Assumptions and Mitigation measures	268

Table 71: Summary of M&E Outcome indicators	270

# LIST OF MAPS/FIGURES

Figure 1: ADP Linkage with other Plans	xv

Figure 2: Location of the County in Kenya	1

Figure 3: County’s Administrative and Political Units	2

# ABBREVIATIONS AND ACRONYMS

CADP 		County Annual Development Plan

CIDP		County Integrated Development Plan

CGK		County Government of Kiambu

CIMES	County Integrated Monitoring and Evaluation System

CPSB		County Public Service Board

ECDE		Early Childhood Development Education

CBEF		County Budget and Economic Forum

CBROP	County Budget Review and Outlook Paper

CFSP		County Fiscal Strategy Paper

FEP		Finance and Economic Planning

FY		Financial Year

ICT		Information Communication Technology

IPSAS		International Public Sector Accounting Standards

KURA		Kenya Urban Roads Authority

M&E 		Monitoring and Evaluation

MTEF		Medium Term Expenditure Framework

MTP		Medium Term Plan

NACADA	National Agency for the Compaign Against Drug Abuse

NIMES	National Integrated Monitoring and Evaluation System

PBB		Program Based Budget

PER 		Public Expenditure Review

PFMA		Public Finance Management Act

CBO		Community based organization

CSO		Civil Society Organization

NGO		Non Governmental Organization

# GLOSSARY OF COMMONLY USED TERMS

County Executive Committee - Means a county executive committee in charge of a department/ sector established in accordance with Article 176 of the Constitution.

County Government: Refers to a political sub-division, which are created within the state for the exercise of duties and responsibilities granted by constitutional provisions or legislative enactments; it is provided for under Article 176 of the Constitution

Baseline: Baseline is an analysis describing the initial state of an indicator before the start of a project/programme, against which progress can be assessed or comparisons made

Programme: A grouping of similar projects and/or services performed by a Ministry or Department to achieve a specific objective; The Programmes must be mapped to strategic objectives.

Project: A project is a set of coordinated activities implemented to meet specific objectives within defined time, cost and performance parameters. Projects aimed at achieving a common goal form a programme.

Performance indicator: A measurement that evaluates the success of an organization or of a particular activity (such as projects, programs, products and other initiatives) in which it engages.

Target: A target refers to planned level of an indicator achievement

Output: The intermediate results generated after implementation of programme or project.

Strategy: It is the overall direction and scope in the long run; which enhances competitiveness in a changing environment through its alignment of both intangible and tangible resources with the aim of gratifying stakeholders’ aspirations.

# FOREWORD

This is the Fifth Kiambu County Annual development Plan (CADP) under the devolved governance structure and the first to be prepared under the Second County Integrated Development Plan (CIDP) covering the period 2018-2022. The 2018/2019 CADP has been prepared in accordance with Section126 of the Public Finance Management Act (PFMA), 2012 and Article 220(2) of the Constitution of Kenya.

The plan outlines the strategic priorities for the medium term that reflects County Government's priorities and plans. It further describes how the County Government will respond to changes in the financial and economic environment; programmes to be delivered with details for each programme; payments to be made on behalf of the county government. The plan also describes significant capital developments including measurable indicators and a summary budget.

The CIDP is a five year plan which set the strategic mid-term priorities of the county government. It contains programs with specific goals and objectives, costed implementation plan, monitoring & implementation framework and clear reporting framework. The CIDP forms the basis for all the budgeting and planning in the county and is implemented through a series of one-year plans known as County Annual Development Plans (CADPs).

The plan was prepared through a participatory process and involved data collection from the County government departments and other stakeholders.  The sectors incorporated views from key stakeholders into their reports and ensure the development priorities and strategies were in line with the County Integrated Development plan (2018-2022). The reports were used in the production of the County Annual Development Plan of FY 2018/19.

To finance expenditures set out in this plan, the County will continue to maximize its efforts in revenue mobilization by strengthening and reforming revenue administration and collection processes already in place and through re-engineering various on-going structural reforms.

Through this plan, the County Government proposes to allocate more resources to infrastructure improvement with an aim to stimulating general economic performance while addressing the real issues that affect the lives of county residents. To achieve this, the policy aims at shifting resources from recurrent to capital investment while at the same time promoting sustainable and inclusive growth.

Special thanks goes to all those of those who took part towards development of the Plan and for your valuable contribution and compilation of this document.

Wilson Mburu Kangethe

CECM Finance, ICT and Economic planning.

# ACKNOWLEDGEMENT

The preparation of the County Annual Development Plan (2018-2019) was achieved through an intensive and consultative process involving key stakeholders.  The preparation process was spearheaded by the CADP secretariat with the guidance from the County Executive Committee Member, Department of Finance, ICT and Economic Planning.

The County is indebted to the Governor, His Excellency. Hon. Ferdinard Waititu Babayao and Deputy Governor Hon. Dr. James Nyoro for their leadership and support in the preparation of this plan. Special thanks go to the County Secretary Dr. Martin Njogu, all County Executive Committee members and Chief Officers for steering the preparation of the CADP process up to its successful completion.

I wish to thank individuals who played key roles during the CADP preparation process including  Ms. Anne Muchai, Ms. Sophiah Kamau, Ms. Nduta Kahiu, Mr. Joseph Ng’ang’a, Ms.Faith Kiragu, Ms. Charity Mwangi, Mr. Arnold Nderitu, Mr. Jackson Kasomo ,Ms.Alice Kamau, Mr. Eliaph Karanja, Ms Esther Chege, Ms Dorcas Njuguna, Mr Sospeter Kefah, Mr Moses Kuria and Mr Harun Mwangi. Their relentless commitment and teamwork is duly acknowledged. We further express our appreciation to all section directors and the department staff whose invaluable contribution enriched this document.

I would like to thank the Council of Governors and the Ministry of Devolution and Planning for their support and guidance during the preparation process.

Lastly, i take this opportunity to thank all our partners who supported preparation of this plan either directly or indirectly.

Faith Njeri Harrisson

Chief Officer

Finance, ICT and  Economic Planning

# EXECUTIVE SUMMARY

Section 126 of the Public Finance Management Act, 2012 forms the basis of preparation of the County Annual Development Plan (CADP) for the financial year 2018/19. The County Annual Development Plan is a one year plan that provides the basis for implementing the County Integrated Development Plan (CIDP) and guiding resource allocation to priority projects and programmes. It  presents the strategic priorities for the medium term that reflect the county government’s priorities and plans; county programmes and projects to be delivered; measurable indicators of performance where feasible; and the budget allocated to the programme and projects.

The preparation of Kiambu County Annual Development Plan (2018-2019) was led by the County Executive Member in charge of Finance and Economic Planning.  It was done in close collaboration with various stakeholders including government departments. The Plan was prepared using guidelines issued by the Ministry of Devolution and Planning.

The County Annual Development Plan has five (5) chapters.  Chapter One provides an overview of the county in terms of the location; size; demographic profiles; administrative and political units. It highlights a summary of the socio-economic and infrastructural information that has a bearing on the development of the county. It describes the county in terms of the location, size, demographic profiles as well as the administrative and political units. The Chapter further summarizes the linkages between the County Annual Development Plan with the County Integrated Development Plan and the plan preparation process.

Chapter Two provides a review of implementation of previous County Annual Development Plan. It summarizes key achievements of the sectors, payment of Grants, Benefits and Subsidies, challenges and lesson learnt from previous experiences.

Chapter Three presents a detailed description of the different sectors within the County and the programmes planned based on the Medium Term Expenditure Framework budgeting system. It also provides the sector vision, mission, development needs, priorities and strategies Programs. In addition, the chapter analysis the programmes/projects and key stakeholders of the sector.

Chapter Four gives a summary of the proposed budget by programme and sector/ sub sector.  It also presents risks, assumptions and mitigation measures during the implementation period

Chapter Five highlights the monitoring and evaluation (M&E) framework that will be used to track progress on implementation of projects and programmes undertaken during the plan period. It specifies objectively verifiable performance indicators that will be used to monitor programs and sets medium term and end term milestones for impact assessment.

# LEGAL BASIS FOR THE PREPARATION OF THE ADP AND THE LINK WITH CIDP AND THE BUDGET

This section present the legal justification for the preparation of the Annual Development Plan as per section 126 of the Public Finance Management Act, 2012 and in accordance with Article 220 (2) of the Constitution of Kenya, 2010. Figure 1 shows a diagrammatic presentation of the link between the ADP, CIDP and the Budget.

Figure 1: ADP Linkage with other Plans

# CHAPTER ONE: INTRODUCTION

## 1.1 Overview of the County

This section provides an overview of the county in terms of the location; size; demographic profiles; administrative and political units. It also highlights a summary of the socio-economic and infrastructural information that has a bearing on the development of the county.

### 1.1.1 Position and Size

Kiambu County is one of the 47 counties in the Republic of Kenya. It is located in the central region and covers a total area of 2,543.5 Km2 with 476.3 Km2 under forest cover according to the 2009 Kenya Population and Housing Census. Kiambu County borders Nairobi and Kajiado Counties to the South, Machakos to the East, Murang‘a to the North and North East, Nyandarua to the North West, and Nakuru to the West as indicated in Map 1. The county lies between latitudes 00 25‘ and 10 20‘ South of the Equator and Longitude 360 31‘ and 370 15‘ East. Figure 1 show the location of the county in Kenya.

Figure 2: Location of the County in Kenya

### 1.1.2 Administrative and Political Units

- 1.1.2.1 Administrative Subdivision

The county is subdivided into twelve sub counties and sixty wards as shown in table 1.

Figure 3: County’s Administrative and Political Units

Table 1:  Area by Sub-county and ward

| Sub county | Area sq.km | No. of wards |
| --- | --- | --- |
| Gatundu South | 192.4 | 4 |
| Gatundu North | 286.0 | 4 |
| Juja | 326.6 | 5 |
| Thika Town | 217.5 | 5 |
| Ruiru | 201.4 | 8 |
| Githunguri | 173.5 | 5 |
| Kiambu | 105.9 | 4 |
| Kiambaa | 83.2 | 5 |
| Limuru | 281.7 | 5 |
| Kikuyu | 175.8 | 5 |
| Kabete | 60.3 | 5 |
| Lari | 439.2 | 5 |
| Total | 2543.5 | 60 |

- 1.1.2.2 Political units

Kiambu County has twelve constituencies and sixty wards. Table 2 shows the names of the constituencies and electoral wards of Kiambu County.

Table 2: County’s Electoral Wards by Constituency

| Constituency | Electoral Wards |
| --- | --- |
| Gatundu South | Kiamwangi, Kiganjo, Ndarugo, Ngenda |
| Gatundu North | Gituamba, Githobokoni, Chania, Mang’u |
| Juja | Murera, Theta, Juja, Witeithie, Kalimoni |
| Thika Town | Township, Kamenu, Hospital, Gatuanyaga |
| Ruiru | Gitothua, Biashara, Gatongora, Kahawa/Sukari, Kahawa Wendani, Kiuu, Mwiki, Mwihoko |
| Githunguri | Githunguri, Githiga, Ikinu, Ngewa, Komothai |
| Kiambu | Ting’ang’a, Ndumberi, Riabai, Township |
| Kiambaa | Cianda, Karuri, Ndenderu, Muchatha, Kihara |
| Limuru | Bibirioni, Limuru Central, Ndeiya, Limuru East, Ngecha Tigoni |
| Kikuyu | Karai, Nachu, Sigona, Kikuyu, Kinoo |
| Kabete | Gitaru, Muguga, Nyathuna, Kabete, Uthiru |
| Lari | Kinale, Kijabe, Nyanduma, Kamburu, Lari/Kirenga |

- 1.1.3. Demographic Features

- 1.1.3.1. Population size and composition

According to the 2009 Kenya Population and Housing Census, Kiambu County population stood at 1,623,282 which is projected to be 1,942,505 by 2018. The population is further projected to reach 2,090,592 by the end of 2022. Table 3 gives population projections for 2018, 2020 and 2022 by gender and age cohorts with 2009 as the base year.

Table 3 : Population Projections by Age Cohort

|  | 2009 |  |  | 2018 |  |  | 2020 |  |  | 2022 |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Age | Male | Female | Total | Male | Female | Total | Male | Female | Total | Male | Female | Total |
| 0-4 | 102,566 | 101,269 | 203,835 | 126,470 | 126,191 | 252,679 | 128,423 | 127,947 | 256,370 | 129,498 | 128,988 | 258,486 |
| 5-9 | 93,358 | 92,84 | 186,198 | 107,188 | 106,852 | 214,055 | 113,281 | 112,786 | 226,067 | 114,997 | 114,495 | 229,491 |
| 10-14 | 84,262 | 85,23 | 169,492 | 90,698 | 90,383 | 181,092 | 93,230 | 93,194 | 186,424 | 99,306 | 99,333 | 198,639 |
| 15-19 | 71,345 | 77,095 | 148,440 | 84,670 | 88,981 | 173,661 | 87,025 | 91,444 | 178,469 | 89,540 | 94,669 | 184,208 |
| 20-24 | 82,088 | 97,187 | 179,275 | 97,613 | 96,782 | 194,386 | 100,291 | 97,020 | 197,311 | 103,139 | 100,041 | 203,180 |
| 25-29 | 84,618 | 90,428 | 175,046 | 97,345 | 93,947 | 191,208 | 100,577 | 92,077 | 192,654 | 103,336 | 92,356 | 195,685 |
| 30-34 | 72,159 | 68,700 | 140,859 | 87,948 | 86,381 | 174,339 | 91,783 | 89,233 | 181,016 | 94,890 | 87,624 | 182,484 |
| 35-39 | 58,391 | 53,513 | 111,904 | 75,605 | 70,282 | 145,887 | 79,182 | 74,728 | 153,910 | 82,879 | 77,499 | 160,377 |
| 40-44 | 42,264 | 39,008 | 81,272 | 61,524 | 54,282 | 115,819 | 65,391 | 57,515 | 122,906 | 68,795 | 61,997 | 130,787 |
| 45-49 | 34,363 | 31,417 | 65,780 | 47,206 | 41,193 | 88,405 | 50,997 | 43,974 | 94,971 | 54,750 | 47,168 | 101,917 |
| 50-54 | 22,379 | 20,781 | 43,160 | 35,848 | 32,064 | 67,918 | 38,651 | 34,331 | 72,982 | 42,561 | 37,228 | 79,788 |
| 55-59 | 16,784 | 15,891 | 32,675 | 24,654 | 23,032 | 47,690 | 27,222 | 25,358 | 52,580 | 29,892 | 27,628 | 57,520 |
| 60-64 | 13,125 | 13,164 | 26,289 | 15,563 | 15,391 | 30,956 | 16,704 | 16,383 | 33,087 | 19,165 | 18,780 | 37,946 |
| 65-69 | 8,389 | 10,210 | 18,599 | 11,292 | 12,077 | 23,368 | 11,755 | 12,342 | 24,097 | 12,836 | 13,358 | 26,193 |
| 70-74 | 6,298 | 7,742 | 14,040 | 7,901 | 9,218 | 17,118 | 8,316 | 9,610 | 17,926 | 8,712 | 9,881 | 18,593 |
| 75-79 | 3,891 | 5,342 | 9,233 | 5,048 | 6,471 | 11,518 | 5,327 | 6,761 | 12,088 | 5,669 | 7,140 | 12,809 |
| 80+ | 5,792 | 10,474 | 16,266 | 4,814 | 7,595 | 12,405 | 4,824 | 7,332 | 12,156 | 5,025 | 7,469 | 12,493 |
| NS | 537 | 382 | 919 | - | - | - | - | - | - | - | - | - |
| Total | 802,609 | 642,603 | 1,623,282 | 981,385 | 961,120 | 1,942,505 | 1,022,979 | 992,035 | 2,015,014 | 1,064,989 | 1,025,654 | 2,090,598 |

Source: KNBS

- 1.1.3.2. Population density and distribution

Kiambu County had a population of 638 persons per square kilometre, according to the 2009 census. This is projected to be 936 persons/km2 by the end of 2022. Kabete Sub County has the highest population density of 2329 persons/km2 which is projected to reach 3056 people per square kilometre.  The least densely populated sub county is Lari with 282 persons/Km2. Table 5 shows the population and density by Sub County.

Table 4: Population distribution and density by Sub-county

|  | 2009 Census |  | 2018 projections |  | 2020 projections |  | 2022 projections |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Name of Sub County | Population | Density (Km2 ) | Population | Density (Km2 ) | Population | Density (Km2 ) | Population | Density (Km2 ) |
| Gatundu South | 114,180 | 593 | 136,634 | 710 | 141,735 | 736 | 149,830 | 778 |
| Gatundu North | 100,611 | 352 | 120,396 | 421 | 124,890 | 437 | 132,024 | 462 |
| Juja | 118,793 | 365 | 142,154 | 437 | 147,461 | 453 | 155,883 | 479 |
| Thika town | 165,342 | 760 | 197,857 | 909 | 205,243 | 943 | 216,966 | 997 |
| Ruiru | 201,986 | 1003 | 241,708 | 1,200 | 250,730 | 1,245 | 265,051 | 1,316 |
| Githunguri | 147,763 | 852 | 176,821 | 1,020 | 183,421 | 1,058 | 193,898 | 1,118 |
| Kiambu | 108,698 | 1026 | 130,073 | 1,228 | 134,929 | 1,274 | 142,635 | 1,346 |
| Kiambaa | 145,053 | 1979 | 173,578 | 2,368 | 180,057 | 2,457 | 190,342 | 2,597 |
| Kabete | 140,427 | 2329 | 168,042 | 2,787 | 174,315 | 2,891 | 184,271 | 3,056 |
| Kikuyu | 125,402 | 713 | 150,063 | 853 | 155,664 | 885 | 164,556 | 936 |
| Limuru | 131,132 | 466 | 156,920 | 558 | 162,777 | 578 | 172,075 | 611 |
| Lari | 123,895 | 282 | 148,260 | 337 | 153,794 | 350 | 162,578 | 370 |
| Kiambu County | 1,623,282 | 638 | 1,942,505 | 763 | 2,015,014 | 792 | 2,130,109 | 837 |

- 1.1.4 Infrastructure Development

- 1.1.4.1. Roads and Rail Network

The county has a total of 5533 Km of roads network. 249 Km of road are yet to be opened. The roads under bitumen standards are 865.4 KMs, 1051km on gravel, 3167km on earth surface. The county is served by Thika Super Highway from Githurai-Ruiru-Juja-Thika on average of 50Kms and A104 Uthiru-Kikuyu-Kamandura- Kinungi on average of 65 which 25.1km of it is on rehabilitation expansion programme. It is also served by a railway line which is 131km and has Railway stations in Kahawa, Ruiru, Juja, Thika, Kikuyu and Limuru. There exist bus parks in all sub counties 9 paved and 4 unpaved.

- 1.1.4.2. Information, Communication Technology

Kiambu County has 98 percent mobile network coverage owing to its location and proximity to the city. Landline coverage has been on the decline due to adoption of new technology and ease of using mobile phones. There are a total of 19 post offices and 14 sub post offices which are fairly distributed in the county. These post offices are; Ruiru, two at Thika, Juja, Githunguri, Karuri, Kiambu, Kikuyu, Limuru and Matathia-Lari post office. There are quite a number of cyber cafes offering internet access hence easy access of communication. This has been possible due to introduction of fibre optic cables in the county. Many residents listen to local FM and radio stations mainly Kameme, Inooro and Coro FM for primary information in addition to other national stations. The citizens are able to watch a variety of TV stations operating in the country. There is one Huduma centre located at Thika where citizens access government services.

- 1.1.4.3. Energy access

Kiambu county 98 percent coverage of electricity with effective coverage on the last mile programme. There has been an increase in the connectivity of rural household to electricity due to rural electrification programme. The total household connected to electricity is 70 percent, and this number is expected to rise to 100 percent in the year 2022. Solar energy has less than 5percent coverage, while Biogas use is at 25 percent especially by farmers in Githunguri, kikuyu, Limuru and other sub-counties where dairy farming is practiced. Wind coverage as a source of energy is not active; however it is being tested in a pilot project in Nachu-Ndeiya. This has been supported by UN habitat in the promotion of renewable energy. Utility directorate has installed flood mast as follows; 56 no. 30m high, 9no. 20M high and 139 no. 15 M high all distributed in all the sub counties and 235 street lighting through WB financing. Kenya power and Lighting Company has played a key role in street lighting, installation of flood masts; 12 in Thika, 11 in Kiambu, 5 in Kikuyu, 11 in Limuru, 11 in Ruiru, 11 in Juja and 9 in Kiambaa. These flood masts are of 30M in height.

## 1.2 Annual Development Plan Linkage with County Integrated Development Plan (CIDP)

County Integrated Development Plan (CIDP) is a five year plan which set the strategic mid-term priorities of the county government. It contains programs with specific goals and objectives, costed implementation plan, monitoring & implementation framework and clear reporting framework. The CIDP forms the basis for all the budgeting and planning in the county and is implemented through a series of  one-year plans known as County Annual Development Plans (CADPs).

The County Annual Development Plan (ADP) guides resource allocation to priority projects and programmes in a particular year. It is prepared in accordance with Section 126 PFMA, 2012 that requires county governments to prepare an Annual Development Plan (ADP) in accordance with Article 220 (2) of the constitution.

## 1.3 Preparation process of the Annual Development Plan

The plan was prepared through a participatory process and involved data collection from the County government departments and other stakeholders.  A circular prepared by the County Executive Committee member of Finance and Economic Planning was sent to all accounting officers to guide them on how to prepare sector reports. The sectors were to incorporate views from key stakeholders into their reports and ensure the development priorities and strategies were in line with the County Integrated Development plan (2018-2022). The reports were used in the production of the County Annual Development Plan of FY 2018/19.

# CHAPTER TWO: REVIEW OF THE IMPLEMENTATION OF THE PREVIOUS ADP

## 2.1 Introduction

This chapter gives a brief review on the implementation of the previous CADP. It gives a summary of achievement of targets versus planned targets for departmental programmes. It also provides a summary of key achievements on the capital and non-capital projects for the departments. Further, the challenges experienced during the implementation of the CADP, lessons learnt and the recommendations are given.

## 2.2. Sector/ Sub-sector Achievements in the Previous Financial Year

### 2.2.1 County Assembly

- In the 2016/17 FY, County Assembly of Kiambu implemented a number of projects started in the previous financial years. This included refurbishment of the assembly chamber and office block and completion of the perimeter fence, conducting capacity building forums, report writing and passing of bills

- In the 2016/17 FY, County Assembly of Kiambu achieved a number of projects. This included refurbishment of the assembly chamber and office block and completion of the perimeter fence, conducting capacity building forums, report writing and passing of bills

- The overall budget in the Annual Development plan under the General Administration and support services was Kshs. 335,872,590 and the actual allocation was Kshs. 47,644,013

- The overall budget in the Annual Development plan under the Legislation and Oversight services was Kshs. 576,558,000 and the actual allocation was Kshs. 96,164,300

Strategic priorities

- Acquisition, construction and equipping of the Assembly infrastructure

Planned versus allocated budget

- The planned budget was Kshs. 335,872,590 for the General Administration and support services and Kshs. 576,558,000 for the Legislation and Oversight services respectively.

- The Allocated budget was Kshs. 47,644,013 for the General Administration and Support services sub-programme and Kshs. 96,164,300 for the Legislation and Oversight services sub-programme.

Key achievements

The County Assembly of Kiambu achieved a number of projects. This included refurbishment of the assembly chamber and office block and completion of the perimeter fence, conducting capacity building forums, report writing and passing of bills.

Table 5: County Assembly Programmes

| Programme Name: Legislation, Oversight and Representation in the county Government |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Objective: Quality and enforceable legislations and improved oversight for accountability and good governance |  |  |  |  |  |
| Outcome: - Improved service delivery, Quality and enforceable legislations and improved oversight for accountability and good governance |  |  |  |  |  |
| Sub Programme | Key Outcomes/ outputs | Key performance indicators | Planned Targets | Achieved Targets | Remarks* |
| General Administration and Support services | Improved service delivery | complete the perimeter wall, | 1 | 1 | Ongoing |
|  |  | construct members and staff canteen, | 2 | ……………. |  |
|  |  | construction and equipping of computer labs | 1 | ……………. |  |
|  |  | Extension of the assembly chambers | 1 | ……………… |  |
|  |  | Renovation of office blocks | 4 | 2 | Ongoing |
|  |  | Capacity building forums | 48 |  |  |
|  |  | Purchase of courtesy bus | 2 | ……………… |  |
|  |  | Purchase of 4*4 vehicles, | 2 | ……………… |  |
|  |  | acquisition of land for speakers residence | 1 acres | ……………… |  |
| Legislation and Oversight services | Quality and enforceable legislations and improved oversight for accountability and good governance | Legislations/ Bills debated in the Assembly | 20 | 11 | Passed |
|  |  | Executive Oversight Reports Produced | 10 | 32 | Adopted |
|  |  | Liaison committee reports produced | 6 | 1 | Adopted |
|  |  | Budget and Appropriation Act | 1 | 1 | Passed |

Analysis of Capital and Non-Capital projects of the Previous ADP

In the 2015/16 FY, the County Assembly of Kiambu achieved a number of the projects started in the previous financial years. This included refurbishment of the assembly chamber and office block and completion of the car park under general administration and support services sub program. Under legislation and oversight services sub program, the assembly debated and passed a number of crucial bills.

Table 6: Performance of Capital Projects for County Assembly

| Project Name/ Location | Objective/ Purpose | Output | Performance Indicators | Status (based on the indicators) | Planned Cost (Ksh.) | Actual Cost (Ksh.) | Source of funds |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Assembly chambers | Refurbishment | Improved service delivery | Renovations of the Assembly chambers | Currently ongoing | 13,000,000 | 13,000,000 | CGK |
| Office Block | Renovations | Improved service delivery | Renovations of Office block | Currently ongoing | 34,644,013 | 34,644,013 | CGK |

Table 7: Performance of Non-Capital Projects for County Assembly

| Project Name/ Location | Objective/ Purpose | Output | Performance indicators | Status (based on the indicators) | Planned Cost (Ksh.) | Actual Cost (Ksh.) | Source of funds |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Legislative and Oversight services | Quality and enforceable legislations | Quality and enforceable legislations and improved oversight for accountability and good governance | Quality and enforceable legislations |  | 96,164,300 | 96,164,300 | CGK |

### 2.2.2 County Executive

The department was involved in the provision of policy direction and guidelines through cabinet meetings, issuance of policy guidelines and statements, cabinet circulars and security interventions.

Maintained good governance in the performance of the county functions and offered strategic direction of the county. Developed various county government issues policies and developed various cabinet papers .It also included developing bills for submission to the County Assembly for approval.

Operationalized service delivery administrative structures within, by implementing the county legislation, manage and coordinate the functions of the county administration and its department. Initiated a performance management system that has helped improve and track performance of projects within the county.

Promoted public participation in the development of policies and various planning documents. Implemented digital communication platforms and feedback mechanisms, this has enabled free and timely flow of information to citizens thus better service delivery.

Key Achievements

Table 8: County Executive Programmes

| Programme Name : Leadership and Co-ordination of County Administration and Departments |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Objective: Promote efficient and effective service delivery to the residents of Kiambu County |  |  |  |  |  |
| Outcome: Good governance |  |  |  |  |  |
| Sub Programme | Key Outcomes/ outputs | Key performance indicators | Planned Targets | Achieved Targets | Remarks* |
| General administration and support services | Assented county assembly bill | No. of bills assented | 10 | 10 | Target Achieved |
|  | County executive committee meetings | No. of meetings held | 12 | 12 | Target Achieved |
|  | Annual state of the county address report | No of Annual state of the county address report | 1 | 1 | Target Achieved |
|  | Policy guidelines | No of policy guidelines to be issued to be issued to departments | 10 | 10 | Target Achieved |
|  | Cabinet agendas and memos prepared | No of memos and agendas to be generated | 12 | 12 | Target Achieved |
|  | Cabinet circulars | No of circulars to be issued | 5 | 5 | Target Achieved |
|  | Assistance offered to institutions and individuals in need | No of donations beneficiaries | 50 | 50 | Target Achieved |
| Public sector advisory services | Intergovernmental forums | No of meetings attended | 4 | 4 | Target Achieved |
|  | Governor’s council meeting | Attended governor’s council meeting | 4 | 4 | Target Achieved |
|  | Security interventions | No of interventions made | 4 | 3 | Target Achieved |
|  | Executive policy | No of policy statements | 12 | 12 | Target Achieved |
|  |  | No of press releases made | 4 | 4 | Target Achieved |

Analysis of Capital and Non-Capital projects of the Previous ADP

Table 9: Performance of Non-Capital Projects for County Executive

| Project Name/ Location | Objective/ Purpose | Output | Performance indicators | Status (based on the indicators) | Planned Cost (Ksh.) | Actual Cost (Ksh.) | Source of funds |
| --- | --- | --- | --- | --- | --- | --- | --- |
| General administration and support services | Promote efficient and effective service delivery to the residents of Kiambu County. | Assented county assembly bill | No. of bills assented | Complete | 375.8 M | 377.5 M | CGK |
|  |  | County executive committee meetings | No. of meetings held | Complete |  |  |  |
|  |  | Annual state of the county address report | No of Annual state of the county address report | Complete |  |  |  |
|  |  | Policy guidelines | No of policy guidelines to be issued to be issued to departments | Complete |  |  |  |
|  |  | Cabinet agendas and memos prepared | No of memos and agendas to be Complete generated | Complete |  |  |  |
|  |  | Cabinet circulars | No of circulars to be issued | Complete |  |  |  |
|  |  | Assistance offered to institutions and individuals in need | No of donations beneficiaries | Complete |  |  |  |
| Public sector advisory services | Promote efficient and effective service delivery to the residents of Kiambu county | Intergovernmental forums | No of forums attended | Complete | 21M | 7.5M | CGK |
|  |  | Governor’s council meeting | Attended governor’s council meeting | Complete |  |  |  |
|  |  | Security interventions | No of interventions made | Complete |  |  |  |
|  |  | Executive policy | No of policy statements | Complete |  |  |  |

- 2.2.3 County Public Service Board

The County Public Service Board had planned to establish and abolish offices in the county public service; to appoint and recruit persons to hold or act in offices of the county public service; to exercise disciplinary control over officers who breach either county policies, regulations or terms of employment; to instill in the county public service values and principles of governance; to facilitate the development of coherent, integrated human resource planning and budgeting for personnel emoluments in county; to advise the county on human resource management development and succession; to advise the county on implementation and monitoring of the national performance management system in the county; and making recommendations to the SRC, on behalf of the County, on the remuneration, pensions and gratuities for county public service employees. Based on what was planned the department was able to ensure that all vacant positions were filled with the most suitable candidate without deviating from the laid down recruitment procedures. The department also enhanced staff skills, and established the competence inventory. In addition, it also formulated the county human resource manual, and complied with county human resource laws. In order to enhance skills in its work force the department has decentralized human resource service at sub county and departmental levels.

Strategic priorities

The core mandate of the department is to appoint and recruit persons to hold or act in offices The major services / output for the Financial Year 2017/18 were to ensure that all vacant positions or any that may arise is filled with the most suitable candidate without deviating from the laid down recruitment procedures; Enhancement of staff skills and establishment of competence inventory, formulation of county human resource Manual, continuous assessment of compliance to county human resource laws, decentralization of human resource service at sub county and departmental levels.

Key Achievements

Table 10: County Public Service Board Programmes

| Programme Name : Leadership and admin of HR management and development in county public service |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Objective: To improve service delivery in the public sector through increased productivity of human resources |  |  |  |  |  |
| Outcome: Improved service delivery |  |  |  |  |  |
| Sub Programme | Key Outcomes/ outputs | Key performance indicators | Planned Targets | Achieved Targets | Remarks* |
| General Administration and support services | Provision of safety measures relating to personnel documents and other relevant data | Data safety policy | 1 |  |  |
| Human Resource development and management services | Harmonization of salary scales/grades | Standard job groups report | 1 |  |  |
|  | Employee satisfaction report | No. of Employee satisfaction report | 1 |  |  |
|  | Human Resource Management policies and guidelines | Policies and guidelines implemented | 2 |  |  |
|  | Performance management guidelines/tools and Appraisals | Performance management guidelines/tools developed ,approved and implemented | 1 |  |  |
|  | Staff exit to service guidelines and policies | Guidelines formulated | 2 |  |  |
|  | CoK(2010) awareness and compliance report | No. of reports prepared | 2 |  |  |
|  | Disciplinary guidelines in place | guidelines formulated | 1 |  |  |
|  | Induction guidelines in place | Induction guidelines formulated | 1 |  |  |
|  | Staff training and development policy | Policy in place | 1 |  |  |
|  | Upgrading and promotions of officers | No. of officers upgraded and promoted | 100 |  |  |
|  | New appointments | No. of staff appointed | 50 |  |  |
|  | Approval of revised scheme of service | No. of revised schemes of service | 1 |  |  |
|  | Decentralization of services to Sub Counties | Number of functions/Services decentralized at sub county level | 10 |  |  |
|  | Acting and temporary appointments reviewed | No. of officers on acting and temporary appointments | 150 |  |  |
|  | Payroll audit reports | No. of audit reports | 1 |  |  |
|  | Staff motivation | % Reduction of complains from staff | 100 |  |  |

Analysis of Non-Capital projects of the Previous ADP

Table 11: Performance of Non-Capital Projects for County Public Service Board

| Project Name/ Location | Objective/ Purpose | Output | Performance indicators | Status (based on the indicators) | Planned Cost (Ksh.) | Actual Cost (Ksh.) | Source of funds |
| --- | --- | --- | --- | --- | --- | --- | --- |
| General Administration and support services | To improve service delivery in the public sector through increased productivity of human resources | Provision of safety measures relating to personnel documents and other relevant data | Data safety policy |  | 55.4M |  | CGK |
| Human Resource development and management services | To improve service delivery in the public sector through increased productivity of human resources | Harmonization of salary scales/grades | Standard job groups report |  | 45.5 M |  | CGK |
|  |  | Employee satisfaction report | No. of Employee satisfaction report |  |  |  |  |
|  |  | Human Resource Management policies and guidelines | Policies and guidelines implemented |  |  |  |  |
|  |  | Performance management guidelines/tools and Appraisals | Performance management guidelines/tools developed ,approved and implemented |  |  |  |  |
|  |  | Staff exit to service guidelines and policies | Guidelines formulated |  |  |  |  |
|  |  | CoK(2010) awareness and compliance report | No. of reports prepared |  |  |  |  |
|  |  | Disciplinary guidelines in place | guidelines formulated |  |  |  |  |
|  |  | Induction guidelines in place | Induction guidelines formulated |  |  |  |  |
|  |  | Staff training and development policy | Policy in place |  |  |  |  |
|  |  | Upgrading and promotions of officers | No. of officers upgraded and promoted |  |  |  |  |
|  |  | New appointments | No. of staff appointed |  |  |  |  |
|  |  | Approval of revised scheme of service | No. of revised schemes of service |  |  |  |  |
|  |  | Decentralization of services to Sub Counties | Number of functions/Services decentralized at sub county level |  |  |  |  |
|  |  | Acting and temporary appointments reviewed | No. of officers on acting and temporary appointments |  |  |  |  |
|  |  | Payroll audit reports | No. of audit reports |  |  |  |  |
|  |  | Staff motivation | % Reduction of complains from staff |  |  |  |  |

- 2.2.4 Finance, ICT and Economic Planning

The Department is mandated with the preparation of annual estimates of revenues and expenditures including the preparation of supplementary estimates as the need arises. It is the County's think tank responsible for policy analysis on a wide range of issues including: fiscal issues, trade issues and private sector development issues. It also ensures that external resources (grants, loans, donations) are effectively mobilized, disbursed and effectively utilized and that there is prudent public debt management. It is responsible for the administration and enforcement of revenue laws and for that purpose collecting and accounting for all rates, taxes, fees and charges payable by or under any laws in the County; collection of statistical data needed for planning purposes; County budget implementation, monitoring and evaluation.

Strategic priorities

The core mandate of the department is to mobilize public resources and ensure efficient allocation of the resources to the county expenditure priorities for enhanced accountability and service delivery. The sector is also the link of all other sectors with the National government in matters of finance and resource mobilization.

Planned versus allocated budget

Planned budget for the sector was Kshs 1.475B and was allocated Kshs 1.106B.

Key Achievements

Key achievements of the Department are shown in the table below.

Table 12: Finance, ICT & Economic Planning Programmes

| Project/Programme | Objectives | Expected outputs | Indicators | Planned Targets | Achieved Targets | Remarks |
| --- | --- | --- | --- | --- | --- | --- |
| General Administration and support service | Predictable revenue collection and efficient allocation of the resources to the county expenditure priorities | Improved prudence in the management of public resources | Percentage reduction in the incidences of corruption and audit queries No. of officers trained on Public Finance Management No. of staff trained on ISO implementation | 80% 70 35 | 60% 70 0 |  |
|  |  | County Emergency Fund | %Allocation of county emergency fund | 0.5% | 0.5% |  |
|  |  | Mortgage/ Housing for civil servant | Amount Allocated No. of staff accessing mortgage | 100M 50 | 0 0 |  |
|  |  | Staff Health Insurance Fund | Amount allocated No. of staff with medical cover | 10M 50 | 10M 50 |  |
|  |  | Implementation of Revenue administration systems | % implementation of revenue administration systems | 100 | 100 |  |
| Financial management services | Predictable revenue collection and efficient allocation of the resources to the county expenditure priorities | Officers in all department trained on MTEF, programme based budgeting, and implementation of budget | No. of officers trained | 80 | 80 | Program implementation is in progress. |
|  |  | Stakeholders involved in budget making process | No. of stakeholders involved per Sub County | 150 | 150 |  |
|  |  | Budget Prepared and Approved | No. of budget prepared and approved | 1 | - |  |
|  |  | Increased budgetary resources allocated towards development projects | Percentage change towards development expenditure to total budget | 40% | 25% |  |
|  |  | Legal and regulatory framework governing preparation and implementation of budget adhered to | No. of budget circular released | 1 | 1 |  |
|  |  |  | No. of budget Review and outlook paper prepared | 1 | 1 |  |
|  |  |  | No. County Fiscal strategy paper prepared | 1 | 1 |  |
|  |  |  | No. of formulated Appropriation and Finance bill | 2 | 2 |  |
|  |  | Local Sources mobilized | Local revenue mobilised as a percentage of total budget | 38% | 30% |  |
|  |  | Monitoring and evaluation report on local resources mobilized | No. of reports Monthly Quarterly Annually | 12 4 1 | 9 3 0 |  |
|  |  | Revenue Enhancement plan | No. of enhancement plan prepared and implemented | 1 | 0 |  |
|  |  | Establishment of County Revenue Commission | No. of appointment of the commissioners done | 1 | 0 |  |
|  |  | Preparation of Annual procurement | No. of Procurement plan prepared | 1 | 1 |  |
|  |  | General procurement administration | No. of tender committee meeting held | 12 | 9 |  |
|  |  | Accounting systems and Financial regulations reviewed and developed | No. of accounting systems regulations reviewed and developed | 1 | 0 |  |
|  |  | Financial Information and reports produced | No. of reports produced Monthly Quarterly Annually | 12 4 1 | 9 3 0 |  |
|  |  | Risk based audit; Institutional risk management framework rolled out | No. of audit reports | 10 | 10 |  |
|  |  | Audit committees training manuals and regulations | No. of audit committee trained | 1 | 1 |  |
|  |  |  | No. of audit manual developed and implemented | 1 | 0 |  |
| Economic Planning services | Predictable revenue collection and efficient allocation of the resources to the county expenditure priorities | Development of economic policies and Sector specific medium term plans; | No. Of economic policies No. Of sector specific medium term plans developed | 5 10 | 4 1 |  |
|  |  | Research papers under various policy topics Prepared and published | No. Of Research papers developed | 4 | 0 |  |
|  |  | Prepare and produce Quarterly and annual M&E report | No. Of reports prepared | 5 | 2 |  |
|  |  | County Integrated Development plan prepared | No. of County Integrated Development plan prepared | 1 | 1 |  |

Analysis of Capital and Non-Capital projects of the Previous ADP

Table 13:  Performance of Non-Capital Projects for Finance, ICT & Economic Planning

| Project Name/ Location | Objective/ Purpose | Output | Performance indicators | Status (based on the indicators) | Planned Cost (Ksh.) | Actual Cost (Ksh.) | Source of funds |
| --- | --- | --- | --- | --- | --- | --- | --- |
| General Administration and support service | Predictable revenue collection and efficient allocation of the resources to the county expenditure priorities | Improved prudence in the management of public resources | Percentage reduction in the incidences of corruption and audit queries No. of officers trained on Public Finance Management No. of staff trained on ISO implementation | 60% Complete On going Not done | 1,053,356,833 | 790,017,625 | CGK |
|  |  | County Emergency Fund | %Allocation of county emergency fund | complete |  |  |  |
|  |  | Mortgage/ Housing for civil servant | Amount Allocated No. of staff accessing mortgage | Not done Not done |  |  |  |
|  |  | Staff Health Insurance Fund | Amount allocated No. of staff with medical cover | Complete Complete |  |  |  |
|  |  | Implementation of Revenue administration systems | % implementation of revenue administration systems | Complete |  |  |  |
| Financial management services | Predictable revenue collection and efficient allocation of the resources to the county expenditure priorities | Officers in all department trained on MTEF, programme based budgeting, and implementation of budget | No. of officers trained | ongoing | 372,115,000 | 279,086,250 | CGK |
|  |  | Stakeholders involved in budget making process | No. of stakeholders involved per Sub County | Complete |  |  |  |
|  |  | Budget Prepared and Approved | No. of budget prepared and approved | Complete |  |  |  |
|  |  | Increased budgetary resources allocated towards development projects | Percentage change towards development expenditure to total budget | On going |  |  |  |
|  |  | Legal and regulatory framework governing preparation and implementation of budget adhered to | No. of budget circular released | Complete |  |  |  |
|  |  |  | No. of budget Review and outlook paper prepared | Complete |  |  |  |
|  |  |  | No. of County Fiscal strategy paper prepared | Complete |  |  |  |
|  |  |  | No. of formulated Appropriation and Finance bill | Complete |  |  |  |
|  |  | Local Sources mobilized | Local revenue mobilised as a percentage of total budget | Ongoing |  |  |  |
|  |  | Monitoring and evaluation report on local resources mobilized | No. of reports Monthly Quarterly Annually | On going |  |  |  |
|  |  | Revenue Enhancement plan | No. of enhancement plan prepared and implemented | Not done |  |  |  |
|  |  | Establishment of County Revenue Commission | No. of appointment of the commissioners done | Not done |  |  |  |
|  |  | Preparation of Annual procurement | No. of Procurement plan prepared | Complete |  |  |  |
|  |  | General procurement administration | No. of tender committee meeting held | On going |  |  |  |
|  |  | Accounting systems and Financial regulations reviewed and developed | No. of accounting systems regulations reviewed and developed | Not done |  |  |  |
|  |  | Financial Information and reports produced | No. of reports produced Monthly Quarterly Annually | On going |  |  |  |
|  |  | Risk based audit; Institutional risk management framework rolled out | No. of audit reports | On going |  |  |  |
|  |  | Audit committees training manuals and regulations | No. of audit committee trained | Complete |  |  |  |
|  |  |  | No. of audit manual developed and implemented | Not done |  |  |  |
| Economic Planning services | Predictable revenue collection and efficient allocation of the resources to the county expenditure priorities | Development of economic policies and Sector specific medium term plans; | No. Of economic policies No. Of sector specific medium term plans developed | Complete Complete | 50, 000,000 | 37,500,000 | CGK |
|  |  | Research papers under various policy topics Prepared and published | No. Of Research papers developed | Not done |  |  |  |
|  |  | Prepare and produce Quarterly and annual M&E report | No. Of reports prepared | On going |  |  |  |
|  |  | County Integrated Development plan prepared | No. of County Integrated Development plan prepared | Complete |  |  |  |

### 2.2.5 Administration and Public Service

The department had planned to harmonize its public service functions, improve on the departmental structure and realign job descriptions. In addition, the department aimed at developing and implementing various policy documents in support of their functions. To improve service delivery the department planned to refurbish and construct more offices to accommodate its workforce. On human resource development the department planned to train its officers so as to enhance capacity and develop their skills. On coordination of county policy formulation the department aimed at minimizing the number of litigations as well as formulation of county bills and revision of existing county laws. Based on what was planned, the department has been able to formulate various policies some of which are still in draft form awaiting approval for operationalization. The department was able to work on its departmental structure which has improved service delivery. A number of offices have been refurbished and occupied while construction of more offices is ongoing. In order to enhance skills in its workforce, the department has facilitated a number of trainings, workshops and seminars.

Strategic priorities

The core mandate of the department is to ensure there is improved performance, consistent and Harmonized Human Resource Management rules and procedures, optimum use of human resource and implementation of computerized registry.

The major services / output for the Financial Year 2017/18 were to ensure that sub county offices were constructed, increased public participation in county decision making and intensify crackdown on illegal, sub-standard, counterfeit and illicit brews. The county endeavored to put in place rehabilitative and treatment programmes for addicts of alcohol, drugs and substances to ensure that they are fully integrated into the society for socioeconomic development. The department also sought to implement a comprehensive Medical insurance cover for members of staff. It also sought to procure adequate vehicles and funding the sub county offices for effective and efficient operations.

Planned versus allocated budget

Planned budget for the sector was Kshs 726,142,902 and was allocated Kshs 649,080,652. The difference, Kshs 77,062,250 was as a result of underperformance in revenue collection. This resulted in reduced budget allocations for projects.

Key achievements in the previous financial year

The sector’s key achievements were;

- Completion of renovation and operationalization of County head Offices at Kiambu

- Launched a baseline survey report on the status of alcohol and drug abuse in the county. The survey report was later cascaded to the sub county level.

- Enactment and operationalization of the Kiambu County Alcoholic Drinks Control Act, 2018.

- Rehabilitation and treatment sensitization meetings for Sub County Administrators.

- The department of Administration and Public Service successfully moved to Kiambu headquarter offices.

- The department successfully completed the performance contract for the entire department.

- The department of Administration and Public Service has successfully integrated the e-procurement system in its operations.

Human Resource Management and Development

- The sector has established a functional unit responsible for human resource management, headed by Director Human Resource.

- The sector has also facilitated Human Resource Audit initiated by County Executive Committee member for Administration and Public Service.

- The department has also deployed Staff of various cadres with a view to beefing up HR capacity in the Sub Counties.

- Development of Integrated Payroll and Personnel Database which by design accommodate executive and County Public Service Board officers. It aims at monitoring accurate and consistent data in the Public Service.

Enforcement, monitoring and compliance

- The department of Administration and Public Service has continuously enforced the Kiambu Finance Act, 2014 through the enforcement unit.

- The department of Administration and Public Service has enforced the Building code regulations to ensure proper development of buildings in the county

- The department of Administration and Public Service has also enforced the environmental and public health laws with a view to minimizing nuisance to the public.

- The department of Administration and Public Service participated in monitoring and evaluation of road construction to ensure that the county realizes value for money spent on road construction and maintenance.

- The department has successfully conducted all the national days’ celebrations in both the county and the sub counties.

Table 14: Administration and Public Service Programmes

| Programme Name: General Administration and Support services |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Objective: To provide quality administrative services and availing competent skilled and accountable human resource for effective and efficient service delivery. |  |  |  |  |  |
| Outcome: Improved Service delivery |  |  |  |  |  |
| Sub-programme | Key outcomes/ outputs | Key performance indicators | Planned targets | Achieved targets | Remarks |
| Administration services | Harmonized public service functions. | Percentage of duplicated functions eliminated in the public service. | 70% | 40% | Awaiting final SRC report |
|  | Approved service structures & job descriptions manuals | Number of structures approved | 10 | 10 | Complete |
|  |  | Number of approved job description manuals | 1 | 0 | Approval to be based on final SRC report |
|  |  | No. of schemes of service revised | 30 | 0 | Lack of funds. |
|  | Development and implementation of affirmative policy document | No. of affirmative policy developed and implemented | 1 | 0 | Lack of funds |
|  | Employee satisfaction survey | No. of survey reports done | 1 | 0 | Lack of funds |
|  | Construction of ward offices and county headquarters | No. of ward offices constructed | 15 ward offices and 1 headquarter (Kiambu offices) | 15 | Complete |
|  | Coordination of public and special community programmes | No. of public participation and community programmes forums held | 4 | 4 | Enhanced support from stakeholders. |
|  | Implementation of public participation Act | No of public participation acts implemented | 1 | 1 | Already operationalised. |
| Coordination of county policy formulation | Reduced number of litigations | Percentage reduction in litigations | 95% | 70% | Efforts in continuous reduction |
|  | Formulation of county bills and revision of existing county laws | No, of county bills formulated | 4 | 6 | Recruitment of skilled personnel in the department. Alcoholic Drinks Control Bill, 2018 Attorney Office Bill, 2018 enacted. |
|  |  | No. of revised county laws | 3 | 7 | Realisation of gaps in existing laws. |
|  | Drafting of conveyance and contractual documents | No. of conveyance and contractual document drafted | 8 | 30 | Increased efficiency due to improved workforce. |
|  | Assessment of compliance of county laws | % reduction of cases of non-compliance | 97% | 80% | Increased efficiency due to improved workforce |
|  | Investigation of complaints | No. of complaints investigated | 3% | 20% | Enhanced mechanisms of handling complaints and feedback. |
|  | Decentralization of county services | No. of functions/services decentralized at sub county level | 2 | 2 | Liquor licensing decentralised to sub county level Public participation up to Ward level |
|  | Staff skills and competence | No. of relevant officers trained | 5 | 50 | Continuous |
|  |  | Skills and competences inventory | 100% | 40% | Continuous |
| Human resource development and management | Capacity building | No. of training needs identified | 50 | 40 | Ongoing |
|  | Training needs assessment | No of training needs identified | 50 | 40 | Ongoing |
|  | Staff redeployment | No. of staffs redeployed | 50 | 50 | Continuous |
|  | Group personal insurance | No. of staffs insured | 4200 | 2000 | Ongoing |

Analysis of Capital and Non Capital projects of the previous ADP

During the 2017/18 ADP, the department achieved the following;

Capital Projects:

- Construction of Juja sub county offices.

- Refurbishment of offices at county headquarters.

- Purchase of motor vehicles, purchase of generator and stabilisers for Kiambu headquarters, construction of generator room at Kiambu headquarters.

Non Capital projects:

- Conducting Public and special community programmes

- Formulation of Public Participation and Citizen Petition Act, other County bills and revision of existing laws

- Implementation of Group personal insurance for county staff

- Redeployment of staff

Table 15: Performance of Capital Projects for Administration and Public Service

| Project name/ Location | Objective / Purpose | Output | Performance indicators | Status based on the indicators | Planned cost (Kshs) | Actual Cost (Kshs) | Source of funds |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Construction of Juja sub county offices | To improve public service delivery | Offices constructed | Number office block constructed | Ongoing | 49M | 13M | CGK |
| Refurbishment of offices at county headquarters | To enhance service delivery | Refurbished offices | Number of office block refurbished | Complete | 16M | 14.3M | CGK |
| Purchase of motor vehicles | To enhance service delivery | Vehicles purchased | Number of vehicles purchased | Complete | 198M | 198M | CGK |
| Purchase of generator and stabiliser for Kiambu Headquarters | To ensure uninterrupted power supply | Generators and stabilisers purchased | Number of generators and stabilisers purchased | Complete | 5.6M | 4.4M | CGK |
| Construction of a generator room | To ensure security and safety of the generator | Generator room constructed | Number generator room constructed | Complete | 1.3M | 0.995M | CGK |

Table 16: Performance of Non capital projects for Administration and Public Service

| Project name/ Location | Objective / Purpose | Output | Performance indicators | Status based on the indicators | Planned cost (Kshs) | Actual Cost (Kshs) | Source of funds |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Public and special community programmes | To Coordinate public participation and special programmes | Public participation forums held. | Number of public participation forums held. | Complete | 6.8M | 6.8M | CGK |
| Public participation and Citizen Petition Act | To implement public participation and citizens’ petition act | Public Participation Act implemented | Number of Public Participation Acts formulated | complete | 2M | 2M | CGK |
| County bills and existing laws | To formulate county bills and revise existing county laws | County bills formulated and laws revised. | Number of county bills formulated and laws revised. | Ongoing | 2M | 2M | CGK |
| Group personal insurance | To ensure workers are compensate incase of work related injury | Affected officers compensated. | Number of workers compensated. | Ongoing | 52M | 36.5M | CGK |

### 2.2.6 Agriculture, Crop Production, Irrigation & Marketing

Strategic priorities

The department had planned to develop one agricultural information resource centre at Waruhiu ATC, establish agro-processing cottage industries for value addition, facilitate farmers to access subsidized fertilizers, assist groups with avocado value addition equipment, procure and distribute soil testing kits to sub counties, development of root crops, promotion of legumes, fruit trees and oil crops, promotion of smart agriculture, soil conservation, training of farmers, promotion of  drip irrigation and appropriate greenhouse farming technology and promotion of water harvesting. Most of the projects are ongoing.

Sector priority was given to irrigation, banana collection centres, agro processing equipment for fruits, vegetables and honey. On crop development conservation Agriculture was to take the lead, followed by Coffee, Tea, Macadamia, Horticulture improvement

Planned versus Allocated Budget

Planned budget for the sector was Kshs 314.125M and was allocated Kshs 362.58M.

Key achievements

Major achievements included:

Crop production

- Sunflower production was promoted in 10 sub counties where 800kg of sunflower was procured and planted.

- Drought tolerant crop varieties; 5 tonnes of drought tolerant certified seeds were distributed to farmers

- The county in collaboration with the nation Government were able to procure and distribute seeds   worth 5.7M to Thika, Juja. Kikuyu and Limuru Sub Counties

- Establishment of 9 plant clinics and training of 32 plant doctors in collaboration with CABI.

Irrigation

- Initiation of 9 irrigation projects namely Kamwamba, Gatina, Wamoro, Kawira, Kiruiru, Nyamuku, Karia and Waruhiu ATC,

- Construction of 2 water pans Kimunyu and Waruhiu ATC

- Designing of 2 irrigation projects Njuno and Chiboni Githongo.

Agribusiness

- Establishment  of one grading shed/collection centre

- Establishment of banana hardening nurseries

- Distribution of subsidized fertilizers to farmers

Other achievements are summarized in table 12.

Table 17: Agriculture, Crop Production, Irrigation & Marketing Programmes

| Programme Name : Administration, Planning and support services |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Objective: To enhance effective and efficient service delivery |  |  |  |  |  |
| Outcome: Enhanced effective and efficient service |  |  |  |  |  |
| Sub Programme | Key Outcomes/ outputs | Key performance indicators | Planned Targets | Achieved Targets | Remarks* |
| Administration services | Information desks equipped and operationalized | Number of information desks equipped and operationalized | 60 | 0 | On going |
|  | An agricultural information centre established and equipped at Waruhiu ATC | Number of agricultural information centres established and equipped | 1 | 0 | On going |

| Programme Name : Agribusiness and information management |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Objective: To enhance agricultural productivity |  |  |  |  |  |
| Outcome: Increased agricultural income |  |  |  |  |  |
| Sub Programme | Key Outcomes/ outputs | Key performance indicators | Planned Targets | Achieved Targets | Remarks* |
| Value addition and agro processing of agricultural produce | Avocado value addition equipments availed to groups | Number of Avocado value addition equipments availed to groups | 6 groups | 0 | On going |
|  | A pineapple agro processing outlet established | Number of pineapple agro processing outlets established | 1 | 0 | On going |
|  | Groups assisted with fruits and vegetable processing equipment | Number of groups assisted with fruits and vegetable processing equipment | 1 | 2 | On going |
|  | Coffee mill established for a farmer group | Number of Coffee mill established for a farmer group | 1 | 1 | On going |
|  | Deep freezers purchased for fish marketing outlets | Number of deep freezers purchased for fish marketing outlets | 4 | 4 | On going |
|  | Grading sheds or collection centres developed | Number of grading sheds or collection centres developed | 3 | 1 | ongoing |
| Agricultural inputs and financing | Farm inputs warehouse established | Number of farm input warehouses established | 1 | 0 | Ongoing |
|  | Farmers accessing subsidized Fertilizer | Number of farmers accessing subsidized fertilizer | 10,000 | 30,000 | Ongoing Farmers increased awareness of the fertilizer and easy access through mini depots |
| Agribusiness market and development | Banana hardening nurseries established | Number of banana hardening nurseries established | 10 | 5 | ongoing |

| Programme Name Crop Development and Management |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Objective: To enhance crop productivity and increase incomes |  |  |  |  |  |
| Outcome: Increased crop yield household incomes and food security |  |  |  |  |  |
| Sub Programme | Key Outcomes/ outputs | Key performance indicators | Planned Targets | Achieved Targets | Remarks* |
| Land and crop management and productivity enhancement | Soil testing kits purchased and distributed | Number of soil testing kits purchased and distributed | 13 | 0 | Ongoing |
|  | Irish potato certified seeds bulking site established | No of bulking sites established | 10 | 0 | Ongoing |
|  | Cassava and sweet potato bulking sites established | No of bulking sites established | 12 | 0 | Ongoing |
|  | Farmers producing Stevia | No of farmers producing Stevia | 500 | 0 | Ongoing |
|  | Maize and beans certified Seed purchased and distributed | Kilograms of seed purchased and distributed | Maize12000 Beans 15000 | 11632 14540 | Ongoing |
|  | Avocado Mango nurseries established | No of nurseries established | 12 | 0 | Ongoing |
|  | Sunflower and soya beans and Macadamia seeds purchased and distributed | Kgs of sunflower and soya beans and Macadamia seeds purchased and distributed | Sunflower 1000 Soya bean 4500 Macadamia 2 | 800 4000 0 | Ongoing |
|  | KM pegged KMs of terraces and CODs constructed | KMs pegged KMs of terraces and CODs constructed | 1000 6000 | 0 | Ongoing |
| Irrigation development and management | Farmers benefitting from Njuno irrigation project | Number of farmers benefitting from Njuno irrigation project | 10 | 0 | Ongoing |
|  | Households benefitting from Karia irrigation project | Number of households benefitting from Karia irrigation project | 400 | 0 | Ongoing |
|  | Households benefitting from Gatina irrigation project | Number of households benefitting from Gatina irrigation project | 500 | 75 | ongoing |
|  | Women groups provided with drip irrigation systems and greenhouses | Number of women groups provided with drip irrigation systems and greenhouses | 6 | 0 | Ongoing |
|  | water pan designed and Constructed- Mathuri | Number of water pans designed and constructed | 1 | 0 | Ongoing |
|  | Households benefitting from Kamwamba irrigation project | Number of households benefiting from Kamwamba irrigation project | 900 | 0 | ongoing |
|  | Trainings conducted | No of trainings conducted | 20 | 0 | Ongoing |
| Promoting Smart Agriculture | demonstration sites established | Number of demonstration sites established | 100 | 0 | Ongoing |
| Upgrading of Waruhiu Agricultural Training Centre(ATC) | Pulping units completed | Number of pulping units completed | 1 | 0 | Ongoing |
|  | -valley dams completed | Number of valley dams completed | One valley reservoir dam capacity 20,000m3 | 0 | Ongoing |
|  | self contained rooms constructed | number of self contained rooms constructed | 10 | 0 | Ongoing |
|  | 80 person capacity dining hall completed | Number of 80 person capacity dining hall completed | 1 | 0 | Ongoing |
|  | Service road murramed and maintained | meters of service road murramed and maintained | 400m | 0 | Ongoing |
| Revitalization of Agricultural Mechanization Services (AMS)-Ruiru | Design and survey dams | water pans/ dams constructed | 2 | 0 | Ongoing |
|  | Plant and machinery repaired | No of plant and machinery repaired | 3 | 0 | Ongoing |
|  | New equipment and implement acquired Automation of survey and design | mould board plough disc plough/disc harrow planter/ Ridger Tall station | 1 1 1 1 | 0 0 0 0 | Ongoing |

Analysis of Capital and Non-Capital projects of the Previous ADP

Table 18: Performance of Capital Projects for Agriculture, Crop Production, Irrigation & Marketing

| Project Name/ Location | Objective/ Purpose | Output | Performance Indicators | Status (based on the indicators) | Planned Cost (Ksh.) | Actual Cost (Ksh.) | Source of funds |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Development of grading shed for agricultural produce at Bibirioni, Ikinu and Kijabe | Aggregation of agricultural produce | Grading sheds established | Number of grading sheds established | 1 | 10M | 3.2 M | CGK |
| Farm inputs warehouse in Thika | Aggregation of agricultural produce | Farm inputs warehouse established | Number of inputs warehouse established | 0 | 20M | 0 | CGK |
| Establishment of tissue culture banana hardening nurseries in Kiambu, Lari, Githunguri and Gatundu South | Increased access to quality planting materials | Banana hardening nurseries constructed | Number of hardening nurseries constructed | 5 | 4M | 3.67M | CGK |
| Coffee mill in Gatundu South | Value addition of coffee | Coffee mill established and operationalized | Number of coffee mill established and operationalized | 0 | 6M | 0 | CGK |
| Soil testing Kits in all subcounties | To increase soil productivity | Soil testing kits purchased and distributed | Number of soil testing kits purchased and distributed | 0 | 2.6 M | 0 | CGK |
| Design and Construction of Njuno irrigation project- Kiambaa | To provide water to farmers for irrigation purpose | Farmers benefitting from Njuno irrigation project | Number of farmers benefitting from Njuno irrigation project | 0 | 10M | 0 | CGK |
| Karia irrigation project-Githunguri | To provide water to farmers for irrigation purpose | Farmers benefitting from Karia irrigation project | Number of farmers benefitting from Karia irrigation project | 0 | 5M | 0 | CGK |
| Gatina irrigation project-Githunguri | To provide water to farmers for irrigation purpose | Farmers benefitting from Gatina irrigation project | Number of farmers benefitting from Gatina irrigation project | 0 | 4.5M | 0 | CGK |
| Drip irrigation and Green house farming technology promotion- Lari, Kiambaa, Kiambu, Githunguri, Gatundu South, Thika | To promote Drip irrigation and appropriate Green house farming technology | Women groups provided with drip irrigation systems and greenhouses | Number of women groups provided with drip irrigation systems and greenhouses | 0 | 5M | 0 | CGK |
| Mathuri water pan | To harvest rain water for irrigation and other farm activities | water pan designed and constructed | Number of water pans designed and constructed | 0 | 9.5M | 0 | CGK |
| Design and construction of Kamwamba irrigation projects-Chania ward | To provide water to farmers for irrigation purpose | Households benefitting from Kamwamba irrigation project | Number of households benefiting from Kamwamba irrigation project | 0 | 4M |  | CGK |
| Coffee pulper installation at Waruhiu ATC | Pulping cherry to parchment to improve value through direct sales | Pulping units completed | Number of pulping units | 0 | 1.5M | 0 | CGK |
| Water Valley Reservoir dam and pumping works at Waruhiu ATC | Water harvesting for domestic and irrigation | -valley dams completed | - Number of valley dam completed | 0 | 9M | 0 | CGK |
| Hostel expansion at Waruhiu ATC | Improved capacity for residential training | self contained rooms constructed | number of self contained rooms constructed | 0 | 3.8M | 0 | CGK |
| Dining hall and kitchen expansion/ renovation at Waruhiu ATC | Enhance catering services at the centre | 80 person capacity dining hall completed | Number of 80 person capacity dining hall completed | 0 | 3.5M | 0 | CGK |
| On farm service road murram | To facilitate efficient on farm operation | Service road murramed and maintained | meters of service road murramed and maintained | 0 | 1.5M | 0 | CGK |
| Promote development of agricultural infrastructure | Developed water storage structures agricultural resource base maintained | Design and survey dams | No of dams surveyed and designed | 0 | 3.3M | 0 | CGK |
| Conserved environment and sustainable land use | To facilitate efficient on farm operation | Plant and machinery repaired | No of plant and machinery repaired | 0 | 0.45M | 0 | CGK |
| Increased adoption of farm mechanization technologies | Increased production per unit area efficient production system achieved | New equipment and implement acquired Automation of survey and design | Mould board plough procured 1 disc plough/disc harrow procured Planter/Ridger procured Total station | 0 0 0 0 | 0.7M 0.45M 0.35M 1.5M | 0 0 0 0 | CGK |

Table 19: Performance of Non-Capital Projects for Agriculture, Crop Production, Irrigation & Marketing

| Project Name/ Location | Objective/ Purpose | Output | Performance indicators | Status (based on the indicators) | Planned Cost (Ksh.) | Actual Cost (Ksh.) | Source of funds |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Equipping of information desks in all wards | Enhanced extension services to farmers | Information desks equipped | Number of information desks equipped | 0 | 5 M | 0 | CGK |
| Developing one agricultural information resource centre at Waruhiu | Enhanced extension services to farmers | agricultural information centre developed | Number of agricultural information centre developed | 0 | 2M | 0 | CGK |
| Avocado value addition equipment in Githunguri, Kiambu and Gatundu North | Promote commercialization of avocadoes Reduced post harvest losses | value addition equipment availed to groups for agro-processing | Number of value addition equipment availed to groups for agro-processing | 0 | 5M | 0 | CGK |
| Pineapple agro processing outlet at Githobokoni | Reduced post harvest losses | Value addition equipments availed to groups for agro-processing | Number of value addition equipments available for groups for agro-processing | 0 | 4M | 0 | CGK |
| Fruits and vegetable processing equipment Lari and Limuru | Promote commercialization of vegetables Reduced post harvest losses | Value addition equipments availed to groups for agro-processing | Number of value addition equipments availed to groups for agro-processing | 0 | 5M | 0 | CGK |
| Crops development improvement in all sub counties | Promotion of Irish potato, Cassava and sweet potato production | Irish potato certified seeds bulking site established | No of bulking sites established | 0 | 0.5M | 0 | CGK |
|  | Promotion of Traditional High Value crops | Cassava and sweet potato bulking sites established | No of bulking sites established | 0 | 2M | 0 | CGK |
|  | To promote stevia production | Farmers producing Stevia | No of farmers producing Stevia | 0 | 2M | 0 | CGK |
| Promotion of legumes- at Ruiru, Thika, Juja, Limuru, Kikuyu | To promote use of certified seeds | Maize and beans certified Seed purchased and distributed | Kilograms of seed purchased and distributed | 0 | 6M | 5.67M | CGK |
| Promotion of fruit trees at Gatundu, Kiambu, Thika, Juja, Lari, Limuru) | To increase production | Avocado Mango nurseries established | No of nurseries established | 0 | 6M | 0 | CGK |
| Promotion of oil crops at Thika, Juja | to diversify income generating enterprises | Sunflower and soya beans and Macadamia seeds purchased and distributed | Kgs of sunflower and soya beans and Macadamia seeds purchased and distributed | 0 | 2M | 0 | CGK |
| Farmers and front line staff training on irrigation, drainage and soil and water conservation technology | To educate and train farmers on irrigation, drainage and soil and water conservation technology | Trainings conducted | No of trainings conducted | 0 | 2M | 0 | CGK |
| Promoting Smart Agriculture | To establish demonstrations on smart Agriculture | Demonstration sites established | Number of demonstration sites established | 0 | 5M | 0 | CGK |

### 2.2.7 Water, Environment, Energy and Natural Resources

Planned versus allocated budget

Planned budget for the sector was Kshs 608,838,983 and was allocated was allocated Kshs 608,838,983.

Key Achievements

Table 20: Water, Environment, Energy and Natural Resources Programmes

| Programme Name : Administration, Planning and support services |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Objective: To enhance effective and efficient service delivery |  |  |  |  |  |
| Outcome: Enhanced effective and efficient service |  |  |  |  |  |
| Sub Programme | Key Outcomes/ outputs | Key performance indicators | Planned Targets | Achieved Targets | Remarks* |
| Administration services | Increased mobility and adequate enforcement and surveillance | No of New vehicles purchased | 2 | 0 | ongoing |
|  | Adequate enforcement and surveillance | No of vehicles Repaired and serviced |  |  | ongoing |
|  | Improved working Environment | Constructions of new offices and | 12 | 0 | Ongoing |
|  |  | No of offices rehabilitated and equipped | 12 | 0 | ongoing |
| Personnel services | Improve service delivery | No.of staff Trained | 6 | 6 | 0ngoing |
|  |  | Number of new staffs Recruited | 3 | 3 | Complete |
|  |  | Number of staffs registered with professional bodies | 2 | 2 | complete |

| Programme Name: Water resources management and sanitation |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Objective: To provide adequate, affordable, safe clean water and sanitation services |  |  |  |  |  |
| Outcome: Increased access to clean and safe water |  |  |  |  |  |
| Sub Programme | Key Outcomes/ Outputs | Key performance indicators | Planned Targets | Achieved Targets | Remarks* |
| Water policy development and management | Improved water and sanitation management | No of policies drafted and developed | 1 | 0 | Ongoing |
|  | Reduction, eliminate negative Advanced impact | Specialization and gaps filled EIA /EA is carried out in in some of the projects implemented | 25 | 19 | 12 complete and 7 ongoing |
| Water resources conservation protection and sewerage | Reliable source of quality water | No of the catchment areas protected | 5 | 1 | 0ngoing |
|  |  | Kms of the river riparian where trees are planted | 30 | 5 | ongoing |
|  | Mapping by pegging riverlines | Kms of Rivers mapped and pegged | 150 | 0 | ongoing |
|  | Improved sanitation services | Kms of sewer lines constructed | 114 | 73 | Ongoing |
|  | Raise standards of sanitation services | Number of renovated and rehabilitated sanitation blocks | 10 | 7 | Ongoing |
|  |  | No of new sanitation blocks constructed | 12 | 8 | Ongoing |
|  | Improvement in sanitation services | No of sewage Exhausters procured | 12 | 5 | ongoing |
|  | Enhance compliance on standards and ensure safe quality water and Environment | No of laboratory constructed and operationalized | 8 | 1 | Ongoing |
| Water storage and flood control | Increased access to water supply | Pans constructed | 3 | 1 | ongoing |
|  | Institutions or special groups supplied with the storage tanks | No. of tanks supplied to institutions or special groups | 200 | 160 | Ongoing |
|  | Provision of adequate storage | Constructed storage tanks either ground or elevated | 8 | 6 | Ongoing |
| Water supply infrastructures | Land acquisition / compensation | No of compensation done | 1 | 0 | Ongoing |
|  | Improved water accessibility | No of Boreholes drilled | 25 | 19 | Ongoing |
|  | Improved water accessibility | No of km laid with pipes | 7 | 5 | Ongoing |
|  | Improved water accessibility to informal settlement | No of water kiosk s | 4 | 3 | Ongoing |
|  | Efficient and accurate ground water results | No of modern ground water investigation instrument Procured | 1 | 0 | Ongoing |
|  | Accurate and efficient survey data establishment | No of surveying equipment units procured | 1 | 0 | Ongoing |
|  | Enhance awareness on county project | No of signage erected | 25 | 17 | Ongoing |

| Programme Name: Environment Management and protection |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Objective: To enhance clean environment |  |  |  |  |  |
| Outcome: Reduced Environmental pollution and degradation |  |  |  |  |  |
| Sub Programme | Key Outcomes/ outputs | Key performance indicators | Planned Targets | Achieved Targets | Remarks* |
| County Environmental monitoring and management | Improved environmental monitoring management | No of environmental committee in place | 1 | 1 | Ongoing |
|  |  | No of GIS systems in place | 1 | 1 | Ongoing |
| Environmental management policy | Environmental policies in place | No. of policies developed and institutionalized | 4 | 2 | Ongoing |
|  | Establishment of county environment committee | Institutionalized county environment committee | 1 | 1 | Ongoing |
| Solid waste management | Clean environment | No. of waste management hub constructed | 1 | 1 | Ongoing |
|  |  | No of Waste segregation unit constructed | 1 | 1 | Ongoing |
|  |  | No. of a skip loaders procured | 1 | 1 | Complete |
|  |  | No. of skips procured | 20 | 13 | Ongoing |
|  |  | No. of decommissioned and rehabilated open dumpsites | 1 | 0 | Ongoing |
| Environmental Education and Awareness’ | Increased Environmental Awareness’ | No. of Eco schools established | 60 | 18 | Ongoing |
|  |  | No of awareness campaigns held | 12 | 11 | Ongoing |

Analysis of Capital and Non-Capital projects of the Previous ADP

Table 21: Performance of Capital Projects for Water, Environment, Energy & Natural Resources

| Project Name/ Location | Objective/ Purpose | Output | Performance Indicators | Status (based on the indicators) | Planned Cost (Ksh.) | Actual Cost (Ksh.) | Source of funds |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Rehabilitation of ground masonary Nyathuna water project | Improved water storage | Reliable storage of Water. | No of ground masonary rehabilitated | ongoing | 1.5M | 1,301,700 | CGK |
| Rehabilitation of Thika town garage toilet | Improved sanitation |  | No of rehabilitated toilets | ongoing | 1.2M | 1,056,946 | CGK |
| Complete construction of water intake, Karinde in Kikuyu | Improve water quality from the swamp and provide a pumping source | Wide diameter well developed | No of wide diameter well developed | ongoing | 4M | 3,983,984 | CGK |
| Drilling of large diameter well at Ondiri. | Improve water quality from the swamp and provide a pumping source | Wide diameter well developed | No of wide diameter well developed | ongoing | 3M | 2,948,081 | CGK |
| Distribution Network for Roromo BH project | Improve water quality from the swamp and provide a pumping source | Wide diameter well developed | No of wide diameter well developed | ongoing | 4M | 3,976,850 | CGK |
| Reticulation system for Mbioni BH project | Improve water quality from the swamp and provide a pumping source | Wide diameter well developed | No of wide diameter well developed | ongoing | 4M | 3,982,682 | CGK |
| Development of Kambara Karia and Gathiri springs in Karuri | Improve water quality from the swamp and provide a pumping source | Wide diameter well developed | No of wide diameter well developed | ongoing | 4M | 3,993,980 | CGK |
| protection of Mbauini and Karaini spring | Improve water quality from the swamp and provide a pumping source | Wide diameter well developed | No of wide diameter well developed | ongoing | 4M | 3,993,980 | CGK |
| Drilling and equipping of Boreholes in Karuri at Karura and Kiriaini | Improved access to safe drinking water and sanitation | Increase water coverage area, Improved access to safe drinking water and sanitation | BH drilled and equipped | ongoing | 4M | 3,993,980 | CGK |
| Drilling, equipping of Borehole at Mbioni for Limuru water Company | Improved access to safe drinking water and sanitation | Increase water coverage area, Improved access to safe drinking water and sanitation | BH drilled and equipped | ongoing | 4M | 3,969,864 | CGK |
| Drilling, equipping of Borehole at Lari (Ass Commissioner's office) Limuru water | Improved access to safe drinking water and sanitation | Increase water coverage area, Improved access to safe drinking water and sanitation | BH drilled and equipped | ongoing | 4M | 3,969,864 | CGK |
| Construction of 225 m3 masonary tank for Mbiuni and Nderu water projects in Limuru | To have a large water reservoir. | Volume of water produced. | No of large water reservoir. | ongoing | 4M | 3,976,560 | CGK |
| Construction of storage tank in Karai | Improved water storage | Reliable storage of Water. | No of water storage | ongoing | 4M | 3,994,867 | CGK |
| Procurement and distribution of 10No plastic water storage tanks for community water projects (24,000 Ltrs capacity) | Improved water storage | Reliable storage of Water. | No of water storage | ongoing | 0.5M | 198,000 | CGK |
| Procurement and distribution of 30No.plastic rain water harvesting tanks for institutions (10,000 Ltrs capacity) | Improved water storage | Reliable storage of Water. | No of water storage | ongoing | 1.5M | 1,291,790 | CGK |
| Procurement and distribution of 60No.plastic rain water harvesting seed tanks for individuals (10,000 Ltrs capacity) | Improved water storage | Reliable storage of Water. | No of water storage | ongoing | 1.3M | 1,286,872 | CGK |
| Construction of proposed Kinale dam | Improved water storage | Reliable storage of Water. | No of water reservoir constructed | ongoing | 2M | 1,755,000 | CGK |
| Construction of Ultra Filtration Unit in four areas, with raw and clean water reservoirs. | To meet the water quality standard is met. | Quality of water produced. |  | ongoing | 1.1M | 1,039,005 | CGK |
| Extension of distribution of sewer lines for, Kiambu, Githunguri,Kikuyu,Thika, Limuru | To improve sewer services to the community. | A complete sewer line done. | No. of KM of sewer lines installed. No. of people connected to sewer lines. |  | 2M | 1,813,537 | CGK |
| • A segregation unit at Kang’oki landfill to be in place a full operation semi-aerobic landfill at Kang’oki • upscale compositing facility at Kang’oki. • -Rehabilitate and decommissioned Kangoki open dumpsite | To establish Integrated solid waste management within Kiambu county | Constructed Integrated solid waste management | No of Integrated solid waste management | Ongoing |  |  | CGK |
| Procurement of skips | To improve garbage collection and management at collection centres | improve garbage collection and management | No. Skips procured | ongoing | 3.5M | 3.25M | CGK |
| Construction of public sanitation facilities with bio digesters in market centers within kiambu county | To increase public access to sanitation services | Improved public sanitation | No of sanitation facilities constructed | Ongoing |  |  | CGK |
| Rehabilitation of public sanitation facilities within Kiambu county | To increase public access to sanitation services | Improved public sanitation | No of rehabilitated and Improved sanitation facilities | Ongoing |  |  | CGK |

Table 22: Performance of Non-Capital Projects for Water, Environment, Energy & Natural Resources

| Project Name/ Location | Objective/ Purpose | Output | Performance indicators | Status (based on the indicators) | Planned Cost (Ksh.) | Actual Cost (Ksh.) | Source of funds |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Trees Planted in catchment and river lines conservation | To conserve river lines | Conserved river lines | No of trees planted in catchment and river lines conservation | ongoing | 10M | 0.36 M | CGK |
| Tree planting in public schools | To enhance tree cover | Increased forest cover | No of trees planted in public schools | ongoing |  | 0.18M | CGK |
| Tree planting in public open space | To enhance tree cover | Increased forest cover | No of trees planted in open spaced | ongoing |  | 3.182M | CGK |
| Urban forestry and beautification | To enhance beautification and urban forestry | Enhanced Urban forestry and beautification | No of county parks and urban open spaces are fenced, lit, mown and watered •no of All major roads sides planted with grass, flowers and trees and shrubs | ongoing |  | 3.119M | CGK |
| Establishment and improvement of county tree nursery | To establish tree seedlings nurseries | Established and improved of county tree nursery | • No. of nurseries established and rehabilitated • No. of tree seedlings in the nurseries | ongoing |  | 0.159 | CGK |

### 2.2.8 Health Services

In the year 2017/18, the department of health planned its targets around the six health policy objectives and made some significant achievements. In order to eliminate communicable conditions disease surveillance, deworming, screening and provision of essential drugs were done.

To halt and reverse increasing burden of non-communicable diseases, screening, community outreaches, treatment and establishment of a renal-dialysis centre and an ICU section in Thika Level 5 hospital were done. To reduce the burden of violence and injuries, the department established an emergency medical services unit. To provide essential medical services, community outreaches, patient education and provision of essential drugs was done. To minimise exposure to health risk factors, there has been active provision of contraception, community outreaches and health education. In order to strengthen collaboration, the department signed several MOUs with development partners and held stakeholder meetings.

In order to ensure a motivated workforce, it ensured remuneration of 2653 health workers and promotion of 1589 staff. Public relations were improved through establishment of customer care desks in all the sub counties. To improve the condition in the facilities, renovations were done.

Strategic Priorities

The strategic priorities for the year 2017/2018 were:

- Community health services

- Physical infrastructure

- Outreach services

- Recruitment and training of new staff

- Procurement of health products

- Information dissemination

- Health Education

- Supportive supervision

- Resource mobilization

- On job training

- Data collections

- Emergency preparedness planning

- Intersectoral collaboration

- Training needs assessment

- Staff training

Planned versus allocated budget

The Health budget for the year 2017/18 was KES 4,527,542,312. After the first supplementary budget amounted to KES 4,449,758,564. There is a proposal to receive more allocation of KES 160,000,000, while the cumulative expenditure was KES 2,692,679,450.

Key Achievements

Some of the key achievements during the 2017/2018 plan period are as summarized in table 18.

Table 23: Health Services Programmes

| Programme Name: Administration and Planning Programme |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Objective: To ensure effective and efficient health service delivery |  |  |  |  |  |
| Outcome: An improved health service delivery system that motivates the workforce to achieve set targets |  |  |  |  |  |
| Sub Programme | Key Outcomes/ outputs | Key performance indicators | Planned Targets | Achieved Targets | Remarks* |
| Health Workforce | Efficient and effective service delivery | No. of staff promoted | 2269 | 1589 | 680 –short fall due to inadequate funds |
|  |  | No. of staff taken through Continuous Medical Educations(CME)done | 2653 | 2653 |  |
|  |  | No. of staff remunerated promptly | 2500 | 2500 |  |
|  |  | No. of staff recruited(All cadres) | 1000 | 266 | 734-shortfall due to inadequate funds |
| Health Commodities and technologies | Continuous supply throughout the year | Amount of money allocated | 415M | 368M | Shortfall of 47M due to shortage of funds |
| Health Information system | Fully automated level 5,4 and 3 facilities | No. of facilities fully automated | 35 | 0 | Lack of funds |
|  |  | No. of facilities installed with HMIS | 35 | 35 |  |
| Health Leadership and governance | Improved public relations | No. of Customer care desks established and operationalized | 12 | 12 |  |
|  | Improved planning for service delivery | No. of plans developed and reviewed(AWP,MTEF,CIDP,ADP) | 4 | 4 |  |
|  | Achieve good governance and management of facilities | No. of Management committees and boards formed | 107 | 94 | 13-Health Act 2014 under review |
| Health Financing | Ensure smooth running and operations in Health services | Amount of funds allocated | 4,527,542,312 | 4,449,758,564 | 77,783,748 |
| Health Research and Development | Establishment and operationalization of the Research Unit | % level of establishment | 100% | 50% | Established but not yet fully operational |
| Health Infrastructure | Improved access to health services as per the WHO standards | No. of renovated facilities | 28 | 25 | 3 are ongoing |
|  |  | No. of Constructed facilities | 17 | 5 | Variance due to limited finances |

| Programme Name: Curative Services |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Objective: To ensure effective and efficient health service delivery |  |  |  |  |  |
| Outcome: An improved health service delivery system that motivates the workforce to achieve set targets |  |  |  |  |  |
| Sub Programme | Key Outcomes/ outputs | Key performance indicators | Planned Targets | Achieved Targets | Remarks* |
| Health Service delivery | Improved primary health care, screening of NCDs and curative services | % of under-five immunized | 100% | 90% | Ongoing |
|  |  | % of 4th ANC visits achieved | 100% | 60% | -Shortfall caused by inadequate theatre services -Ongoing |
|  |  | % of under 5 children supplemented | 70%(national) | 69% | Ongoing |
|  |  | No. of medical camps done | 12 | 8 | Ongoing |
|  |  | No. of endoscopy centers established | 1 | 1 |  |
|  |  | No. of pathology centers established | 1 | 1 | Ongoing |
|  |  | No. of ICU and renal centers established | 6 | 2 | Ongoing (Gatundu level 5) |

Analysis of Capital and Non-Capital projects of the Previous ADP

Table 24: Performance of Capital Projects for Health Services

| Projects Name/ Location | Objective/ Purpose | Output | Performance Indicators | Status (Based on the Indicators) | Planned Cost (Ksh) | Actual Cost (Ksh) | Source of Funds |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Construction of surgical theatre at Lusigetti level 4 hospital | To provide the surgical services | A fully equipped theatre | No. of theatres constructed | Completed | 11,598,890 | 11,598,890 | County government of Kiambu |
| Construction of surgical theatre at Lari level 4 hospital | To provide the surgical services | A fully equipped theatre | No. of theatres constructed | 95% complete | 11,586,370 | 11,956,674 | County government of Kiambu |
| Renovation and refurbishment of theatre, kitchen and laundry at Karatu level 4 hospital | To enable provision of surgical, kitchen and laundry services | A fully equipped theatre, kitchen and laundry | No. of hospitals renovated and refurbished | Ongoing- 70% complete. | 4,206,170 | 0 | County government of Kiambu |
| Completion of patient toilet block at Lusigetti level 4 hospital | To increase sanitary facilities | A completion ablution block | No. of patient toilet blocks completed | Ongoing – 65% complete | 2,700,000 | 0 | County government of Kiambu |
| Renovation and refurbishment of Nyayo male ward (phase I) at Kiambu level 5 hospital | To make the ward more hospitable to the patients and staffs | Renovated wards | No. of wards renovated and refurbished | Complete | 3,996,500 | 3,996,500 | County government of Kiambu |
| Renovation and refurbishment of Nyayo male ward (phase II) at Kiambu level 5 hospital | To make the ward more hospitable to the patients and staffs | Renovated wards | No. of wards renovated and refurbished | Complete | 3,016,420 | 3,016,420 | County government of Kiambu |
| Refurbishment and renovation of OPD and fence at Mundoro dispensary | To improve hospitability of the patients ,general outlook and security | Renovated OPD and erected fence | No. of dispensaries refurbished and renovated | Complete | 3,993,585 | 3,993,585 | County government of Kiambu |
| Refurbishment and renovation of OPD, fence and maternity at Mutonya dispensary | To improve hospitability of the patients ,general outlook and security | Renovated OPD and erected fence | No. of dispensaries refurbished and renovated | Ongoing | 4,000,000 | 0 | County government of Kiambu |
| Expansion of MCH at Ndenderu dispensary | To increase the working space for the MCH services | Provision of maternal and child health services | No. of MCH blocks expanded | Ongoing | 2,650,000 | 0 | County government of Kiambu |
| Expansion of MCH at Kamae dispensary | To increase the working space for the MCH services | Provision of maternal and child health services | No. of MCH blocks expanded | Ongoing | 3,500,000 | 0 | County government of Kiambu |
| Expansion of MCH at Juja farm health centre | To increase the working space for the MCH services | Provision of maternal and child health services | No. of MCH blocks expanded | Ongoing | 2,600,000 | 0 | County government of Kiambu |
| Construction of RH unit Thika at level 5 hospital | To improve reproductive health services | Increased and improved reproductive health services | No of reproductive health units constructed | Ongoing- 92% complete | 667,395,434 | 766,002,030 | County government of Kiambu |
| Construction of wards at Wangige level 4 hospital | To increase bed capacity of the hospital | Increased inpatient services | No. of wards constructed | Ongoing – 38% complete. | 220,292,842 | 140,000,000 | County government of Kiambu |
| Construction of level 4 hospital at Kikuyu level 4 hospital | To increase bed capacity of the hospital | Increased inpatient services | No. of wards constructed | Ongoing- 44% complete | 210,787,424 | 142,000,000 | County government of Kiambu |
| Construction of wards at Lari level 4 hospital | To increase bed capacity of the hospital | Increased inpatient services | No. of wards constructed | Ongoing – 40% complete. | 191,807,805 | 122,000,000 | County government of Kiambu |
| Construction of 200 bed capacity wards at Tigoni level 4 hospital | To increase bed capacity of the hospital | Increased inpatient services | No. of wards constructed | Ongoing- 70% complete | 160,740,400 | 152,000,000 | County government of Kiambu |
| Construction of perimeter wall and gate at Gatundu level 4 hospital | To improve security to the hospital | Well secured health facility | % completion of perimeter wall and gate | 54% complete | 18,000,000 | 16,892,650 | County government of Kiambu |
| Construction of a connecting walkway from theatre to OPD and ward in Lusigetti level 4 hospital | To improve patient and staff movement in the facility | Covered walkways | No of connecting walk ways constructed | Completed | 1,200,000 | 1,200,000 | County government of Kiambu |
| Construction of a connecting walkway from theatre to OPD and ward in Lari level 4 hospital | To improve patient and staff movement in the facility | Covered walkways | No of connecting walk ways constructed | Completed | 1,000,000 | 1,000,000 | County government of Kiambu |
| Renovation and refurbishment of fence, gate and laboratory in Maguguni dispensary | To improve hospitability of the patients ,general outlook and security | Renovated laboratory and erected fence | No. of dispensaries renovated and refurbished | At Procurement stage | 3,500,000 | 0 | County government of Kiambu |
| Completion of dispensary (Lari CDF) in Githirioni dispensary | To move the current dispensary to the new site | An operational dispensary | % completion of dispensary | Ongoing | 4,400,000 | 0 | County government of Kiambu |
| Completion of dispensary (Lari CDF) in Uplands dispensary | To move the current dispensary to the new site | An operational dispensary | % completion of dispensary | Ongoing | 3,900,000 | 0 | County government of Kiambu |
| Completion of dispensary (Lari CDF) in Kamuchege dispensary | To move the current dispensary to the new site | An operational dispensary | % completion of dispensary | Ongoing | 1,500,000 | 0 | County government of Kiambu |
| Renovation of maternity unit in Githunguri health centre( Ruiru) | To improve maternal health services | Improved maternal health services | No. of maternity units renovated | Ongoing | 3,096,200 | 0 | County government of Kiambu |
| Construction of perimeter wall in Githunguri health centre( ruiru) | To improve the security of the facility | Improved security within the facility | % completion of perimeter wall | Ongoing | 3,165,250 | 0 | County government of Kiambu |
| Construction of patient toilet block at Gichuru dispensary | To increase sanitary facilities in the facility | Improved sanitation | No. of patient toilet blocks constructed | Ongoing | 2,512,330 | 0 | County government of Kiambu |
| Construction of patient toilet block at Karia health centre | To increase sanitary facilities in the facility | Improved sanitation | No. of patient toilet blocks constructed | Ongoing | 2,267,100 | 0 | County government of Kiambu |
| Construction of patient toilet block at Thigio dispensary | To increase sanitary facilities in the facility | Improved sanitation | No. of patient toilet blocks constructed | Complete | 2,161,423 | 2,161,423 | County government of Kiambu |
| Construction of patient toilet block at Githunguri health centre | To increase sanitary facilities in the facility | Improved sanitation | No. of patient toilet blocks constructed | Ongoing | 2,241,800 | 0 | County government of Kiambu |
| Construction of patient toilet block at Kamuchege dispensary | To increase sanitary facilities in the facility | Improved sanitation | No. of patient toilet blocks constructed | Ongoing | 2,433,150 | 0 | County government of Kiambu |
| Completion of CDF dispensary and fencing at Kamuchege dispensary | To move the dispensary to a new site | An operational dispensary | % completion of dispensary | Ongoing | 3,413,765 | 0 | County government of Kiambu |
| Construction of patient toilet block and refurbishment of OPD at Ting’ang’a dispensary | To increase sanitary facilities and hospitability of the facility | Improved sanitation and improved OPD services | No. of patient toilet blocks constructed and OPD units refurbished | Ongoing | 3,153,490 | 0 | County government of Kiambu |
| Construction of perimeter wall (phase 1) at Ting’ang’a dispensary | To improve security in the facility | Improved security | % completion of perimeter wall | Ongoing | 3,440,190 | 0 | County government of Kiambu |
| Construction of perimeter wall (phase 2) at Ting’ang’a dispensary | To improve security in the facility | Improved security | % completion of perimeter wall | At Procurement stage | 2,538,704 | 0 | County government of Kiambu |
| Construction of patient toilet block at Kerwa dispensary | To increase sanitary facilities in the facility | Improved sanitation | No. of toilet blocks constructed | BQ ready Awaiting site hand over | 2,512,330 | 0 | County government of Kiambu |
| Construction of base and supply and installation of 10,000 water tanks in Gatundu south sub county | To improve the harvesting of rain water in facilities | Improved water rain harvesting in health facilities | Number of water tanks installed | Ongoing | 2,000,000 | 0 | County government of Kiambu |
| Construction of base and supply and installation of 10,000 water tanks in Gatundu north sub county | To improve the harvesting of rain water in facilities | Improved water rain harvesting in health facilities | Number of water tanks installed | Ongoing | 2,000,000 | 0 | County government of Kiambu |
| Construction of base and supply and installation of 10,000 water tanks in Juja sub county | To improve the harvesting of rain water in facilities | Improved water rain harvesting in health facilities | Number of water tanks installed | Ongoing | 2,000,000 | 0 | County government of Kiambu |
| Construction of base and supply and installation of 10,000 water tanks in Thika sub county | To improve the harvesting of rain water in facilities | Improved water rain harvesting in health facilities | Number of water tanks installed | Ongoing | 2,000,000 | 0 | County government of Kiambu |
| Construction of base and supply and installation of 10,000 water tanks in Ruiru sub county | To improve the harvesting of rain water in facilities | Improved water rain harvesting in health facilities | Number of water tanks installed | Ongoing | 2,000,000 | 0 | County government of Kiambu |
| Construction of base and supply and installation of 10,000 water tanks in Kiambu sub county | To improve the harvesting of rain water in facilities | Improved water rain harvesting in health facilities | Number of water tanks installed | Ongoing | 2,000,000 | 0 | County government of Kiambu |
| Construction of base and supply and installation of 10,000 water tanks in Kiambaa sub county | To improve the harvesting of rain water in facilities | Improved water rain harvesting in health facilities | Number of water tanks installed | Ongoing | 2,000,000 | 0 | County government of Kiambu |
| Construction of base and supply and installation of 10,000 water tanks in Githunguri sub county | To improve the harvesting of rain water in facilities | Improved water rain harvesting in health facilities | Number of water tanks installed | Ongoing | 2,000,000 | 0 | County government of Kiambu |
| Construction of base and supply and installation of 10,000 water tanks in Limuru sub county | To improve the harvesting of rain water in facilities | Improved water rain harvesting in health facilities | Number of water tanks installed | Ongoing | 2,000,000 | 0 | County government of Kiambu |
| Construction of base and supply and installation of 10,000 water tanks in Lari sub county | To improve the harvesting of rain water in facilities | Improved water rain harvesting in health facilities | Number of water tanks installed | Ongoing | 2,000,000 | 0 | County government of Kiambu |
| Construction of base and supply and installation of 10,000 water tanks in Kikuyu sub county | To improve the harvesting of rain water in facilities | Improved water rain harvesting in health facilities | Number of water tanks installed | Ongoing | 2,000,000 | 0 | County government of Kiambu |
| Construction of base and supply and installation of 10,000 water tanks in Kabete sub county | To improve the harvesting of rain water in facilities | Improved water rain harvesting in health facilities | Number of water tanks installed | Ongoing | 2,000,000 | 0 | County government of Kiambu |
| Renovation and refurbishment of OPD at Ngeteti dispensary | To improve the services and hospitability of the facility | Improved services in the facility | No. of OPD units renovated and refurbished | Ongoing | 2,729,005 | 0 | County government of Kiambu |
| Construction of fence at Ngeteti dispensary | To improve the security of the facility | Improved security in the facility | % completion of fence and gate | Ongoing | 1,731,420 | 0 | County government of Kiambu |
| Renovation and refurbishment of OPD at Mbici dispensary | To improve the services and hospitability of the facility | Improved services in the facility | No. of OPD units renovated and refurbished | At BQ preparation stage | 2,500,000 | 0 | County government of Kiambu |
| Construction of a dispensary at Gitaru dispensary | To have a new health facility in the area | A new dispensary | No. of dispensaries constructed | At BQ preparation stage | 12,000,000 | 0 | County government of Kiambu |
| Renovation works and construction of fence and gate at Kinoo dispensary | To improve the security of the facility | Improved security in the facility | % completion of fence and gate | At BQ preparation stage | 1,613,395 | 0 | County government of Kiambu |
| Construction of a dispensary at Muthiga dispensary | To have a new health facility in the area | A new dispensary | No. of dispensaries constructed | At BQ preparation stage | 12,000,000 | 0 | County government of Kiambu |
| Construction of a dispensary at Kiawaroga dispensary | To have a new health facility in the area | A new dispensary | No. of dispensaries constructed | At BQ preparation stage | 12,000,000 | 0 | County government of Kiambu |
| Construction of a dispensary at Kawaida dispensary | To have a new health facility in the area | A new dispensary | No. of dispensaries constructed | At BQ preparation stage | 12,000,000 | 0 | County government of Kiambu |
| Construction of fence and gate and refurbishment of OPD building at Karai muslim dispensary | To operationalize a dispensary | To have a functional health facility | % completion of fence and gate No. of OPD units refurbished | Ongoing | 2,000,000 | 0 | County government of Kiambu |
| Renovation works of the maternity at Gituamba community dispensary | To improve maternal health services | Improved maternal health services | No. of maternity blocks renovated | Complete | 261,000 | 261,000 | County government of Kiambu |
| Construction of the perimeter wall and gate and incinerator at Gikambura dispensary | To improve security and health care waste disposal | Improved security and health care waste disposal | % completion of perimeter wall and incinerator | At BQ preparation stage | 5,200,000 | 0 | County government of Kiambu |
| Renovation of maternity and construction of waiting bay at Gikambura dispensary | To improve maternal health services | Improved maternal health services | No. of maternity blocks renovated | Ongoing | 3,000,000 | 0 | County government of Kiambu |
| Renovation works of maternity in Gichuru dispensary | To improve maternal health services | Improved maternal health services | No. of maternity blocks renovated | At BQ preparation stage | 2,500,000 | 0 | County government of Kiambu |
| Construction of razer security on the perimeter wall at Githurai-lang’ata health centre | To improve the security of the facility | Improved security in the facility | % completion of razer security perimeter wall | complete | 200,000 | 0 | County government of Kiambu |
| Construction of a level 4 hospital in Bibirioni area | To provide a new health facility | Operational health facility | No of health facility constructed | Procurement stage | 230,000,000 | 0 | County government of Kiambu |
| Upgrade of Githunguri health centre to a level 4 hospital | Upgrade of Githunguri health centre to a level 4 hospital | A level 4 centre of excellence for mental health, oncology and orthopaedic | No of health centres upgraded | Procurement stage | 780,000,000 | 676,000,000 | County government of Kiambu |
| Construction 36 body modern mortuary in Gatundu level 5 hospital | To improve mortuary services | An ultra-modern funeral home | No of ultra-modern funeral home constructed | Procurement stage | 50,000,000 | 0 | County government of Kiambu |

Table 25: Performance of Non-Capital Projects for Health Services

| Project Name/ Location | Objective/ Purpose | Output | Performance indicators | Status (based on the indicators) | Planned Cost (Ksh.) | Actual Cost (Ksh.) | Source of funds |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Cervical cancer screening county wide | To enhance cervical screening | Distribution of EVA devices | No of devices distributed | 50 devices distributed | 14M | 14M | County government of Kiambu |
| Conduct community based outreaches county wide | Revive community based outreaches using Beyond zero truck | No of outreaches conducted | No of outreaches conducted | 72 outreaches conducted | 18M | 18M | County government of Kiambu |

### 2.2.9 Education, Culture & Social Services

The department has endeavored to fulfill its mandate by making various interventions through the 3 Sub Sectors. Notable achievements include the successful roll out of the ‘Uji’ program in all the public ECDE Centers, construction, refurbishment and equipping of new Polytechnics and ECDE centers, distribution of sanitary towels, assistive devices and blankets, disbursement of bursary grants, socio-economic empowerment of Self Help Groups i.e. Women/Youth and PWDs. Among the challenges experienced include resource constraints, a prolonged campaign period which affected implementation of the planned projects, lack of credible data to guide planning and lack of legislation, inadequate office space and office equipment, anxiety among staff due to change of leadership, lack of vehicles for field work and very high expectations from members of the public among others. Moving forward, the department plans to be more active in public participation forums in a bid to manage their expectations, lobbying for more resources, forging partnerships and prioritizing the projects to be implemented.

Strategic priorities

The department has prioritized to increase enrolment in ECDEs and polytechnics, expanded school feeding programme to ensure that ALL the children are included, ensuring that quality and relevant training is happening in the Vocational Training Centers, conservation of heritage and management of cultural and historical sites, mapping and gazettement of those sites, social protection and welfare of the vulnerable members of society and gender and disability mainstreaming.

Key achievements

11 ECDE centers were constructed and renovated, 6 youth polytechnics are under construction while 3 YPs were renovated. 100 more ECDE caregivers were recruited, instructional materials worthy 7M were procured for ECDEs. ALL ECDE centers were integrated into the feeding programme.35 polytechnic trainees were placed for internship with various industries across the region. Enrolment in both ECDEs and YPs increased. Kshs 60,000,000 was disbursed as bursary to needy and vulnerable students across the county. Blankets, sanitary towels and assistive devices were distributed. The department supported cultural groups in participating in the Kenya Music and Cultural Festivals.

Table 26: Education, Culture & Social Services Programmes

| Programme name : Education, Culture and Social Services |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Outcome: |  |  |  |  |  |
| Sub Programme | Key Outcomes/ Outputs | Key performance indicators | Planned Targets | Achieved Targets | Remarks* |
| General Administration and Support Services | Capacity building forum held | No. of capacity building forums | 4 | 1 | Ongoing |
|  |  | No. of officers capacity built | 50 | 120 | ongoing |
|  | Trade shows and exhibitions | No. of trade shows | 2 | 1 | ongoing |
|  |  | No. exhibitions held | 2 | 1 | ongoing |
| Pre-Primary Education and Youth Polytechnics | Workshops constructed and refurbished | No of constructed and renovated workshops. | 15 | 10 | On going |
|  | Instructors recruited | No of instructors recruited | 60 | 15 | Ongoing |
|  | ECDE centers under feeding program | No. of ECDE centers under feeding Programme | 493 | 510 | Ongoing |
|  | ECDE centers provided with learning materials | No. of ECDE centers provided with learning materials | 120 | 120 | complete |
|  | Capacity building | No. of ECDE teachers and care givers capacity built | 1500 | 1047 | Ongoing |
|  | ECDE teachers recruited | No of ECDE teachers recruited | 1500 | 1047 | Ongoing |
|  | ECDE centers monitored and evaluated | No of ECDE centers monitored and evaluated | 493 | 200 | Ongoing |
| Culture, Gender and Social Services | Capacity building | No of residents reached | 1200 | 1200 | Complete |
|  | Life skills training | No of trainings held | 12 | 6 | Ongoing |
|  | Rehabilitation centers constructed | No. of rehabilitation centers constructed | 1 | 0 | Ongoing |
|  | Sensitization programmes | No of sensitization sessions held | 12 | 12 | Complete |
|  | social halls equipped | No. of halls equipped | 3 | 3 | Complete |
|  | trainings held | No of trainings held | 4 | 2 | Ongoing |
|  | Sanitary pads purchased | No of sanitary pads purchased | 96,000 | 96,000 | complete |
|  | Music and cultural festivals | No of music and cultural festivals | 24 | 18 | ongoing |
|  | Exhibitions and workshops | No of workshop and exhibition held for visual artists | 2 | 1 | Ongoing |
|  | Mwomboko teams formed | No of Mwomboko teams formed | 4 | 2 | Ongoing |
|  | Drama festivals held | No of drama festivals conducted | 13 | 12 | ongoing |
|  | County cultural committee formed | No. of County cultural committees formed | 1 | 1 | Complete |
|  | Cultural center rehabilitated | No. of Cultural centers rehabilitated | 1 | 1 | complete |

Analysis of Capital and Non-Capital projects of the Previous ADP

Capital projects; Construction, renovation and refurbishment of classrooms and workshops, equipping renovated existing social halls, Purchase of modern tools and equipment, Construction of rehab center and Equipping of matron’s house at Jamhuri Children’s Home.

Non capital projects; Capacity building for ECDE teachers, Quality assurance, Child care and feeding program, Capacity building of staff, Tradeshows and exhibitions, Recruitments of instructors, Recruitment of ECDE teachers and Alcohol, drug and substance abuse.

Table 27: Performance of Capital Projects for Education, Culture, & Social Services

| Project Name/ Location | Objective/ Purpose | Output | Performance Indicators | Status (based on the indicators) | Planned Cost (Ksh.) | Actual Cost (Ksh.) | Source of funds |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Construction, renovation and refurbishment of classrooms and workshops | To Improve learning environment and increase enrollment | New and improved classrooms and workshops | No of classrooms, workshops and social halls refurbished and renovated | Ongoing | 190,000,000 | 60,000,000 | CGK |
| Modern tools and equipment | To improve the quality of education | Tools and Equipment purchased | No. of tools and equipment purchased.. | Ongoing | 170,000,000 | 20,000,000 | CGK |
| Construction of rehab center | To reduce alcohol and drug abuse among victims | Rehab center constructed | No of rehab centers constructed | stalled | 10,000,000 | 0 | CGK |

Table 28: Performance of Non-Capital Projects for Education, Culture, & Social Services

| Project Name/ Location | Objective/ Purpose | Output | Performance indicators | Status (based on the indicators) | Planned Cost (Ksh.) | Actual Cost (Ksh.) | Source of funds |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Capacity building for ECDE teachers | To enhance skills, knowledge and quality service | Staff trained | No. of staff trained | ongoing | 2,000,000 | 1,000,000 | CGK |
| Quality assurance | To improve the quality of ECDE and polytechnics | ECDE and Youth Programmes centers assessed | No. of ECDE and Youth Programme centers assessed for quality assurance and standards | On going | 1,000,000 | 1,000,000 | CGK |
| Child care and feeding program | To Improve health, learning and wellbeing of ECDE going children | ECDE pupils benefiting from nutrition program | No. of ECDE centers under feeding Programme | Complete | 60,000,000 | 60,000,000 | CGK |
| Capacity building of staff Tradeshows and exhibitions | To enhance skills and knowledge To increase public awareness and informed decision making | Capacity building forums held Tradeshows and exhibitions held. | Number of capacity building held No. of tradeshows and exhibitions held | Ongoing Ongoing | 3,500,000 5,000,000 | 2,000,000 2,400,000 | CGK |
| Recruitments of instructors | To improve the quality of education | Instructors recruited | The No. of instructors recruited | Ongoing | 65 | 1 | CGK |
| Recruitment of ECDE teachers | To improve the quality of education | ECDE teachers recruited | The No. of ECDE teachers recruited | Ongoing | 100 | 25 | CGK |
| Alcohol, drug and substance abuse | To reduce the level of alcohol and drug abuse in the county | Less cases of alcohol and drug abuse reported | Number of alcohol and drug abuse cases reported | Ongoing | 100 | 100 | CGK |

### 2.2.10 Youth and Sports

The department embarked on youth empowerment through capacity building and skill enhancement, registration and participation of county staff teams with various sports federations, affiliation of county team with relevant sports federation, equipping county teams with sportswear and loans to youth women and people with disability through Kiambu enterprise fund.

Strategic priorities

The department embarks on:  training and funding of county teams, establishment of county sports academy, construction and rehabilitation of sporting facilities, formulation of a sports management, legislative policy to govern sporting activities in the county, identification and nurturing of sporting talent in the county, creating a conducive environment for growth and development of small and medium enterprise sector,  new brand of entrepreneurs to undertake activities such as road construction, repair and maintenance, water drilling and distribution systems, create jobs through direct investment in agriculture and agro-processing.

Key Achievements

The department disbursed non-interest loans to twelve thousand youth, women and people with disability, held champions cup tournament and distributed uniforms to 2,160 teams all over the county, constructed Ruiru, Gikambura and Kagwe Astroturf fields, held skill enhancement trainings all over the county and constructed Kirigiti amphitheater.

Table 29: Youths and Sports Programmes

| Program: Sports |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Objective: To develop and promote a sporting culture in the County through identification, nurturing sports talents, developing and upgrading sports infrastructure. |  |  |  |  |  |
| Outcome: Increased participation of the youths and sporting activities |  |  |  |  |  |
| Sub Program | Key Outcomes/ outputs | Key performance indicators | Planned Targets | Achieved Targets | Remarks* |
| Ruiru stadium | One state of the art stadium | Percentage completion | 100% | 30% | ongoing |
| Limuru stadium | One State of the art stadium. | Percentage completion | 30% | 20% | ongoing |
| Thika stadium | One State of the art stadium with a tartan track | Percentage completion | 30% | 10% | ongoing |
| Kirigiti stadium | One State of the art stadium | Percentage completion | 20% | 0% | ongoing |
| Athletics | One hundred athletes selected and sponsored | Number of athletes | 100 | 100 | Complete |
| Kicosca tournament | Improved sports competition in the county | Number of athletes selected and sponsored | 450 | 450 | Complete |
| Repair and maintenance of sports facilities | Well maintained and operational sports facilities | Number of sports field repaired and maintained | 4 stadiums and 60 sports field | 4 stadiums and 40 sports field | Ongoing |
| Kiambu all stars and starlets football clubs | Two teams sponsored | Number of teams sponsored | 2 teams | 2 teams | Complete |
| Purchase of sports equipment | Teams supplied with sport equipment | Number of teams supplied with equipment | 144 teams | 144 teams | Complete |

| Program: Youth |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Objective: To develop and promote a sporting culture in the County through identification, nurturing sports talents, developing and upgrading sports infrastructure. |  |  |  |  |  |
| Outcome: Increased participation of the youths and sporting activities |  |  |  |  |  |
| Sub Program | Key Outcomes/ outputs | Key performance indicators | Planned Targets | Achieved Targets | Remarks* |
| Kirigiti amphitheater/Kiambu talent academy | One Amphitheatre | Percentage completion | 30% | 20% | Ongoing |
| Youth technical skills enhancement and capacity building | Five trainings and capacity building offered | Number of trainings and capacity building held | 11 | 5 | Ongoing |

Analysis of Capital and Non-Capital projects of the Previous ADP

Capital projects: Upgrade of Thika stadium, Limuru stadium, ruiru stadium, one field per ward and construction of amphitheater.

Non capital projects: Youth technical skills enhancement and capacity building

Table 30: Performance of Capital Projects for Youths and Sports

| Project Name/ Location | Objective/ Purpose | Output | Performance Indicators | Status (based on the indicators) | Planned Cost (Ksh.) | Actual Cost (Ksh.) | Source of funds |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Ruiru stadium | To promote sports | One state of the art stadium | Percentage completion | ongoing | 50,000,000 | 32,823,265 | KCG |
| Limuru stadium | Promote sports, engage youths to reduce crime rate | One state of the art stadium. | Percentage completion | ongoing | 30,000,000 | 11,910,000 | KCG |
| Thika stadium | To promote sports. | One state of the art stadium with a tartan track | Percentage completion | ongoing | 35,000,000 | 14,529,230 | KCG |
| Kirigiti stadium | Promote sports, engage youths to reduce crime rate | One state of the art stadium | Percentage completion | ongoing | 100M | Nil | KCG |
| Repair and maintenance of sports facilities | Improved technical skills to youths | Well maintained and operational sports facilities | Number of sports field repaired and maintained | ongoing | 15.M | 10M | KCG |
| Amphitheatre Kirigiti | Improve youth engagement and tapping of talent | One Amphitheatre | Percentage completion | Ongoing | 80.M | 40M | KCG |

Table 31: Performance of Non-Capital Projects for Youths and Sports

| Project Name/ Location | Objective/ Purpose | Output | Performance indicators | Status (based on the indicators) | Planned Cost (Ksh.) | Actual Cost (Ksh.) | Source of funds |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Youth technical skills enhancement and capacity building | To empower youths | No. of youths trained | 4500 youths trained | Ongoing | 10M | 6.5M | KCG |

### 2.2.11 Lands, Physical Planning & Housing

The department had planned to hire qualified and competent staffs, conduct research and innovation on emerging urbanization and developments dynamics, prepare integrated strategic urban development plan (ISUDPS), prepare advisory plans/ part development plans (PDP) per sub county, ensure safety and compliance audit of buildings , draft legislative bills, take possession and secure public land, establish GIS based land Information Management System (LIMS), enhance land rates revenue, improve informal settlement and prepare county spatial plan.

Strategic priorities

- Preparation of county spatial plan

- Preparation of integrated strategic urban development plan

- Updating of county land information   system (LIMS) through addition of various attributes

- Slum upgrading

- Updating of the valuation Roll.

- Identification Surveying &obtaining of title deed for public land

Planned versus allocated budget

The planned budget for the sector was KSHS 258.9M and was allocated KSHS 372,643,380.

Key Achievements

Land Management & Physical Planning

- The department prepared four (4) bills namely County Physical Planning Bill, County Valuation and Rating Bill, County Survey and mapping Bill and County Housing bill. One bill was completed and the other three are in draft form awaiting approval.

- The department prepared one County Spatial plan and 12 Integrated Strategic Urban Development Plans (ISUDPs).The preparation process of the plans is still ongoing. The ISUDPs’ projects are funded by the World Bank, and are being implemented through the departments of Urban Development Department (UDD) and Nairobi Metropolitan Service Improvement Programme (NaMSIP).

The department has been able to achieve efficiency in Service Delivery through;

- Harmonization of the approval process and enhanced revenue generation.

- E-Development Application and Management Systems (e-DAMS) has been embraced for the purposes of enhancing service delivery, promoting transparency and accountability.

- Sensitization workshops through print media and land clinics in Kikuyu, Juja, Karuri, Kabete Sub-Counties to enhance create awareness and good perception of the public on departmental matters.

- Preparation of Kiambu county draft Valuation rolls

- Preparation for land database for area rating

- Valuation for land acquisition purposes

- Setting up of GIS which has enhanced inventory of public land and mapping of sub-county wards and headquarters, health centres and stadiums.

Housing Development

- The county was able to pay pending bills for the renovation of County Depot Flats in Thika Block 9/108

- We were able to take inventory of county houses, urban Renewal and partial completion of renovation works for departmental headquarters at Red Nova.

- We had Promotion of slum upgrading initiatives such as support of on-going project on mapping informal settlements, being implemented through KISIP and KENSUP and the complete project in Shauri Yako slum, Kikuyu sub-county.

- The land department headquarters at Red Nova was fully fitted with a Local Area Network (LAN) and Telecoms to aid in quick service delivery at the offices to people

Table 32: Lands, Physical Planning and Housing Programmes

| Programme Name: General Administration and support Services |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Objective: To improve service delivery |  |  |  |  |  |
| Outcome: Improved efficiency and effectiveness in service delivery |  |  |  |  |  |
| Sub Programme | Key Outcomes/ outputs | Key performance indicators | Planned Targets | Achieved Targets | Remarks* |
| Personnel | Staffs hired and retained | Number of staffs hired and retained | 2deputy directors 6 professional staffs 8technicians 12 support staff |  | Ongoing |
|  | Training programmes, conferences, peer forums and team building activities attended | Number of Training programmes, conferences, peer forums and team building activities attended | 2SLDP 5 SMC 5Administrative 2prosecution course 4 conferences |  | Ongoing |

| Programme Name: Planning, Land Survey and Mapping |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Objective: To provide an overall spatial framework for the county to guide development |  |  |  |  |  |
| Outcome: Updated, spatial plans and maps for the county |  |  |  |  |  |
| Sub Programme | Key Outcomes/ outputs | Key performance indicators | Planned Targets | Achieved Targets | Remarks* |
| County Spatial Planning and Development | Integrated Strategic Urban Development Plans (ISUDPs) prepared and launch | Number of Integrated Strategic Urban Development Plans (ISUDPs) prepared and launch | 6 | 50% | Ongoing |
|  | Part Development Plan (PDPs) completed | Number of Part Development Plan (PDPs) completed | 24 | 12 | Ongoing |
|  | Legislative bills drafted and tabled in the county assembly | Number of Legislative bills drafted and tabled in the county assembly | 4 | 4 | 1 complete and 3 in draft form awaiting approval |
|  | Houses properly designed , safe and pre-approved | Number of houses properly designed , safe and pre-approved | 2BR units 3BR units 4BR units |  |  |
|  | County planning technical committee meetings held | Number of County planning technical committee meetings held | 12 |  | Ongoing |
| Valuation of county property | Properties captured and valued for rating purposes | Number of Properties captured and valued for rating purposes | 200,000 properties | 8,050 properties | Ongoing |

| Programme Name: County Urban Planning and Housing |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Objective: To ensure sustainable urban growth and development |  |  |  |  |  |
| Outcome: Livable well managed urban areas with adequate, safe, decent and affordable housing |  |  |  |  |  |
| Sub Programme | Key Outcomes/ outputs | Key performance indicators | Planned Targets | Achieved Targets | Remarks* |
| Audit and renovation of county duty and rental residential houses and office spaces | Houses and offices audited and renovated | Number of house and offices audited and renovated | 500 Audited 114 renovated | 30 | Ongoing |
|  | Neighborhood meetings, land clinics / barazas and exhibitions conducted | Number of Neighborhood meetings, land clinics / barazas and exhibitions conducted | 24 meetings/clinics 2exhibitions |  | Ongoing |
|  | Up to date existing and ongoing building inventories in place | Number of Up to date existing and ongoing building inventories in place | 12 |  | Ongoing |
| Feasibility studies | Studies carried out and reports prepared | Number of studies carried out and reports prepared | 1 on infrastructural provisions 1 on urban renewal and development |  | Ongoing |

| Programme Name: Planning, Land Survey and Mapping |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Objective: To provide an overall spatial framework for the county to guide development |  |  |  |  |  |
| Outcome: Updated, spatial plans and maps for the county |  |  |  |  |  |
| Sub Programme | Key Outcomes/ outputs | Key performance indicators | Planned Targets | Achieved Targets | Remarks* |
| County Land Survey, Mapping, Boundaries establishment | Land parcels surveyed | Number of land parcels surveyed | 36 market centers |  | Ongoing |
|  | Survey maps and land record digitized | Number of Survey maps and land record digitized | 300,000 parcels of land | 10,000 | Ongoing |
|  | Land boundary disputes resolved and parcels secured | Number of Land boundary disputes resolved and parcels secured | 250 | 100 | Ongoing |
|  | Public land plots identified | Number of public land plots identified | 200 | 50 | Ongoing |
|  | Portfolio or inventory of physical assets established | Number of Portfolio or inventory of physical assets established | Initial portfolio with 10,000 physical assets |  | Ongoing |
| County Informal settlement upgrading | Slums upgraded | Number of slums upgraded | 3 | 3 | complete |
|  | Research and innovation proposal done on emerging urbanization and development dynamics | Number of research and innovation proposal done on emerging urbanization and development dynamics | 2 |  | Ongoing |

### 2.2.12 Trade, Tourism, Co-operative and Enterprise Development

During the planning period 2017 / 2018 the Department of Trade, Tourism, Cooperatives and Enterprise Development did not achieve most of the targets due to inadequate financing and lack of a clear guide on how to achieve the set targets. Moving forward the Department aims at having a Strategic Plan to guide the Annual Budgeting Process based on realistic targets.

Key Achievements

Trade

- Refurbishment of two offices occupied by the CEC for Trade and CO for Trade

- Construction of  TWO (2) Boda Boda sheds

- Refurbishment and Renovation of 8 existing markets whereby one is complete – Kamwangi Market others are  ongoing namely Madaraka, Jamuhuri and Ruaka

Co-operatives

- Managed to mobilize and register 40 co-operatives Societies hence membership increment and is still ongoing

- Increment of share capital from Kshs 4.6B to Kshs 5.1.B

- Turnover increment from Kshs 15.5B to Kshs 17B

Tourism

- Promotion of tourism in Kiambu county through,

  - Partnered with the Kenya Tourism Fund to hold the first  County Tourism Stakeholders forum( attended by over 300 stakeholders)

  - Partnered with the Kenya Tourism Fund to carry out profiling of some of our hospitality facilities.

  - Partnered with Fairview coffee estate to host the international coffee day celebrations

  - Participation in the Kenya Tourism week in Kilifi ( got some visitors to 14 falls as a result)

- Rehabilitation of tourism sites e.g.

  - Construction of ablution block at 14 falls ( 80% complete)

  - Construction of ablution block at Mathore view point ( 80% complete)

Table 33: Trade, Tourism, Co-operative and Enterprise Development Programmes

| Programme Name: Administration, Planning and Support Services |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Objective: To improve Service Delivery |  |  |  |  |  |
| Outcome: Improved efficiency and effectiveness in service delivery |  |  |  |  |  |
| Sub Programme | Key Outcomes/ Outputs | Key performance indicators | Planned Targets | Achieved Targets | Remarks* |
| Construction of office blocks | Office constructed | No. of Office blocks | 1 | Nil | Lack of funding |
| Refurbishment of Office Blocks | Refurbishment of Office Blocks | No. of office Blocks Refurbished | 10 | 2 | Ongoing |
| Programme Name: Trade Development and Promotion |  |  |  |  |  |
| Objective: To promote and Develop Trade |  |  |  |  |  |
| Outcome: Increased contribution to employment, FDIs and Export Leading to increased income |  |  |  |  |  |
| Sub Programme | Key Outcomes/ Outputs | Key performance indicators | Planned Targets | Achieved Targets | Remarks* |
| Establishment and construction of new Markets | Markets Constructed | No. of Markets Constructed | 7 | 1 | Ongoing |
| Establishment of Boda Boda Sheds | Boda Boda Sheds constructed | No. of Boda Boda Sheds constructed | 120 | 2 | Ongoing |
| Refurbishment and renovation of existing markets | No of markets refurbished and renovated | No. of markets refurbished and renovated | 24 | 4 | Ongoing |
| Establishment of Modern Model Kiosks | Modern Model Kiosks established | No. of Modern Model Kiosks established | 240 | Nil | No funds |
| Verification and inspection of weighing and measuring equipment | Verification and inspection of weighing and measuring equipment in place | % increase in No. of measuring and weighing equipment verified and inspected | 30% | 15% | Ongoing |

| Programme Name: Enterprise Development |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Objective: To promote enterprises in the county |  |  |  |  |  |
| Outcome: Increased contribution to employment, FDI and Export to enhanced income |  |  |  |  |  |
| Sub Programme | Key Outcomes/ Outputs | Key performance indicators | Planned Targets | Achieved Targets | Remarks* |
| Support Training on Value addition among MSME s, Co-operatives, Tourism and Business Groups | MSMEs capacity built | no of MSMEs trained on Value Addition and M&E reports | 120 | 105 | Ongoing |
| Participating in Exhibitions and Expos both Local and International to market Kiambu County as an Investment Hub, (4 -Trade, 4- Tourism,2 – Co-operative) | Exhibitions and expos held | No of exhibitions and Expos held | 10 | Nil | Non availability of funds |
| Establishment of Livestock Markets | livestock Markets established | No of livestock Markets established | 3 | Nil | Non availability of funds |
| Establishment of an Investor Enabling Centre | Investor Enabling Centrein place | No of Investor Enabling Centre established | 2 | 1 | Ongoing |
| Construction of Weights and Measures workshop/Block | Weights and Measures workshop/Block in place | No. of Weights and Measures Block constructed | 1 | Nil | No funds |

| Programme Name; Tourism Development and Promotion |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Objective: Promotion and marketing of Tourism Sector |  |  |  |  |  |
| Outcome: A vibrant tourism sector leading to job creation and increased in income |  |  |  |  |  |
| Sub Programme | Key Outcomes/ Outputs | Key performance indicators | Planned Targets | Achieved Targets | Remarks* |
| Rehabilitation and/or construction of Historical, Heritage and Tourist Attraction sites | Rehabilitation and/or construction of Historical ,Heritage and Tourist Attraction sites done | No. of Centers rehabilitated and/or constructed | 6 | Nil | No funding |
| Landscaping works and Construction of ablution blocks in tourism attraction areas | Landscaping works and Construction of ablution blocks done | No of tourism sites rehabilitated | 6 | 2 | Ongoing |
| Mapping of Tourism Attraction sites | Mapping of Tourism Attraction sites | No. of Sites mapped and identified | 12 | Nil | No funding |

| Programme Name; Co-operative Development and Management |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Objective: To promote and develop cooperative movement in Kiambu county |  |  |  |  |  |
| Outcome: Sustainable and empowered socio-economic livelihoods |  |  |  |  |  |
| Sub Programme | Key Outcomes/ Outputs | Key performance indicators | Planned Targets | Achieved Targets | Remarks* |
| Marketing and Branding | Purchase of branded materials | No of Branding Materials purchased | 20 | Nil | Non availability of funds |
| Purchase Coffee for Branding, Marketing and Export | Branded, Marketed and Exported Kiambu County Coffee | Quantity of Kiambu County Coffee purchased for Branding, Marketing and Exportation | 20 | Nil | Non availability of funds |
| Capacity building in areas of Trade, Tourism, Co-operatives, Audit, Weight and Measures | Enhanced skills, good corporate governance and improved performance | No. of people capacity built | 1,500 | 1,500 | completed |
| Workshops, Forums and Seminars on Trade, Tourism, Co-operatives, Audit, Weight and Measure | Awareness | No of people sensitized | 1,000 | 880 | Ongoing |
| Purchase of one acre of land in Ndeiya, Lari Sub County | A monument for Mau Mau heros constructed | No. of acres of land purchased | 1 | Nil | No funds |
| Construction of Central County Warehouse | A Central Warehouses constructed | No. of Warehouses constructed | 4 | Nil | No funds |
| Purchase of coffee Parchment Milling Machines to be installed at Komothai area | A Coffee Milling Plant in place | No. of coffee Parchment Milling machines purchased | 1 | Nil | No funds |
| Construction of milk collection centers for co-operative societies | Milk collection Centres in place | Number of collection centers in constructed | 35 | Nil | No funds |
| Creation of revolving funds for co-operatives | Increase coffee farming capital | No of revolving funds established | 1 | Nil | No fund |

Analysis of Capital and Non-Capital projects of the Previous ADP

Table 34: Performance of Capital Projects for Trade, Tourism, Co-operative & Enterprise Development

| Project Name/ Location | Objective/ Purpose | Output | Performance Indicators | Status (based on the indicators) | Planned Cost (Ksh.) | Actual Cost (Ksh.) | Source of funds |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Construction of office block | Office Space | Office constructed | No of Office blocks constructed | 1 | 100M | Nil | County Govt of Kiambu |
| Establishment and construction of new Markets | Providing an enabling environment for entrepreneurship trade and investments | Markets Constructed | No. of Markets Constructed | 7 | 250M | 55M | County Govt of Kiambu |
| Establishment of Boda Boda Sheds | Providing a good working business environment for operators in the Boda Boda Sector | Boda Boda Sheds constructed | No of Boda Boda Sheds constructed | 120 | 60M | 5M | County Govt of Kiambu |
| Establishment of Modern Model Kiosks | Providing a conducive business environment for vendors and other SMEs | Modern Model Kiosks established | No of Modern Model Kiosks established | 240 | 50M | Nil | County Govt of Kiambu |
| Support Training on Value addition among MSME s, Co-operatives, Tourism and Business Groups | Facilitating trade and investments through capacity building and value addition on various products | MSMEs capacity built | no of MSMEs trained on Value Addition and M&E reports | 120 | 20M | NIL | County Govt of Kiambu |
| Participating in Exhibitions and Expos both Local and International to market Kiambu County as an Investment Hub, (4 -Trade, 4- Tourism,2 – Co-operative) | Providing a platform for market networking and linkages | Exhibitions and expos held | No of exhibitions and Expos held | 10 | 20M | 2M | County Govt of Kiambu |
| Establishment of Livestock Markets | Providing a holding ground for livestock dealers | livestock Markets established | No of livestock Markets established | 3 | 13M | NIL | County Govt of Kiambu |
| Establishment of an Investor Enabling Centre | Facilitating trade and Investment | Investor Enabling Centre in place | No of Investor Enabling Centre established | 2 | 20M | 1.5M | County Govt of Kiambu |
| Rehabilitation and/or construction of Historical, Heritage and Tourist Attraction sites | Increasing numbers of Tourists and Tourists attraction sites | Rehabilitation and/or construction of Historical, Heritage and Tourist Attraction sites done | No. of Centers rehabilitated and/or constructed | 6 | 50M | NIL | County Govt of Kiambu |
| Purchase of one acre of land in Ndeiya, Lari Sub County | Concealed graves | Built a monument for Mau Mauheros | N0. Of acres purchased | 1 | 25M | NIL | County Govt of Kiambu |
| Construction of Central County Warehouse | To provide a Warehouse facility for Co-operatives | Constructed Central Warehouses | No. of Warehouses constructed | 4 | 20 M | NIL | County Govt of Kiambu |
| Purchase of coffee Parchment Milling Machines to be installed at Komothai area | To facilitate Coffee Milling | Coffee Milling Plant in place | No. of coffee Parchment Milling Machines purchased | 1 | 500M | NIL | County Govt of Kiambu |
| Construction of milk collection centers for co-operative societies | To provide milk collection Centres | Milk collection Centres in place | Number of milk collection centers in place | 35 | 7M | NIL | County Govt of Kiambu |
| Totals |  |  |  |  | 1.135B |  |  |

Table 35: Performance of Non-Capital Projects for Trade, Tourism, Co-operative & Enterprise Development

| Project Name/ Location | Objective/ Purpose | Output | Performance indicators | Status (based on the indicators) | Planned Cost (Ksh.) | Actual Cost (Ksh.) | Source of funds |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Refurbishment of Office Blocks | To provide a conducive working office space | Refurbishment of Office Blocks | No. of office Blocks Refurbished | 10 | 25M | NIL | County Govt of Kiambu |
| Refurbishment and renovation of existing markets | Providing an enabling environment for investments in trade | No of markets refurbished and renovated | No of markets refurbished and renovated | 24 | 50M | 5M | County Govt of Kiambu |
| Support Training on Value addition among MSME s, Co-operatives, Tourism and Business Groups | Facilitating trade and investments through capacity building and value addition on various products | MSMEs capacity built | no of MSMEs trained on Value Addition and M&E reports | 120 | 20M | 2M | County Govt of Kiambu |
| Verification and inspection of weighing and measuring equipment | Ensuring fair Trade Practices and consumer Protection | Verification and inspection of weighing and measuring equipment in place | % Increase in no of measuring and weighing equipment verified and inspected | 30% | 3M | 500K | County Govt of Kiambu |
| Establishment of Weights and Measures workshop/Block | Providing a working place at the headquarters for verification and inspection of weighing and measuring equipment | Weights and Measures workshop/Block in place | No of Weights and Measures Blocks constructed | 1 | 10M | NIL | County Govt of Kiambu |
| Landscaping works and Construction of ablution blocks in tourism attraction areas | Creating a platform for more attractions | Landscaping works and Construction of ablution blocks done | No. of tourism attraction sites rehabilitated | 6 | 50M | 4M | County Govt of Kiambu |
| Mapping of Tourism Attraction sites | To create a baseline data base of all attraction sites to help in planning | Mapping of Tourism Attraction sites | No. of Sites mapped and identified | 12 | 30M | NIL | County Govt of Kiambu |
| Purchase Coffee for Branding, Marketing and Export | To Brand, Market and Export Kiambu County Coffee | Branded, Marketed and Exported Kiambu County Coffee | Quantity of Kiambu County Coffee purchased for Branding, Marketing and Exportation | 20 | 20M | NIL | County Govt of Kiambu |
| Creation of revolving funds for co-operatives | Prompt payment to farmers / on delivery | Increase in coffee production | No of the revolving funds created | 1 | 300M | NIL | County Govt of Kiambu |
| Capacity building in areas of Trade, Tourism, Co-operatives, Audit, Weight and Measures | To build capacity | Enhanced skills, good corporate governance and improved performance | No. of staff trained | 1500 | 50M | NIL | County Govt of Kiambu |
| Workshops, Forums and Seminars on Trade, Tourism, Co-operatives, Audit, Weight and Measures | To sensitize the stakeholders | Awareness | No. of people sensitzed | 1,000 | 50M | 1M | County Govt of Kiambu |
| Totals |  |  |  |  | 608M |  |  |

### 2.2.13 Roads, Transport, Public Works and Utilities

The department had planned to carry out the following works; In the Roads and Transport directorate, Construction 15Km of bituminous road, Construction of 240Km of gravel roads, construction of 5No. Bridges, construct 10Km of Non-motorized transport, preparation of master plan for the roads and storm water drainage systems, construction of 50Km of storm water drainages, Construction of Bus parks, Street lighting within the county towns, purchase of vehicles and equipment; in utility directorate, construction of 60No. 15meters high flood masts, construction of 300 streetlights and construction of 3 No. fire stations in Kikuyu, Ruiru and Kiambaa while in public works directorate planned construction of 6 No. footbridges and support of all the other departments in design, construction and supervision of various facilities.

Planned versus allocated budget

| PROGRAMME | Planned FY 2017/2018 (Kshs.) | Allocation FY 2017/2018 (Kshs.) |
| --- | --- | --- |
| 0201:P1 Maintenance of Roads, Bridges, Transport, Construction and Maintenance | 1,761,474,098 | 1,489,739,104 |
| 020101: SP 1: General administration and support services | 1,697,874,098 | 1,140,760,174 |
| Current Expenditure | 415,244,400 | 348,978,930 |
| Capital Expenditure | 1,282,629,698 | 1,140,760,174 |
| 020102: SP 2 Construction of road and civil works | 63,600,000 | - |
| Total Expenditures for the vote | 1,761,474,098 | 1,489,739,104 |

Key Achievements

The department has registered various achievements in all its directorates in year 2017-18; Construction to gravel standards over 250km of rural access roads; rehabilitating/constructing 2No. bridges; rehabilitating/reconstruction of 31Kms of bituminous roads; construction and marking of street parking in  major  towns; construction of 2No. bus parks; construction of circuit gravel roads at rural shopping centres and maintenance of  over 350Km of rural roads; and, maintenance of storm water drainage throughout the County. The Department is also constructing 3No.fire stations and is in possession of 12 No. fire engines and vehicles. With respect to lighting the County the Department has installed 60No. 15metres high flood masts and 139 street lights funded by the county Government.  The department has also acquired 2No graders which supports in roads opening and maintenance.

Table 36: Roads, Transport, Public Works & Utilities Programmes

| Programme Name: Roads and Transport |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Objective: To develop quality, reliable, sustainable and resilient infrastructure to support economic development |  |  |  |  |  |
| Outcome: Improved road network and Increased road safety |  |  |  |  |  |
| Sub Programme | Key Outcomes/ Outputs | Key Performance Indicators | Planned Targets | Achieved Targets | Remarks |
| Construct 15 Km of bituminous roads | Improved road network Increased road safety. | No. of Km upgraded to bitumen status | 15Km Bitumen road | 30.8Km of Bitumen roads | Some of the works are ongoing |
| Construct 240 km of gravel rural access roads | Improved road network Increased road safety. | No of Km upgraded to gravel road network | 240Km gravel road | 362 Km of graded and gravel done | This includes grading and gravelling |
| Construct or rehabilitate 5No. motorable bridges | Improved connectivity and good passable bridges | No of motorable bridges constructed. | 5 No. bridges | 2 No. bridges done | Some of the works are ongoing |
| To construct 10 KM of NMT facility (foot paths) | Improved safe walkways for the pedestrians. | No of KM of NMT constructed | 10Km NMT | 6Km of NMT Constructed | Some of the works are ongoing |
| Preparation of master plan for the roads and storm water drainage systems | Developed Long-vision for road policy framework for decisions that affect the physical, social and economic environment of the Towns in the County | Master Plan produced and Published | 1No. master plan | 1No. master plan | The works being implemented by a consultant |
| Construct 50Km storm water drainages | Improved drainage systems and clean environment | No of Km of drain constructed | 50Km of storm water drain | 4Km | The drainages works are ongoing. Maintenance works of other towns conducted on routine bases |
| Construct Bus parks (Kiambu, uthiru, Kikuyu, Thika) | Increased parking space for PSV vehicles. Improved service delivery and also enhances revenue collection. | No. of Bus parks constructed | 4No. Bus Parks | 2No. busparks complete | Kiambu and Githurai 45 |
| Construct Street parkings with the County Towns | Increased parking space for PSV vehicles. Improved service delivery and enhances revenue collection | No of street Parkings constructed | Street parking constructed | This is implemented as county town roads are rehabilitated |  |
| Purchase of Motor Vehicles and equipment | Improved mobility and operations for the Department | Project Management Vehicles Double Cabins. | Pick-ups, trucks & grader | - Graders | None |
|  |  | No. of Lorries |  |  | None |
|  |  | No of graders |  |  | 3 Graders |

| Programme Name: Energy, Disaster Management, Fire, Safety and Rescue |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Objective: Improved security and safety of people and property |  |  |  |  |  |
| Outcome: To promote 24 hour economy and attraction of investors |  |  |  |  |  |
| Sub Programme | Key Outcomes/ Outputs | Key Performance Indicators | Planned Targets | Achieved Targets | Remarks |
| Construct 60 Number, 15 metres flood masts within the County | Improved lighting and enhanced security | No of flood masts constructed | 60No. flood masts | 60No Floodmasts |  |
| Construct streetlight within the County 300 poles | Improved lighting and enhanced security | No of street lights constructed | 300 No. streetlights | 139 No. Street lights done |  |
| Construct 3No.Fire stations at Kikuyu, Ruiru and Kiambaa | To enhance safety and response to disasters | No of fire stations constructed | 3No. Fire stations | 3 No fire stations ongoing | Completion of construction of 3 fire stations Kiambu, Githunguri and Limuru |

Analysis of Capital and Non Capital Projects of the Previous ADP

The department has registered 31 Km of bituminous roads; these roads link the major centres and increase accessibility therefore improving the economic status of the County. There are also 2 No. bridges which enhance connectivity. Beside the major projects, the department has registered over 362Km of graded and graveled roads complete with proper drainage system.

Table 37: Performance of Capital Projects for Roads, Transport, Public Works and Utilities

| Project Name | Objective/ Purpose | Output /Outcome | Performance indicators | Status (based on the Indicators | Planned Cost (Ksh.) | Actual Cost (Ksh.) | Sources of funds |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Thogoto –Ndaire road | To connect Thogoto village and Dagoretti market | To ease mobility of motorists and passengers | No. of Kilometers completed | On going | 181,145,250.99 | 181,145,250.99 | CGK |
| Githunguri- Ndumberi road | To enhance Connectivity | Increased connectivity | No. of Kilometers completed | On going | 340,801,794 | 340,801,794 | CGK |
| Githunguri CBD roads | To enhance Connectivity | Increased connectivity | No. of Kilometers completed | On going | 103,997,581 | 103,997,581 | CGK |
| Gatitu Junction and other roads | To enhance Connectivity | Increased connectivity | No. of Kilometers completed | On going | 221,005,870.30 | 221,005,870.30 | CGK |
| Road C64-C65 | To enhance Connectivity | Increased connectivity | No. of Kilometers completed | On going | 145,346,505.00 | 145,346,505.00 | CGK |
| Kimende Town Roads | To enhance Connectivity | Increased connectivity | No. of Kilometers completed | On going | 139,821,008.80 | 139,821,008.80 | KRB |
| A2 Junction Kimbo Matangini | To enhance Connectivity | Increased connectivity | No. of Kilometers completed | On going | 170,552,896.31 | 170,552,896.31 | CGK |
| Ewaso Kedong Road | To enhance Connectivity | Increased connectivity | No. of Kilometers completed | On going | 14,701,450.00 | 14,701,450.00 | CGK |
| Gachororo road | To enhance Connectivity | Increased connectivity | No. of Kilometers completed | On going | 395,000,000 | 395,000,000 | Namsip |
| Kimuchu corner 3 Muthaiga junction | To enhance Connectivity | Increased connectivity | No. of Kilometers completed | On going | 90,000,000.00 | 90,000,000.00 | CGK |
| Full gospel Githunguri Primary school road | To enhance Connectivity | Increased connectivity | No. of Kilometers completed | On going | 30,000,000.00 | 30,000,000.00 | CGK |
| Rainbow Hotel _Eastern Bypass Road | To enhance Connectivity | Increased connectivity | No. of Kilometers completed | On going | 111,000,000.00 | 111,000,000.00 | CGK |
| Kahawa wendani Nakumatt Supermat road to Kwa Ngethe road | To enhance Connectivity | Increased connectivity | No. of Kilometers completed | On going | 78,000,000.00 | 78,000,000.00 | CGK |
| Thika Highway Maraba Junction | To enhance Connectivity | Increased connectivity | No. of Kilometers completed | On going | 60,000,000.00 | 60,000,000.00 | CGK |
| Igegania health centre- igegania pri sch | To enhance Connectivity | Increased connectivity | No. of Kilometers completed | On going | 31,500,000.00 | 31,500,000.00 | CGK |
| Kamirithu Ngenia High-ACK Ngarariga | To enhance Connectivity | Increased connectivity | No. of Kilometers completed | On going | 120,000,000.00 | 120,000,000.00 | CGK |
| Kahata Junction Kibaoini – Gachege road | To enhance Connectivity | Increased connectivity | No. of Kilometers completed | On going | 30,000,000.00 | 30,000,000.00 | CGK |
| GathangaMuchatha road | To enhance Connectivity | Increased connectivity | No. of Kilometers completed | On going | 60,000,000.00 | 60,000,000.00 | CGK |
| Karura Ka Nyungu - Gikuni | To enhance Connectivity | Increased connectivity | No. of Kilometers completed | On going | 60,000,000.00 | 60,000,000.00 | CGK |

Table 38: Performance of Non capital Projects for Roads, Transport, Public Works and Utilities

| Project Name | Objective/ Purpose | Output /Outcome | Performance indicators | Status (based on the Indicators | Planned Cost (Ksh.) | Actual Cost (Ksh.) | Sources of funds |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Rehabilitation and construction of access roads | To enhance Connectivity | Increased connectivity | No. of Kilometers completed | On going | 337,100,000 | 337,100,000 | CGK |
| Renovation of Fire stations | To improve service delivery | Increased connectivity | No. | On going | 50,000,000 | 50,000,000 | CGK |

### 2.2.14 Livestock, Fisheries and Marketing

Strategic priorities

The directorate of livestock had planned to construct 3 office blocks in Kabete, Juja and Kiambaa subcounties, purchase of motor vehicles for enforcement, electrification of Gatundu south slaughter house, establishment and equipping of information desks in all the wards, development of an agricultural resource centre, rehabilitation of 2 cattle dips in each subcounty, establishment of an animal feeds factory in the county, licensing of all slaughterhouses and meat containers, training of the youths on hides and skin development, upgrading and improving dairy animals by increasing AI inseminations and also undertake livestock development  and improvement.

The directorate of fisheries had planned to install fish ponds liner and stock them with fingerlings, construction of a recirculatory fish farming system in Juja and Gatundu sub counties, development of cage farming, stocking of Gatamaiyu, Thiririka, Karimenu and Rwambora rivers, establishment of a fish collection center in Thika and Kiambu sub counties, fish feed making center establishment and also the establishment of cold facilities at Lari and Githunguri.

Priority was given to purchase of vaccines and disease control, value addition for milk through installation of pasteurizers and dispensers, improved poultry production, promotion of aquaculture technologies through recirculatory system and caged fish farming where Waruhiu ATC and Ruiru AMS was to pursue revolving funds for ease operations.

Planned versus Allocated Budget

The planned budget for the sector was Ksh314.125M and was allocated Ksh 362.58M.

Key Achievements

During the last ADP the department procured, installed and commissioned 5000 liters per hour pasteurizer and 3milk coolers (15,000ltrs combined capacity).  In disease prevention and control 71,646 Cattle, 1,795 Shoats, 2,516 Dogs /cat, 72 Donkey and 3,056,530 Poultry were vaccinated.  While in fish farming 72 fishing nets were procured, 5 fish farming greenhouses established, 2 recirculatory fish farming system constructed, 6 fish cages installed in dams, 4 rivers stocked with fingerings, two fish collection centers established and two groups issued with a pelletizer each.

Table 39: Summary of Livestock, Fisheries and Marketing Programmes

| Programme Name: Livestock Resources Management and Development |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Objective: To increase livestock productivity |  |  |  |  |  |
| Outcome: Increased livestock production and increased income |  |  |  |  |  |
| Sub Programme | Key Outcomes/ Outputs | Key performance indicators | Planned Targets | Achieved Targets | Remarks* |
| Construction of Sub County Offices | Offices constructed at Kabete, Juja and Kiambaa Sub Counties | No of offices constructed | 3 Offices | 0 | On going |
| Slaughter house electrification | Electrification of 1slaughter house at Gatundu South | Slaughter house connected to electricity | 1 slaughter house | 0 | On going |
| Purchase of motor vehicles | 5 Vehicles purchased | No of vehicles purchased | 5 vehicles | 0 | On going |
| Purchase of motor cycles | 5 Motor cycles purchased | No of motor cycle purchased | 5 M/cycles | 0 | On going |
| Enhance ICT technology | 90 computer system purchased for the 12 Sub Counties Printers Website development LAN and WIFI | No of Computers and laptops | 40 Desktops 50 Laptops | 0 | On going |
| Establishment and equipping of information desks in the wards | Information desks in all wards equipped with -tables -chairs -tablets -branded banners -tents | No of information desks established and equipped | 60 desks | 0 | On going |
| Develop an agricultural information resources centre | One agricultural information resources centre developed at Waruhiu | No of agricultural information resources centre developed | 1 centre | 0 | On going |
| Milk Coolers, Pasteurizers and Dispensers | Milk coolers & Pasteurizers purchased and installed at - Githiga - Ngewa - Bibilioni -Kiambaa | 4 of milk Coolers, 3 Pasteurizers and 5 Dispensers | Four Milk coolers &Pasteurizers and Dispensers | 3 milk coolers 1pasteurizer 0 dispensers | On going |
| Rehabilitation of cattle dips | 2 cattle dips rehabilitated per Sub County | No of cattle dips rehabilitated | 24 cattle dips | 0 | On going |
| Animal feeds factory | Develop 1 animal feeds factory at Lari Sub county | No of factories developed | 1 animal feed factory | 0 | On going |
| D Disease Control Prevention and Control programme | Vaccinate livestock 50,000 H/C 10000 Sheep& goats against FMD, Anthrax, LSD. | Number of livestock vaccinated | Vaccinate 50,000heads of cattle and 10,000 shoats. | Cattle - 71,646 Shoats - 1,795 Dogs /cat – 2,516 Donkey -72 Poultry -3,056,530 | Target achieved |
| Disease control and surveillance in animals | To rehabilitate 1laboratory for disease diagnosis in Limuru | Percentage completion of rehabilitation | 80 percent rehabilitation | Not rehabilitated | On going |
| v Veterinary Public Health | Licensing of slaughter houses and meat containers; | Number of Slaughter houses and meat carriers licensed | License 60 slaughter houses and 900 meat containers | 24 slaughter houses and 370 meat carriers licensed | On going |
| Hides and skins development | 500 youths trained in hides and skin development County wide | No of youths capacity built | 500 youths trained | 0 | On going |
| A.I and clinical services | Upgrade and improve the dairy animals by increasing AI inseminations. License inseminators. | AI inseminations done | -record 15,000 inseminations -license 200 inseminators | 46,845 inseminations 34 inseminators licensed | On going |
| Poultry Rabbit Slaughter House | upgrade and improve Thika poultry and rabbit slaughter house | Percentage Completion of the phase II of the slaughter House | 80 percent completion | 0 | On going |
| Veterinary inspectorate services | Improved services to the farmers | Improved livestock industry | Inspect All agrovets in Kiambu. | 164 | On going |
| Livestock development and improvement | An embryo transfer laboratory Developed at Waruhiu | No of laboratories established | Establish1 laboratory | 0 | On going |
|  | Purchase of local poultry chicks | No of farmers benefiting | 10,000 farmers | 0 | On going |
|  | Increased pork production | No of farmers trained | 2400 farmers | 1200 | On going |
|  | Increased emerging livestock productivity | No of bee apiary and rabbit farmers trained | Establish 10 bee Apiaries And train1200 rabbit farmers | 0 bee apiaries established 600 rabbit farmers trained | On going |

| Programme name; Fisheries Development And Management |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Objective; To Increase Fisheries Productivity |  |  |  |  |  |
| Outcome; Increased Fisheries Production And Utilization |  |  |  |  |  |
| Sub Programme | Key Outcomes/ Outputs | Key performance indicators | Planned Targets | Achieved Targets | Remarks* |
| Installation of fish ponds liners | Fish ponds lined and stocked | No of fish ponds lined and stocked | 72 fish ponds | 24 liners in requisition | On going |
| Procurement of fishing nets | Fishing nets procured | No of fishing nets | Procure 72 fishing nets | 4 in requisition stage | On going |
| Construction of green house fish farming | fish farming greenhouses constructed | No of fish farming greenhouses | 5 fish farming greenhouses | 1 in requisition stage | On going |
| Recirculatory fish farming (solar energy) | Recirculatory fish farming system constructed in Juja and Gatundu South Sub Counties | No of Recirculatory fish farming system constructed | Construct 2 recirculatory fish farming system | 0 | On going |
| Cage fish farming | Cage fish farming developed at Ruiru, Juja, Kiambu (Kiamumbi dam) | No of cages installed | Install 6 cages | 4 in requisition stage | On going |
| Fish stocking in selected rivers | Fish stocked at Gatamayu river, Thiririka river, karimenu and Rwambora | No of rivers stocked | Stock 4 rivers | 1in requisition stage | On going |
| Establishment of fish collection centre | Fish collection centres established in Thika and Kiambu subcounties | No. of collection centre | Establish two centres | 2 in requisition stage | Target achieved |
| Establishment of fish feed making centre | Feed making centres established | No. of feed making centres | Issue Two groups with pelletisers | 1 in requisition stage | On going |
| Fish cold facilities | cooling facilities established at Lari and Githunguri | No. of fish cooling facilities established | Establish 4 fish cooling facilities | 4 in requisition stage | Target achieved |

Analysis of Capital and Non-Capital projects of the Previous ADP

Table 40: Performance of Capital Projects for Livestock, Fisheries and Marketing

| Project Name/ Location | Objective/ Purpose | Output | Performance Indicators | Status (based on the indicators) | Planned Cost (Ksh.) | Actual Cost (Ksh.) | Source of funds |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Construction of Offices at Kabete, Juja and Kiambaa Sub Counties | Improvement of public service delivery | Construction of offices | No of offices constructed | 0 | 36M | 0 | CGK |
| Slaughter house electrification | Improvement of public service delivery | Electrification of slaughter house at Gatundu South | Percentage completion | 0 | 0.5M | 0 | CGK |
| Purchase of motor vehicles | Provide transport to staff to improve service delivery | 5 Vehicles purchased | No of vehicles purchased | 0 | 30M | 0 | CGK |
| Purchase of motor cycles | Provide transport to staff to improve service delivery | 5 Motor cycles purchased | No of motor cycle purchased | 0 | 2M | 0 | CGK |
| Enhance ICT technology | To improve efficiency and effectiveness in service delivery and implementation | 90 computer system purchased for the 12 Sub Counties Printers Website development LAN and WIFI | No of Computers and laptops | 0 | 10M | 0 | CGK |
| Milk Coolers, Pasteurizers and Dispensers | To increase the household income of dairy farmers | Milk coolers & Pasteurizers purchased and installed at - Githiga - Ngewa - Bibilioni - kiambaa | 4 of milk Coolers, 3 Pasteurizers and 5 Dispensers | 3-Milk coolers 1-Pasteurizers 0-Dispensers | 70M | 39.6M | CGK |
| Animal feeds factory | To promote livestock | 01 animal feeds factory developed at Lari Sub county | No of factories developed | 0 | 100M | 0 | CGK |
| Poultry Rabbit Slaughter House | To improve poultry & rabbit slaughter hygiene | upgrade and improve thika poultry and rabbit slaughter house | Completion of the phase II of the slaughter House | 0 | 10 M | 0 | CGK |
| Livestock development and improvement | To increase animal production for increased yields and farm income | Develop an embryo transfer laboratory at Waruhiu | No of laboratories established | 0 | 25 M | 0 | CGK |
|  | To improve poultry rearing | Purchase of local poultry chicks | No of farmers benefiting | 0 | 10 M | 0 | CGK |
|  | To promote bee keeping and rabbit rearing | Increased emerging livestock productivity | No of bee apiaries established and rabbit farmers trained | 0 | 24 M | 0 | CGK |
| Construction of fish ponds, stocking, fencing and installation of fish ponds liners | To promote fish production | Fish ponds lined and stocked | No of fish ponds lined and stocked | 72 fish ponds | 9.2M | 4M | CGK |
| Procurement of fishing nets | To promote fish farming | Fishing nets procured | No of fishing nets | 72 fishing nets procured | 0.7M | 0.15M | CGK |
| Construction of green house fish farming | To promote fish farming | fish farming greenhouses constructed | No of fish farming greenhouses | 5 fish farming greenhouses | 4M | 2M | CGK |
| Recirculatory fish farming (solar energy) | To promote fish farming | Recirculatory fish farming system constructed in Juja and Gatundu South Sub Counties | No of Recirculatory fish farming system constructed | 2 recirculatory fish farming system constructed | 7M | 0 | CGK |
| Cage fish farming | To promote fish farming | Cage fish farming developed at Ruiru, Juja, Kiambu (Kiamumbi dam) | No of cages installed | 6 cages installed | 4M | 2M | CGK |
| Fish stocking in selected rivers | To promote fish farming | Gatamayu river, Thiririka river, karimenu and Rwambora stocked | No of rivers stocked | 04 rivers stocked | 1.5M | 0.5M | CGK |
| Establishment of fish collection centre | To promote fish marketing | Fish collection centres established in Thika and Kiambu subcounties | No. of collection centre | two centres established | 2M | 0.3M | CGK |
| Establishment of fish feed making centre | To promote fish production | Two centres established | No. of feed making centres | Two groups issued with pelletisers | 2M | 1.65M | CGK |
| Establishment of agro processing cottage industries for value addition Agricultural markets and marketing development | To promote market access and product development | 01 hides and skins cottage industry established at Kikuyu | No of hides and skins cottage industry established | 01 hides and skins cottage industry | 20M | 0 | CGK |
|  |  | 01 honey processing cottage industry established at Kikuyu Karai ward | No. of honey processing cottage industry established | 0 | 5M | 5M | CGK |
|  |  | 04 fish cooling facilities established at Lari and Githunguri | No. of fish cooling facilities established | 04 fish cooling facilities | 4M | 0.6M | CGK |

Table 41: Performance of Non-Capital Projects for Livestock, Fisheries and Marketing

| Project Name/ Location | Objective/ Purpose | Output | Performance Indicators | Status (based on the indicators) | Planned Cost (Ksh.) | Actual Cost (Ksh.) | Source of funds |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Establishment and equipping of information desks in the wards | To enhance extension | Information desks in all wards equipped with -tables -chairs -tablets -branded banners -tents | No of information desks established and equipped | 0 | 5 M | 0 | CGK |
| Develop an agricultural information resources centre | To enhance extension outreach to farmers | One agricultural information resources centre developed at Waruhiu | No of agricultural information resources centre developed | 0 | 2 M | 0 | CGK |
| Rehabilitation of cattle dips | To improve animal husbandry and vector control | 2 cattle dips rehabilitated per Sub County | No of cattle dips rehabilitated | 0 | 6M | 0 | CGK |
| Disease Control Prevention and Control programme | Reduce incidences of notifiable diseases | Vaccinate livestock 50,000 H/C 10000 Sheep& goats against FMD, Anthrax, LSD. | Number of livestock vaccinated | Cattle - 71,646 Shoats - 1,795 Dogs /cat – 2,516 Donkey -72 Poultry -3,056,530 | 30M | 3.5M | CGK |
| Disease control and surveillance in animals | To prevent animal diseases | To rehabilitate 1laboratory for disease diagnosis in Limuru | No of laboratories | 0 | 10M |  | CGK |
| Veterinary Public Health | Ensure the public consume wholesome meat | Licensing of slaughter houses and meat containers; | Number of Slaughter houses and meat carriers licensed | 24 slaughter houses and 370 meat carriers licensed | 1.2M | 0 | CGK |
| Hides and skins development | To improve the quality of the hides and skins for value addition | 500 youths capacity built County wide | No of youths capacity built | 0 | 20M |  | CGK |
| A.I and clinical services | To increase animal productivity for more milk production | Upgrade and improve the dairy animals by increasing AI inseminations. License inseminators. | AI inseminations done | 46,845 inseminations 34 inseminators licensed | 2M | 0 | CGK |
| Veterinary inspectorate services | To supervise and inspect agro-vets and clinics | Improved services to the farmers | Improved livestock industry | 164 | 2M | 0 | CGK |
| Livestock development and improvement | Pig farming development | Increased pork production | No of farmers trained | 3000 | 6M | 0 | CGK |

## 2.3 Payments of Grants, Benefits and Subsidies

This section provides information on total payments done by the county government.

Table 42:  Payments of Grants, Benefits and Subsidies

| Type of payment | Budgeted Amount (Ksh.) | Actual Amount paid (Ksh.) | Beneficiary | Remarks* |
| --- | --- | --- | --- | --- |
| Finance, ICT and Economic Planning |  |  |  |  |
| Emergency fund | 24M | 0 | Disaster victims |  |
| Health Services |  |  |  |  |
| DANIDA | 21,851,856 | 21,851,856 | Gazetted Level 2 and 3 Health facilities | Conditional Grant from development partner(Recurrent expenditure) |
| Compensation for user fee foregone | 34,671,542 | 17,355,221 | Gazetted level 2 and 3 health facilities | Conditional grant from development partner(O& M) |
| Conditional Grant | 412,716,764 | 412,716,764 | Thika level 5 | Fully funded |
| FIF(Facility Improvement Fund) | 470,000,000 | 434,161,354 | All gazetted Health facilities | Ongoing |
| Linda Mama | 262,624,046 | 64,624,048 | All gazetted Health facilities | Ongoing |
| THS(Transforming Health for Universal care project) | 10,000,000 | 10,000,000 | Primary Health care | Improve on Indicators |
| Education, Youth, Sports, Culture, & Social Services |  |  |  |  |
| Education Bursary Fund | 200,000,000 | 134,000,000 | Vulnerable students in society | ongoing |
| Youths and Sports |  |  |  |  |
| Biashara Fund | 100m | 0 | Youth, Women and Persons with disability | ongoing |
| Clubs affiliation & participation fee | 2.7m | 0 | County football teams | ongoing |

## 2.4 Challenges experienced during implementation of the previous ADP

The county government has faced several challenges during the implementation period of the previous CADP. The following are some of the challenges:

- Untimely disbursement of funds by the national government to the county government

- Inadequate financial resources

- Inherited huge wage bill which affects the allocation of funds for development

- Under developed infrastructure

- Low levels of awareness of the county plans, Acts and policies by the community

- Lack of proper coordination in the implementation of projects by various development actors

- Weak Monitoring and Evaluation systems

- Missing of revenue targets affecting budgeting process

- Lengthy procurement procedures delaying implementation of the planned projects

- Inadequate technical personnel e.g. Architects and Quantity Surveyors delaying development of technical documents like Bills of Quantities

- Weak Public Private Partnership framework

## 2.5 Lessons learnt and recommendations

The key lessons learnt from the implementation of the previous plan and proposed recommendations for improvement are as listed here below.

- Ownership  of project is critical in project implementation

- More funding measures should be explored to supplement inadequate resources from the county government.

- Proper project planning and management is critical for successful program/project implementation

- Research and development, innovations and strong Monitoring and Evaluation systems are critical in project/program planning and management.

- Weak regulatory framework hinders implementation and realization of programme’s benefits and relevant registrations need be prioritized.

- Monitoring and Evaluation is key component to ensure value for money is realized.

- Close linkages among department and a coordination team need be in place for effective service delivery

- Private Public Partnership need to be strengthened as private sector plays a key role in the implementation of projects.

- Performance contract and appraisal need to be implemented for better results.

- Need to build the capacity of the staff to improve service delivery

# CHAPTER THREE: COUNTY STRATEGIC PRIORITIES, PROGRAMMES AND PROJECTS

## 3.1 Introduction

This chapter present sector/sub-sector strategic priorities, programmes and projects to be implemented during 2018/19 Financial Year. It also provides a summary of sector goals, targets, performance indicators and overall resource requirement. Further, the chapter analysis the key stakeholders and provide information on proposed payment of Grants, Benefits and Subsidies to be done by the county government during the plan period.

## 3.2 Sector / Subsector Capital and Non Capital Projects for 2018/2019 FY

### 3.2.1 County Assembly

Vision

To be a vibrant, value oriented, quality driven and people responsive County Assembly in Kenya

Mission

Transformative, efficient, effective and democratic discharge of representation, legislative, and oversight mandates

Sub-sector goals and targets

- To strength the capacity of members of the County Assembly in executing their role in Legislative, Oversight and Representation;

- To enhance the County Assembly of Kiambu Public image

- Staff Performance, Capacity & Service Delivery

- Strengthen the Office of the Speaker  and the Office of the Clerk

- Improve the Working Environment for members and staff of the County Assembly

Capital and Non-Capital Projects

Table 43: County Assembly Capital projects for the FY 2018/2019

| Programme Name: Legislation, Representation and Oversight in the County Government |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Sub Programme | Project name location (ward/Sub County/county wide) | Description of activities | Green Economy consideration | Estimated cost (Kshs) | Source of funds | Timeframe | Performance indicators | Targets | Status | Implementing agency |
| General Administration and support services | Assembly Infrastructure | Construction and Completion of structural and infrastructural development projects and utilities |  | 55 Million | CGK | 2018-2019 | Construction and equipping of Assembly infrastructure | 10% | To commence | County Assembly of Kiambu |
|  |  | Personal Emoluments (Amount allocated for personnel emoluments) |  | 465 million | CGK | 2018-2019 |  | 100% | ongoing |  |
|  |  | Operations & Maintenance |  | 735 million | CGK | 2018-2019 |  |  | ongoing |  |
|  |  | No. of vehicles Purchased |  | 8 Million | CGK | 2018-2019 |  | 2 vehicles | To commence |  |
|  |  | No. of ward offices constructed and equipped |  | 55 Million | CGK | 2018-2019 |  | 11 offices constructed and equiped | To commence |  |

Table 44: County Assembly Non-Capital Projects for FY 2018/19

| Programme Name: Legislation, Representation and Oversight in the County Government |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Sub Programme | Project name location (ward/Sub County/county wide) | Description of activities | Green Economy consideration | Estimated cost (Kshs) | Source of funds | Timeframe | Performance indicators | Targets | Status | Implementing agency |
| Legislative, Oversight and Representation services | Assembly Infrastructure | No of capacity building forums held |  | 10 Million | CGK | 2018-2019 |  | 2 | ongoing | County Assembly of Kiambu |
|  |  | No. of County Assembly staff Trained, |  | 20 million | CGK | 2018-2019 |  | 86 | ongoing |  |
|  |  | No. of Performance appraisals done. |  |  |  |  |  | 86 | To commence |  |
|  |  | Number of legislations/ bills processed and passed |  |  | CGK | 2018-2019 |  | 15 | To comence |  |
|  |  | Number of oversight reports produced |  |  | CGK | 2018-2019 |  | 30 | Ongoing |  |
|  |  | Number of bi annual committee reports produced |  |  | CGK | 2018-2019 |  | 2 | Ongoing |  |
|  |  | No. of Budgets approved and Appropriation Act enacted |  |  | CGK | 2018-2019 |  | 2 | Ongoing |  |

### 3.2.2 County Executive

Vision

Excellence in County leadership for a competitive and prosperous Kiambu County.

Mission

To provide overall policy and leadership direction in the management of public affairs for the prosperity of Kiambu County

Sub-sector goals

- To provide effective and efficient services to the public.

- To ensure coordination of various structures within the county.

- To develop and maintain effective and efficient county workforce.

- Effectively planning future staffing requirements.

- Carry out staff training and development.

- Conduct staff performance management.

Development needs, Priorities and Strategies

| Development needs | Priorities | Strategies |
| --- | --- | --- |
| Coordination of Sector plans and Policies | Coordinate departments/sectors to formulate sector plans and policies | - Facilitate development of sector plans and policies - Table the sector plan and policies before the County Executive Committee - Table the sector plans and policies before the County Assembly for approval - Follow up on implementation of sector plans and policies |
| Effective and efficient service delivery | Service charter | - Facilitate formulation and development of a County Service Charter - Coordinate county departments to develop their service charters - Follow up on implementation of the service charter |
| Inter-county relations | Strengthen Inter-county relations | - Develop harmonized working relationship between counties - Develop inter-County dispute resolution mechanisms |
| Inter-governmental relations | Strengthen linkages between County and National Government | - Collaborate with County Security Agencies on security matters - Link up with the national government on eradication of plastics and other toxic wastes - source funds for fire engines , fire fighting equipment and other emergencies |
| Performance Contract | Increase employee efficiency through Performance Contracting | - Formulation of a county performance contract - Cascade the Performance Contract to Departments - Coordinate departments to develop and implement performance contracts - Follow up on rewards system |

Sector Stakeholders

| Stakeholder Category | Stakeholder Expectation | Sector Expectation |
| --- | --- | --- |
| National Government | Adherence and Proper implementation of the Legal framework | Provision of legal framework |
| County Assembly | Comply with the stated laws and policies. | Enact Laws and policies |
| County Public Service Board | Ensure performance of employees in the departments | Human resource management and development |
| Citizens | Good service delivery. | Service delivery and public participation |

Non-Capital Projects

Table 45: County Executive Non-Capital Projects for FY 2018/19

| P1: Administration, Planning and Support Services |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Sub Programme | Project name Location (Ward/Sub county/ county wide) | Description of activities | Green Economy consideration | Estimated cost (Ksh.) | Source of funds | Time frame | Performance indicators | Targets | Status | Implementing Agency |
| SP 1.1 Administration Services | office operations and maintenance (County wide) | Budget allocation to office operations and maintenance |  | 141 M | CGK | 2018-2019 | Amount allocated to office operations and maintenance | 141M | Ongoing | County Executive |
|  | Purchase of vehicle (County wide) | Purchase of new vehicles. |  | 5M | CGK | 2018-2019 | No. of vehicles purchased | 1 | New | County Executive |
| SP 1.2 Personnel Services | Staff training (County wide) | Training of staff |  | 1.5M | CGK | 2018-2019 | Number of staff trained | 20 | Ongoing | County Executive |
|  | personal Emoluments (County wide) | Budget allocation to personal Emoluments |  | 64M | CGK | 2018-2019 | Amount allocated to personal Emoluments | 64M | Ongoing | County Executive |
| Total |  |  |  | 211.5M |  |  |  |  |  |  |

| P2: Government Advisory Services |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Sub Programme | Project name Location (Ward/Sub county/ county wide) | Description of activities | Green Economy consideration | Estimated cost (Ksh.) | Source of funds | Time frame | Performance indicators | Targets | Status | Implementing Agency |
| SP 2.2 Inter-County Advisory Services | collaboration and cooperation meetings (County wide) | Attending meetings |  | 1M | CGK | 2018-2019 | Number of collaboration and cooperation meetings with other counties | 1 | New | County Executive |
| Total |  |  |  | 1 M |  |  |  |  |  |  |

| P3: Leadership and Coordination of Departments |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Sub Programme | Project name Location (Ward/Sub county/ county wide) | Description of activities | Green Economy consideration | Estimated cost (Ksh.) | Source of funds | Time frame | Performance indicators | Targets | status | Implementing Agency |
| SP 3.1 Departments | e-service delivery (County Wide) | Automation of basic departmental information |  | 4.4M | CGK | 2018-2019 | Reduction in time in mins used on transacting a service | 2 | New | County Executive |
|  |  | Development of service charters |  | 0.5M | CGK | 2018-2019 | Number of service charters developed | 1 | New | County Executive |
| SP 3.2 Intergovernmental Relations Council Support | MOUs and agreements (County wide) | Drafting of MOUs and agreements |  | 1M | CGK | 2018-2019 | Number of MOUs and agreements signed with the National Government | 1 | Ongoing | County Executive |
| SP 3.3 Performance Management | performance contracting (County wide) | Sensitization of staff on performance contracting |  | 0.6M | CGK | 2018-2019 | Number of employees under performance contracting | 10 |  | County Executive |
| Total |  |  |  | 6.5 M |  |  |  |  |  |  |

Cross-Sectoral Implementation Considerations

| Programme Name | Sector | Cross-sector impact |  | Measures to harness or mitigate the impact |
| --- | --- | --- | --- | --- |
|  |  | Synergies | Adverse effects |  |
| Administration, Planning and Support Services | All sectors/ departments | Communication, coordination and cooperation | Ineffective communication and administration systems | Setting up clear and effective communication channels. |
| Government Advisory Services | National Government, government agencies and other county governments | Collaborations and cooperation between National Government, government agencies and other county governments on various issues and overlapping functions | Overlapping functions in the two government levels | Regular meetings, agreements and MOUs to guide working relationship between the two levels of governments. |
| Leadership and Coordination of departments | All departments and National Government | Collaboration in service delivery, Conservation of environment and emergency management | Ineffective, and Uncoordinated Environmental degradation and emergencies management | Regular inter-departmental and inter-agencies meetings, Involvement of all sectors and government agencies in environmental law enforcement Regular disaster preparedness and prevention meetings |

### 3.2.3 County Public Service Board

Vision

To be a leading agency of excellence in county public service, management and development.

Mission

To provide policy direction in human resource management and development, advice on appropriate organization structures initiate and coordinate human resource reforms to improve service delivery in county public service for sustainable socio-economic development.

Sub sector Goals

- To provide the right quality and quantity of employees

- To ensure optimal utilization of human resources in Kiambu county

- To promote and sanction employees based on set targets

- To comply with the appropriate legal and corporate governance frameworks

- To achieve inclusivity as stipulated in the regulatory framework

- To increase quality of service delivery to stakeholders as per the service level agreements

- To increase operational efficiency in service delivery

- To establish necessary offices and to abolish unnecessary offices

CPSB stakeholders

| Stakeholder category | Stakeholder expectation | Sector expectation |
| --- | --- | --- |
| National Government | Adherence and proper implementation of the legal framework | Provision of legal framework |
| County Assembly | Comply with the stated laws and policies | Enact laws and policies |
| Line department | - Provide service in terms of information particularly on human resource requirements - Understanding of HR policy and staffing needs - Facilitate effective staff motivation - Practice good governance | - Receive timely sectoral information for HR policy formulation - Effective implementation of HR policies - Proper coordination with other line departments |
| Citizens | Good service delivery | Service delivery and public participation |

Non-Capital Projects

Table 46: County Public Service Board Non-Capital Projects for FY 2018/19

| Programme Name: General Administration, Planning and Support Services |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Sub Programme | Project name Location (Ward/Sub county/ county wide) | Description of activities | Green Economy consideration | Estimated cost (Ksh.) | Source of funds | Time frame | Performance indicators | Targets | status | Implementing Agency |
| SP 1.1 Administration and Personnel services | Staff recruitment and promotion | Recruiting and promoting staff |  | 30M | CGK | 2018-2019 | % of successful recruitments and promotions done | 30 |  | County Public Service Board |
|  | Personal emoluments | Budget allocation to personal emoluments |  | 25.8M | CGK | 2018-2019 | Amount in Kshs allocated per annum for personal emoluments | 23M |  |  |
|  | Disciplinary cases resolution | Resolving disciplinary cases |  |  | CGK | 2018-2019 | % of disciplinary cases successfully resolved | 40 |  |  |
|  |  |  |  |  | CGK | 2018-2019 | % of staff satisfaction | 20 |  |  |
|  | Competence inventory | Issuing competence inventory |  |  | CGK | 2018-2019 | Number of competence inventory | 1 |  |  |
|  | Manuals development | Developing manuals |  |  | CGK | 2018-2019 | No. of Manuals developed. | 1 |  |  |
|  | Staff sensitization forums | Sensitizing staff |  | 18M | CGK | 2018-2019 | Number of constitution sensitization forums held(Article 10 and 232) | 12 |  |  |
|  | Advisory meetings | Holding advisory meetings |  | 5M | CGK | 2018-2019 | Number of human resource advisory meetings held | 4 |  |  |
|  | Training and capacity building | Training staff |  | 5M | CGK | 2018-2019 | Number of capacity building /Trainings conducted | 2 |  |  |
| Total |  |  |  | 83.8M |  |  |  |  |  |  |

### 3.2.4 Finance, ICT and Economic Planning

Vision

A strategic leader in resource mobilization, economic planning and prudent public financial management

Mission

To offer effective and efficient services in resource mobilization, public finance management, coordination, economic planning and development for a safe and harmonious county.

Sector Goal

The sector goal is to mobilize public resources and ensure efficient allocation of the resources to the county expenditure priorities for enhanced accountability and service delivery.

Development needs, Priorities and Strategies

| Need | Priority | Strategy |
| --- | --- | --- |
| Planning, policy document formulation and results tracking | - County Development plans, Budgets, CBROP, CFSP, FEP strategic plan, Procurement plan, annual work plan, Finance and Appropriation bills - Monitoring and evaluation legal framework - Data management | - Formulation, development and implementation of sectoral policies and programmes - Formulation of M&E legal framework and Establishment of CIMES - Regular data collection and management to support evidence based decision making - Operationalizing the M&E system in the county through E-NIMES |
| Linkages between policy, planning and budgeting | Strengthen the MTEF process at all levels | - Deepen MTEF process by basing it on the CIDP - Cascade and operationalize the MTEF process at the Sub County and ward level - Institutionalize Public Expenditure Review (PER) and use it as a basis to allocate resources annually |
| Coordination and tracking the implementation of CIDP | Capacity to provide leadership and coordination required for successful implementation of the CIDP | - Establishment of the Sector Working groups and County Budget and Economic Forum. - Preparation of annual budgets - Provide leadership in fast tracking of the implementation of CIDP. - Establish a clear operational framework between the Sector Working Groups and the Departments. - Track progress of the implementation of CIDP - Mid Term and End Term reviews of CIDP - Training staff and citizens on CIDP |
| Human Resource Development | Capacity building | - Prepare staff establishment - Identification of training needs - Provide staff capacity developments and Trainings |
| Internal Revenue | Revenue enhancement | - Revenue mapping - Revise fees, rates, levies, - Reduce revenue leakages and seal loopholes - Broaden the fees, rates and levies base - Adopt appropriate technology in revenue collection - Enhance capacity of the revenue collectors - Sensitization of the public on fees, rates and levies compliance |
| Public Finance management | - Compliance to financial regulations - Internal and external audits - Public procurements - Accountability of public resources | - Institutionalize strong accounting internal control systems - Carry out regular audits - e-procurement - Proper maintenance of accounting records, - Timely provision of financial reports. - Monitoring of revenue and expenditures approved by County Assembly |
| Office space | - County and Sub county Finance and Economic Planning offices - Financial and non financial resources | - Construction and equipping of County and Sub county Finance and Economic Planning offices - Allocate adequate resources to run these offices |

Stakeholders Analysis

The sector takes cognizance of the many stakeholders and their varied expectations which the sector intends to meet. The sector in turn has expectation of these stakeholders which it hopes will be equally met. Table below presents a synthesis of the stakeholders and an analysis of the various expectations.

| Stakeholder Category | Stakeholder Expectation | Sector Expectation |
| --- | --- | --- |
| Line Departments | - Provide service in terms of information particularly data, monitoring and evaluation of development projects and programmes - Understanding of their policy and planning needs - Facilitate effective mobilization, of resources - Deployment of qualified officers - Involve all line Departments in budgeting, planning and decision making - Undertake effective monitoring and evaluation of the programs undertaken - Program sustainability - Practice good governance | - Receive sectoral information for planning, budgeting, policy formulation and Monitoring and Evaluation purposes - Ensure efficient allocation and utilization of resources - Effective implementation of policies - Proper coordination with other line departments |
| Development Partners | - Provide timely reports and reviews - Effective and efficient resource utilization - Achievement of project goals and outcomes - Involvement of stakeholders in the various aspects of county planning, budgeting and development - Adherence to project regulations and philosophies - Plan project sustainability - Practice the principles of good governance - Continuous monitoring and evaluation and provision of reports | - Support the government in the implementation of development projects and programmes - Support specific programmes whose implementation is coordinated by the Department. - Timely disbursement of promised resources - Provision of technical assistance and capacity building - Understanding and responsiveness of Department’s challenges, needs and expectations - Effective collaboration and synergy building - Consistency and commitment |
| National Government | - Provide timely and accurate reports - Effective and efficient resource utilization - Involvement of stakeholders in the various aspects of county planning, budgeting and development | - Timely disbursement of funds - Provision of technical assistance and capacity building - Effective collaboration |
| Suppliers/Merchants | - Timely disbursement of payments for goods and services supplied - Transparent procurement process | - Timely supply of procured goods and services - Supply of high quality goods and services |
| Staff | - Commitment to their welfare - Conducive work environment where individuals are trusted, respected and appreciated - Favourable terms & conditions of service - Training & Development - Fair appraisal - Rewards/Incentive system | - Provide the necessary manpower and human resource capacity - Commitment & productivity - Portray the right image of Department - Adherence to policies, rules, & regulations of Department - Provide effective and efficient services to partners and stakeholders |
| Public | - Practice participatory planning budgeting and management practices - Understanding of their needs and expectations and plan for them - Initiating sustainable projects for poverty reduction - Achieving project outcomes - Ensure good governance and ethical behaviour - Successful implementation of the CIDP | - Providing local support to Departments policies and initiatives - Participating in local development projects and decision making - Participate in project monitoring and evaluation - Participate in planning and budgeting process |
| Research/academic institutions | - Provide internship to students from such institutions - Set the policy agenda - Provide complementary data and information - Partnership/collaboration in research and policy formulation | - Provide the necessary training to the Department’s staff |
| Media | - Receive timely and accurate information - Accessibility to facts | - Disseminate timely and accurate information |
| Private sector | - Involvement in the planning and budgeting process - Sustainable investment policies - Provision of reliable information on development indicators - Effective and efficient service delivery - Practice principles of good governance | - Partner in the implementation of development projects and programmes. - Partner with the Department in determining the policy agenda - Increase local investment - Improved governance and institutional capacity |
| Professional Bodies (Lawyers, medical Practitioners, Surveyors, Engineers etc) | - Provision of reliable data and information - Establish IEC partnerships | - Partner in the implementation of development projects and programmes. - Provision of reliable data and information |
| Senate/County Assembly/political parties | - Provide reliable data/information required for the allocation of devolved funds and other development programmes - Well trained staff - Proper use of resources and accounting - Senate/County questions satisfactorily responded to | - Partner in development particularly at the local levels - Provide the necessary checks - Provide inputs to the policy formulation and budgeting and planning process through party manifestos |
| Political Leadership | - To develop strong institutional capacity that enhances service delivery and achievement of development goals - Competent and skilled personnel - Adherence to rules and regulations of the government - Development and tracking of policies - Advisory/policy services on the economy | - Provide measures of good governance - Promotion of good image & reputation - Provide strategic direction and leadership - Formulation of relevant policies - Facilitate resource mobilization |
| Office of Governor | - Provide the required information to facilitate coordination of all the Departments | Guidance and support |
| Judiciary | - Abide by the law to minimise risks and exposure of government to legal tussles - Propose new/changes to the law to make the economy competitive and ensure best practices | Provide support in legal matters affecting policy formulation and financial planning |
| Non-State actors (NGOs, CBOs, FBOs etc.) | - Provision of reliable information on development indicators - Collaboration to incorporate their issues in the policy documents | Compliment the Department in the implementation of development projects and programmes |

Capital and Non-Capital Projects

Table 47: Finance, ICT and Economic Planning Capital Projects for FY 2018/19

| Programme Name |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Sub Programme | Project name Location (Ward/Sub county/ county wide) | Description of activities | Green Economy consideration | Estimated cost (Ksh.) | Source of funds | Time frame | Performance indicators | Targets | status | Implementing Agency |
| ICT infrastructures | LAN Connections/ Coun ty wide | Installation of LAN |  | 20M | CGK | 2018-2019 | No of offices connected to with functional LAN | 20 | New | FEP |
|  | Public Hotspots/ County Wide | Installation of Public hotspots/ County wide |  | 40M | CGK | 2018-2019 | No. of public hotspots | 12 | New | FEP |
|  | Office WIFI Hotspot / County wide | Installation of WIFI hotspots/ County wide |  | 30M | CGK | 2018-2019 | No of active office WiFi hotspot | 20 | New | FEP |
|  | ICT hubs/ County wide | Construction of ICT hubs |  | 60M | CGK | 2018-2019 | No. of operational ICT hubs constructed and equipped | 3 | New | FEP |
| Management information system | e-platforms/ County wide | Development of e-platforms |  | 10M | CGK | 2018-2019 | No of e-platforms developed and in use | 1 | New | FEP |
|  | e-registered youths database/ County wide | e- registration of youth on County data base |  | 5M | CGK | 2018-2019 | No of e-registered youths on the County data base | 1000 | New | FEP |
| Total |  |  |  | 165M |  |  |  |  |  |  |

Table 48: Finance, ICT and Economic Planning Non-Capital Projects for FY 2018/19

| Programme P1:General Administration, Planning and Support Services |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Sub Programme | Project name Location (Ward/Sub county/ county wide) | Description of activities | Green Economy consideration | Estimated cost (Ksh.) | Source of funds | Time frame | Performance indicators | Targets | status | Implementing Agency |
| Administration Services | Preparation of finance and Appropriation bills Headquarters | Drafting of bill |  | 6M | CGK | 2018/19 | No of finance and Appropriation bills drafted and tabled to the county assembly | 2 | On going | FEP |
|  | CBEF committee Headquarters | Establishment of CBEF committee |  | 1M | CGK | 2018/19 | CBEF committee formed and functional | 1 | On going | FEP |
|  | Capacity Building Headquarters | Conduct trainings |  | 2M | CGK | 2018/19 | No. of CBEF trainings conducted | 2 | On going | FEP |
|  | Construction of office block (County wide ) | Construction works |  | 20M | CGK | 2018/19 | No of office blocks constructed | 2 | On going | FEP |
| Personnel services | Staff training County wide | Training of officers |  | 8M | CGK | 2018/19 | Number of officers capacity built | 806 | On going | FEP |
|  | Staff registration Headquarters | Registration of officers |  | 3M | CGK | 2018/19 | Number of staffs registered with professional bodies | 180 | On going | FEP |
|  | Preparation of audit report Headquarters | Writing Audit reports |  | 2M | CGK | 2018/19 | Number of HR audit done | 1 | On going | FEP |
| Financial services | personal emolument County wide | Budget allocation to personal emoluments |  | 600M | CGK | 2018/19 | Amount in Kshs allocated per personal emoluments | 806 | On going | FEP |
|  | Office operation County wide | Budget allocation to operation and maintenance |  | 719M | CGK | 2018/19 | Amount allocated operation and maintenance. |  | On going | FEP |
| Total |  |  |  | 1.361B |  |  |  |  |  |  |

| Programme P2: Financial Management Services |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Sub Programme | Project name Location (Ward/Sub county/ county wide) | Description of activities | Green Economy consideration | Estimated cost (Ksh.) | Source of funds | Time frame | Performance indicators | Targets | status | Implementing Agency |
| Accounting, Financial Standards and Reporting | Preparation of accrual based and cash based financial statements County wide | Preparation and presentation of accrual based and cash based financial statements |  | 2M | CGK | 2018/19 | % compliance to IPSAS | 40% | On going | FEP |
|  | Preparation of Financial statements Headquarters | Preparation of quarterly financial statements |  | 2M | CGK | 2018/19 | Number of quarterly financial statements prepared and submitted | 4 | On going | FEP |
|  | Preparation of financial statements Headquarters | Preparation of financial statements |  | 2M | CGK | 2018/19 | Number of annual financial statements prepared and submitted | 1 | On going | FEP |
| Procurement and Supply Chain Management | Procurement laws and regulations County wide | Implementation of Procurement laws and regulations |  | 2M | CGK | 2018/19 | % compliance to Procurement laws and regulations | 40% | On going | FEP |
|  | Preparation of plan Headquarters | Preparation of plan |  | 2M | CGK | 2018/19 | Number of annual procurement plans prepared | 1 | On going | FEP |
| Internal Audit | internal controls County wide | Implementation of internal controls |  | 2M | CGK | 2018/19 | % compliance | 45% | On going | FEP |
|  | Preparation of reports County wide | Preparation of reports |  | 2M | CGK | 2018/19 | Number of quarterly audit reports prepared | 4 | On going | FEP |
|  | Preparation of reports County wide | Preparation of reports |  | 2M | CGK | 2018/19 | Number of internal annual audit reports prepared and submitted | 1 | On going | FEP |
|  | Trainings County wide | Conduct trainings |  | 2M | CGK | 2018/19 | Number of capacity building sessions on audit committee | 2 | On going | FEP |
| Total |  |  |  | 18M |  |  |  |  |  |  |

| Programme P3: Economic Planning and Budgetary Services |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Sub Programme | Project name Location (Ward/Sub county/ county wide) | Description of activities | Green Economy consideration | Estimated cost (Ksh.) | Source of funds | Time frame | Performance indicators | Targets | status | Implementing Agency |
| Economic policy and County planning | Preparation of a plan Headquarters | Preparation of a plan |  | 12M | CGK | 2018/19 | Number of CIDP prepared and submitted to the county assembly | 1 | On going | FEP |
|  | Preparation of a plan Headquarters | Preparation of a plan |  | 1M | CGK | 2018/19 | Number of ADP prepared and submitted to the county assembly | 1 | On going | FEP |
|  | public participation forums County wide | Conduct public participation forums |  | 2M | CGK | 2018/19 | No of ward public participation meetings held | 60 | On going | FEP |
| Monitoring and Evaluation | Reports County wide | Report writing |  | 4M | CGK | 2018/19 | Number of monitoring and evaluation reports | 4 | On going | FEP |
| County Statistical information services | Surveys County wide | Conduct surveys |  | 2M | CGK | 2018/19 | Number of surveys done and quality assessment | 1 | On going | FEP |
|  | county fact sheet County wide | Updating of county fact sheet |  | 3M | CGK | 2018/19 | Number of county fact sheets develop, updated and disseminated | 1 | On going | FEP |
| Budget and expenditure | Budget Headquarter | Budget preparation |  | 4M | CGK | 2018/19 | Percentage of development budget to total county budget | 31 | On going | FEP |
|  | Preparation of CBROP Headquarter | Drafting of CBROP |  | 2M | CGK | 2018/19 | Number of CBROP prepared and submitted to the county assembly | 1 | On going | FEP |
|  | Preparation of CFSP Headquarter | Drafting of CFSP |  | 2M | CGK | 2018/19 | Number of CFSP prepared and submitted to the county assembly | 1 | On going | FEP |
|  | Preparation of PBB Headquarter | Drafting of PBB |  | 2M | CGK | 2018/19 | Number of PBB prepared and submitted to the county assembly | 1 | On going | FEP |
| Total |  |  |  | 34M |  |  |  |  |  |  |

| Programme P4: Resource Mobilization And Revenue |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Sub Programme | Project name Location (Ward/Sub county/ county wide) | Description of activities | Green Economy consideration | Estimated cost (Ksh.) | Source of funds | Time frame | Performance indicators | Targets | status | Implementing Agency |
| SP 4.1 Revenue Generation and Estimates Modelling | Local revenue County Wide | Collection of local revenue |  | 50M | CGK | 2018/19 | Amount in kshs(million ) collected annually as internal revenue | 2.6B | On going | FEP |
|  | Revenue automation County Wide | Automation of revenue |  |  | CGK | 2018/19 | Number of automated Revenue streams | 1 | On going | FEP |
| Total |  |  |  | 50M |  |  |  |  |  |  |

Cross-Sectoral Implementation Considerations

| Programme Name | Sector | Cross-sector Impact |  | Measures to Harness or Mitigate the Impact |
| --- | --- | --- | --- | --- |
|  |  | Synergies | Adverse impact |  |
| Resource Mobilization and Revenue | All sectors | Increased County revenue | High resistance from citizens | Improved and efficient service delivery |
| Economic planning and budgetary services | All sectors | Improved efficiency and proper expenditure controls |  | Encourage proper planning |
| Financial management services | All sectors | Compliance to international public sector , accounting standards (IPSAS) |  |  |

### 3.2.5 Administration, Public Service and Communication

Vision

A people-centred, transformative and accountable administration and public service.

Mission

To provide effective and efficient services through guided formulation and implementation of regulatory framework to the public.

Sub-sector goals and targets

Administration and Public Service

- To provide effective and efficient services to the public.

- To ensure coordination of various structures within the county.

Human Resource Management

- To develop and maintain an effective and efficient county workforce.

- Effectively planning future staffing requirements.

- Carry out staff training and development.

- Conduct staff performance management.

Enforcement, Monitoring and Compliance

- To enforce various county laws to ensure compliance.

- Well-coordinated, efficient and effective enforcement unit.

Betting and Gaming Control

- To enhance responsible betting and curb illegal gambling, lotteries and gaming.

- Authorization and control of prize competition and lotteries.

- To create awareness and public confidence in betting, lotteries and gaming.

Alcoholic Drinks Control

- To reduce and create awareness on alcohol, drug and substance abuse and offer rehabilitation services.

- Public education on alcoholic drinks control in the county.

- Collaboration with other public institutions and non-state actors.

- Undertake research on alcohol related issues and disseminate findings.

Public Participation

- Conduct public participation to create citizen awareness on services offered by the county government.

- Enhance civic engagement on county matters.

Communication

- Improve dissemination of information on governance to the members of the public through diversified platforms of communication.

Performance Management

- Developing and implementing Performance Contracting

- Conducting staff performance appraisal systems.

Strategic priorities of the sector

| Development need | Priority | Strategy |
| --- | --- | --- |
| Human Resource Development | Capacity building | - Prepare staff establishment. - Identification of training needs. - Conduct staff capacity developments and trainings |
| Office space | - County and Sub county offices. - Financial and non-financial resources. | - Construction and equipping of County and Sub county offices. - Allocate adequate resources to run these offices. |
| Public Education and Awareness | - Community participation - Alcohol and substance abuse sensitization - Curbing of illegal gambling and irresponsible betting. | - Engaging the public on participation during projects/programs, prioritization and legislation. - Applying preventive science as a measure to fight alcohol and substance abuse during meetings and workshops. - Public meetings and forums to sensitize the public against illegal gambling. |
| Enforcement, monitoring and compliance | Empower County enforcement unit. | - Providing staff uniforms and equipment. - Staff training and Capacity building. |
|  | Adherence to law and order in the county | - Conduct raids, crackdowns, arrests and charging those who do not comply with the set County laws. - Provision of adequate resources to ease operations i.e transport and subsistence allowances |
| Alcoholic Drinks Control | Construction of a county treatment and rehabilitation Centre | - Allocate adequate resources to put up the centre - Construction and equipping referral centre |
| County Headquarters’ exit, public lounge and ablution block. | Safety, security and service delivery. | - Construction of an exit gate. - Construction and equipping of a public lounge. - Construction and furnishing of an ablution block |
| One stop shop for county services | Centralization of services | - Construction of a one stop building where the citizens can access all county services under one roof. |
| Communication | Increase awareness of government services and operations to the members of the public | - Developing and dissemination of county monthly magazine - Increased use of online platforms in communicating government programmes. |
| Performance Management | Performance contracts Staff performance appraisal system | - Create a performance management directorate. |

Sector stakeholder’s analysis

| Stakeholders Category | Stakeholders Expectation | Sector Expectation |
| --- | --- | --- |
| Public / citizen | - Provide information pertaining to various county activities, project and programmes. - Ensure good governance of and ethical behavior. - Efficient service delivery - Involvement in decision making on county programmes and projects. | - Provide local support to the department initiatives - participate in public forums to give their views and opinions - To abide to the county laws and regulation. - To participate in various decision making. |
| County public service board | - Provide information regarding various staff gaps and establishment - Provide information regarding various staff issues e.g. promotions | - Advisory services - Recruitment and selection of qualified staff |
| National government | - Provide timely and accurate reports - Utilize resources efficiently and effectively - Involvement of various stakeholders in development | - Timely disbursement of funds - Provision of technical assistance and capacity building - Effective collaboration |
| Development partners | - Provide timely and accurate reports - Achievement of various projects and outcomes - Practice the principle of good governance - Prudent utilization of resources - Effective monitoring and evaluation of projects | - Support in implementation of various development projects - Provision of technical assistance - Effective collaboration |
| Parastatals | - Collaboration and cooperation during implantation of various projects | - Provision of technical support and assistance - Advisory services |
| Training institutions | - Collaboration and cooperation - Provide information on various training needs arising | - Collaboration and cooperation - Provision of effective and relevant skills |
| County Assembly | - Prudent use of resources and accounting - Implementation of set laws and policies | - Provision of oversight role - Enact laws and approve various bills and policies |
| Non state actors | - Collaboration and cooperation - Provide relevant information and data - Creation of an enabling environment | - Technical and financial support - Advisory services |
| Corporates | - Collaboration and cooperation - Prudent use of resources - Adherence to various project regulations and philosophies | - Effective collaborations and synergy building - Consistency and commitment |

Capital and Non-Capital projects

- Providing enhanced medical scheme for the members of staff.

- Creating the function of Health and Safety with the county.

- Adoption of Human Resource policies within the county.

- Promotions for staff that deserve them in all the ten departments.

- Streamlining of staff welfare matters across the county.

- Carry out a survey on the status of alcohol, drug and substance abuse in the county.

- Completion of Juja sub county offices.

- Renovation of Kiambu sub county offices.

- Renovation of Gatundu North sub county offices.

- Construction of public toilets and Refurbishment of banking hall at Kiambu headquarter offices.

- Renovation of Gatundu South offices.

- Construction of Lari sub county offices.

- Construction of Lusegetti County Referral, Treatment and Rehabilitation center.

- Roll out public education and campaigns on alcohol and drug abuse.

- Intensify crackdown on illegal, sub-standard, counterfeit and illicit brews.

- Betting control and crackdown on illegal and irresponsible gambling, illegal betting and gambling machines.

- Public engagement in civic education and citizen sensitization.

- Public communication through various media platforms.

- Enforcement services to ensure county laws and regulations are adhered to.

Table 49: Administration, Public Service & Communication Capital projects for the FY 2018/2019

| Programme Name: Administration, Planning and Support Services |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Sub programme | Project name location (ward/sub county/county wide) | Description of activities | Green economy consideration | Estimated cost (Kshs) | Source of funds | Timeframe | Performance indicators | Targets | Status | Implementing agency |
| Administration services | Sub county offices – Kabete, Juja, Lari, Kiambu, Gatundu North and South | Construction and equipping sub county offices | NEMA rules to be observed Planting of trees | 70M | CGK | 2018 - 2022 | Number of Office blocks constructed | 1 | New project | Admin & PS RTPW&U |
|  | County headquarters exit gate | Construction of exit gate | NEMA rules to be observed Planting of trees | 7M | CGK | 2018/2019 | The number Gate constructed | 1 | New project | Admin & PS RTPW&U |
|  | County headquarters public lounge | Construction and furnishing of a public lounge | NEMA rules to be observed Planting of trees | 10M | CGK | 2018/2019 | The number of Lounge constructed and furnished | 1 | Ongoing | Admin & PS RTPW&U |
|  | County headquarters one stop county service centre | Construction and equipping of a one stop county service centre. | NEMA rules to be observed Planting of trees | 20M | CGK | 2018-2022 | Number of One stop county service centre constructed | 1 | New project | Admin & PS RTPW&U |
|  | County headquarters ablution block | Construction and equipping of ablution block. | NEMA rules to be observed Planting of trees | 5M | CGK | 2018/2019 | Number of ablution block constructed | 1 | Ongoing | Admin & PS RTPW&U |
|  | Purchase of motor vehicles | Purchase of motor vehicles. |  | 15M | CGK | 2018-2022 | Number of motor vehicles purchased. | 3 | New project | Admin & PS |
| Total |  |  |  | 127M |  |  |  |  |  |  |

| Programme Name: ALCOHOL, DRUG AND SUBSTANCE ABUSE CONTROL AND REHABILITATION |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Sub programme | Project name location (ward/sub county/county wide) | Description of activities | Green economy consideration | Estimated cost (Kshs) | Source of funds | Timeframe | Performance indicators | Targets | Status | Implementing agency |
| Rehabilitation services | County referral rehabilitation and treatment centre – Lusegetti, Kikuyu. | Construction and equipping of a county referral rehabilitation and treatment centre. | NEMA rules to be observed Planting of trees. | 12M | CGK | 2018-2022 | Number of completed rehabilitation and treatment centre. | 1 | New project | Admin & PS RTPW&U |
| Total |  |  |  | 12M |  |  |  |  |  |  |

Table 50: Administration, Public Service & Communication Non Capital projects for the FY 2018/2019

| Programme Name: Administration, Planning and Support Services |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Sub programme | Project name location (ward/sub county/county wide) | Description of activities | Green economy consideration | Estimated cost (Kshs) | Source of funds | Timeframe | Performance indicators | Targets | Status | Implementing agency |
| Administration services | Refurbishment of sub county offices in Limuru, Ruiru, Kiambu, Kiambaa, Kikuyu. | Renovation, refurbishment and rehabilitation of sub county offices. | NEMA rules to be observed. Planting of trees. | 10.29M | CGK | 2018-2022 | Number of offices renovated | 5 | Ongoing | Admin & PS RTPW&U |
| Personnel Services | Delivery and improvement in personnel services | Allocation of budget to P.E |  | 357.9M | CGK | 2018-2022 | Number of staffs remunerated, and allowances paid | 357.9M | ongoing | Admin & PS |
| Financial Services | Execution and delivery of financial services | Allocation of budget to O & M |  | 146.5M | CGK | 2018-2022 | Number of financial operations carried out | 146.5M | Ongoing | Admin & PS |
| County Inspectorate services | County enforcement uniforms and equipment. | Purchase of uniforms and equipment for county inspectorate officers. |  | 5.4M | CGK | 2018-2022 | Number of uniforms and equipment purchased. | 300 | New project | Admin & PS |
| Total |  |  |  | 517.9M |  |  |  |  |  |  |

| Programme name: Alcohol, Drug and Substance Abuse, Control and Rehabilitation |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Sub programme | Project name location (ward/sub county/county wide) | Description of activities | Green economy consideration | Estimated cost (Kshs) | Source of funds | Timeframe | Performance indicators | Targets | Status | Implementing agency |
| Rehabilitation services | Prevention and Treatment programmes. | Initiate prevention and treatment programmes through partnerships. |  | 3.7M | CGK | 2018-2022 | Number of prevention and treatment programmes initiated and implemented through partnerships. | 24 | Ongoing | Admin & PS, NACADA, CSOs, CBOs, FBOs |
|  | Drop in centres in county Level 4/ health centres (at least one per sub county). | Establishment and equipping of drop in centres. |  | 6.1M | CGK | 2018-2022 | Number of drop in centres operationalized. | 12 | New project | Admin & PS |
|  |  | Treatment and rehabilitative services. |  | 2M | CGK | 2018-2022 | Percentage increase in the number of people accessing treatment and rehabilitative services. | 10% | New | Admin & PS |
| Enforcement and crackdown | Reduction of illicit, substandard, counterfeit and illegal alcohol in the county. | Enforcement and crackdown on illicit, substandard, counterfeit and illegal alcohol. |  | 4.72M | CGK | 2018-2022 | Percentage reduction on illicit, substandard, counterfeit and illegal alcohol. | 16% | Ongoing | Admin & PS |
| Intervention programmes for illicit brewers | Alternative programmes for illicit brewers in the county | Initiate intervention programmes for illicit brewers as alternative to brewing. |  | 6.2M | CGK | 2018-2022 | Number of people engaged in alternative businesses/ programme/ projects initiated. | 300 | Ongoing | Admin & PS |
| Public education and awareness | Sensitization campaigns on drug and substance abuse in the county. | Facilitate public education and awareness on harmful use of alcohol, drugs and substances. |  | 1.5M | CGK | 2018-2022 | Number of people sensitized on dangers of harmful use of alcohol, drugs and substances. | 12,000 | Ongoing | Admin & PS |
| Research on alcohol, drug and substance abuse. | Status report on alcohol, drug and substance abuse in the county. | Carry out a research on the status of alcohol, drug and substance abuse and disseminate results. |  | 0.6M | CGK | 2018-2022 | Number of status reports prepared. | 1 | New | Admin & PS NACADA |
|  |  | Employ intervention strategies based on the outcomes of the research. |  | 0.4M | CGK | 2018-2022 | Percentage increase in the number of intervention strategies put in place. | 5 | New | Admin & PS NACADA |
| Total |  |  |  | 25.2M |  |  |  |  |  |  |

| Programme Name: Betting and Gaming |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Sub programme | Project name location (ward/sub county/county wide) | Description of activities | Green economy consideration | Estimated cost (Kshs) | Source of funds | Timeframe | Performance indicators | Targets | Status | Implementing agency |
| Betting Control, Licensing And Regulation Services | Formalization and control of betting and gaming industry in the county. | Carry out registration and licensing for betting outlets. |  | 0.43M | CGK | 2018-2022 | Percentage reduction in the number of illegal betting outlets. | 30% | Ongoing | Admin & PS |
| Public education and awareness. | Sensitization campaigns on responsible betting and gaming | Educate the public on responsible and illegal gambling. |  | 1.02M | CGK | 2018-2022 | Number of public awareness forums held. | 13 | Ongoing | Admin & PS |
| Enforcement and crackdown. | Reduction of illegal betting and gaming machines and outlets. | Intensify enforcement and crackdown on illegal gambling and gaming outlets. |  | 0.425M | CGK | 2018-2022 | Percentage reduction on illegal betting and gaming machines and outlets. | 30% | Ongoing | Admin & PS |
| Total |  |  |  | 1.87M |  |  |  |  |  |  |

| Programme Name: Public Participation and Citizen Petitions |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Sub programme | Project name location (ward/sub county/county wide) | Description of activities | Green economy consideration | Estimated cost (Kshs) | Source of funds | Timeframe | Performance indicators | Targets | Status | Implementing agency |
| Civic education and public sensitization. | Awareness on county service delivery structures in the county. | Sensitize the public on various service delivery structures on the county. |  | 2.04M | CGK | 2018-2022 | Number of information, education and communication (IEC) materials disseminated. | 12000 | New | Admin & PS |
| Public participation, civic engagement and citizen petitions. | Public participation forums. | Enhance public participation and citizen engagement on county matters. Formulation of public participation and civic education guidelines/policies through partnerships with other state and non-state agencies. |  | 4.4M | CGK | 2018-2022 | Number of public participation forums held. | 60 | Ongoing | Admin & PS |
|  | Guidelines on public participation. |  |  | 1M | CGK | 2018-2022 | Number of guidelines / policies developed. | 1 | New | Admin & PS with partners |
| Complaints & Feedback handling mechanism. | Formulation of complaints and feedback mechanisms. | Formulate mechanisms for complaints and feedback handling. |  | 3.4M | CGK | 2018-2022 | Number of complaints and feedback mechanisms formulated. | 1 | New | Admin & PS |
| Total |  |  |  | 10.88M |  |  |  |  |  |  |

| Programme Name: Human Resource Management Services |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Sub programme | Project name location (ward/sub county/county wide) | Description of activities | Green economy consideration | Estimated cost (Kshs) | Source of funds | Timeframe | Performance indicators | Targets | Status | Implementing agency |
| Human Resource Management. | Human resource policies and surveys. | Establishment of human resource policy and conducting staff surveys. |  | 1.4M | CGK | 2018-2022 | Number of human resource policies developed. | 1 | Ongoing | Admin & PS |
|  |  |  |  |  |  |  | Number of staff surveys conducted | 1 | New | Admin & PS |
|  | Performance management | Performance contracting, training of Staff on performance management, conduct staff performance appraisal and rationalization. |  | 0.9M | CGK | 2018-2022 | Number of performance contracts. Number of staff trained. Number of staff appraised. Number of staff rationalization reports prepared. | 1 150 150 1 | New | Admin & PS |
| Human Resource Development | Enhanced staff capacity | Conduct staff training needs assessment. |  | 0.425M | CGK | 2018-2022 | Number of staff training needs assessments done. | 1 | New | Admin & PS |
| Anti-corruption | Anti-corruption and ethical practices. | Reduce unethical and corrupt practices, Conduct staff training on Public Officers Ethics Act 2003. |  | 0.714M | CGK | 2018-2022 | % reduction on unethical and corrupt practices. | 10% | Ongoing | Admin & PS |
|  |  |  |  |  |  |  | Number of officers trained | 1500 | New | Admin & PS |
| Total |  |  |  | 3.4M |  |  |  |  |  |  |

| Programme Name: Communication |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Sub programme | Project name location (ward/sub county/county wide) | Description of activities | Green economy consideration | Estimated cost (Kshs) | Source of funds | Timeframe | Performance indicators | Targets | Status | Implementing agency |
| Public Communication | Monthly county newspaper. | Printing and distribution of monthly county newspaper. | Inclusion of articles and adverts raising awareness of environmental conservation. | 0.75M | CGK | 2018-2022 | Number of Monthly newspaper copies printed and distributed. | 1000 | Ongoing | Admin &PS |
|  | Digital platforms | Creation of additional digital platforms. | Reduction in use of paper | 1.1M | CGK | 2018-2022 | Number of active digital platforms | 6 | Ongoing | Admin & PS |
|  | Customer care desk and information box. | Establishment of customer care desks and information boxes. |  | 1.1M | CGK | 2018-2022 | Number of customer care desks and information boxes established. | 12 | Ongoing | Admin & PS |
|  | Media advertisements | Advertisement of county developments and information on various media platforms. | Inclusion of articles and adverts raising awareness of environmental conservation. | 17.6M | CGK | 2018-2022 | Number of adverts featured in newspaper, radio and TV platforms. | 250 | Ongoing | Admin & PS |
| Total |  |  |  | 20.5M |  |  |  |  |  |  |

Cross -Sectoral Implementations and Considerations

The sector will ensure that all the issues related to the youth, people living with disabilities and women are mainstreamed as per the Constitution of Kenya. This will be done through encouraging women, people living with disabilities and youth to fully participate in matters of community interest during the public participation meetings. To achieve gender equality, the sector is implementing the 30 percent representation in any new employment, management and decision making committee. The sector will sensitize the county staff and community on HIV /AIDS and encourage them to undergo Voluntary Counselling and Testing. This will be done during the public participation meetings and workshops. The Sub County Administrators and county staff will sensitize the community on environmental protection and management during the public forums.

| Programme Name | Sector | Cross-sector Impact |  | Measures to Harness or Mitigate the Impact |
| --- | --- | --- | --- | --- |
|  |  | Synergies | Adverse impact |  |
| Alcohol, Drug and substance abuse, control and rehabilitation. | All sectors | A healthy productive county population. | Loss of business after closure of some alcoholic drinks outlets and illegal brewing. | Provision of alternative income generating projects to those involved in illegal alcoholic trade. |
| Public Participation and Citizen petitions. | All sectors | Timely access to county information, documents and other related information relevant to county policy formulation, implementation and oversight. | A lot of resources will be spent. | Allocating budgets for public participation. Training on civic education and public participation |
| Human Resource Management | All sectors | Improved service delivery. | Requires enormous resources. | Provision of adequate budgetary allocations. Performance management |
| County enforcement | All sectors | Well-coordinated enforcement and inspectorate services. | Friction between public and the county government. | Sensitize the public on various county legislations and their importance. |
| Betting and gaming | All sectors | Responsible betting and gaming. | Loss of business after closure of some betting and gaming outlets. | Sensitization on the need for responsible betting and gaming. |
| Performance contracting | All sectors | Improved staff morale, increased staff output, improved service delivery. | Requires enormous resources. | Provision for adequate budgetary allocation. Sourcing for qualified personnel to undertake the exercise. |
| Communication | All sectors | Improved information flow between sectors and general public | Misinformation between sectors and the public. | Updating of county website and digital platforms. Improved distribution of monthly newspaper. Informative and timely advertisements in the media. |

### 3.2.6 Agriculture, Crop Production and Irrigation

The sector comprises of the following directorates:

- Crop production

- Irrigation

- Coffee & Tea

- Agribusiness & Marketing

Vision

A Healthy, Food secure and Prosperous County

Mission

To promote sustainable agriculture through capacity building on agricultural productivity, food and nutrition security, value addition, marketing, extension and infrastructural development.

Sector goals

- To create a favourable framework for sustainable development of the livestock, fisheries sector and provide support services that increase productivity, value addition and market access for the sector products

- To provide sustainable livelihoods, household food and nutritional security to families while contributing to socio economic development of Kiambu County.

General information and key statistics on the Sector

Crop Production

Major crops grown in the county include maize, beans, Irish potatoes, coffee, tea and macadamia. Their production can be summarized in the table below:

| CROPS | AREA (HA) | Average Yield | POTENTIAL |
| --- | --- | --- | --- |
| Maize | 45981 | 20 bags/Ha | 50 bags/Ha |
| Beans | 17,427 | 2 bags/Ha | 8 bags/Ha |
| Irish Potatoes | 9198 | 8 tons/Ha | 20tons /Ha |
| Coffee | 38279 | 5 kgs/tree | 20kg/tree |
| Tea | 16940 | 400mt/ha/yr | 3000mt/ha/yr |
| Macadamia | 817 | 10kg/tree | 50kg/tree |

Agricultural extension and training

The county has extension officers deployed in the ward, Sub County and county levels. The staff to farmer ratio is 1:2000. Due to this large ratio, the main extension method used is group approach which target farmer in groups of similar interests, informal or formal groups. Other approaches include Field days/ exhibitions, trade fairs and demonstrations.

Irrigation potential

Based on the available surface, sub surface water and water harvesting capacity, Kiambu county has an Irrigation potential of over 62,812 Acres (254 Km2)  So far only 7,500 Acres (12%) is under irrigation. To increase the area under irrigation, several irrigation projects have been initiated which include Kamwamba, Gatina, Wamoro, Kawira, Kiruiru, Nyamuku, Karia and Waruhiu ATC. Two water pans have also been built in Kimuyu and Waruhiu ATC.

Agribusiness & Marketing

A characteristic feature of the County’s agriculture is the dominance of primary production. Currently, 40 percent of agricultural production is lost through poor storage. There are several farmer groups undertaking value addition of agricultural produce in the county. This is mainly done for milk, bananas, honey, sunflower, spices and vegetables. The value added products include yoghurt, banana flour, sunflower oil, dried spices, dried vegetables, and jams among others.

Development needs, Priorities and Strategies

|  | Development Need | Priority | Strategy |
| --- | --- | --- | --- |
| 1. | Irrigation Water | Increase area under irrigation agriculture in the County | - Rain water harvesting into -dams -water pans -Water reservoirs - Drilling of shallow wells - Renewable energy for pumping water - Empower/capacity build community water management committees - Expand intakes - River catchment - Drip Irrigation - Conservation Agriculture |
| 2. | Extension services | Provide quality and efficient technical services to farmers across the County | - E-extension - Village Based Advisory services - New innovative technologies - Field days/ farmer field schools/farmer groups/ demonstrations/ shows and exhibitions/ symposium/ |
| 3. | Accessible, quality and affordable agricultural inputs | Seed, fertilizer, herbicides and pesticides. | - Smart Subsidy programmes - Appropriateness of inputs - Agricultural inputs fund - Input distribution system |
| 4. | Marketing | Agricultural products | Infrastructure and information development - collection centers - organized marketing system - value addition - Real time market information platforms - Information Resource Centre |
| 5. | Agro-processing | Agricultural products | Multi fruit Vegetables |
| 6. | Reduce post-harvest losses | Agricultural products | - Cold storage chains - Post-harvest storage facilities - Post-harvest training programmes |
| 7. | Crop pests and Diseases | Crops | - Pest and Disease surveillance and control - Plant clinics |
| 8. | Research | Agricultural research | - Research liaison meetings - Linkage with research institutions - Research agenda setting - Lobby for representation in research institutions |

Stakeholder Analysis

| Stakeholder category | Stakeholder expectation | Sector expectation |
| --- | --- | --- |
| Farmer | - Extension services and capacity building services - Subsidies (quality inputs) - Credit - Information on surveillance (climate, pests & diseases, market & market information) - Good infrastructure - Irrigation water | - Quality Produce - Adherence to safety standards & MRLs (maximum residue levels) |
| Farmer Organizations | - Stimulating market demands - Extension information - Enabling policy and legal framework | - Marketing - Lending - Quality inputs at affordable costs (through their bargaining power) - Provide mechanisms for post-harvest storage e.g. warehouses - Capacity building (extension services) on value addition - Bulking of produce |
| Consumers | - Availability of products - Quality &quantity products - Good prices - Clean accessible markets | - Demand quality & safe products - Buy local produce |
| Regulators (KEPHIS, PCPB, KEBS, WRMA, NEMA, WHO, FAO, MOH etc.) | - Compliance to the set standards - Political good will - Food policies & effective policy implementation structures - Financing/funding - Sufficient human resource | - Ensure only quality products get to the market - Enforcing compliance to the set standards |
| County Government | - Political goodwill from the national government, CSOs, farmers - Compliance to tax remissions - Funding - Cooperation & support from the County Assembly, private partners/NGOs | - Develop &implement policies - Provide sufficient extension services - Facilitate capacity building of the staff |
| County Department of Agriculture | - Marketing support, regulatory role, information dissemination, identification of farmers needs | - Resources: transport, equipment, , good remuneration/facilitation - More human resource |
| Agrochemical service providers | Production and promotion of the products, Trainings on use of inputs, research, identification of farmers needs | - Supportive policy framework - Security |
| Media | Market information Advisory Activism | - Supportive policy framework - Political good will |
| KFS | Technical advice and regulations on agro forestry/farm forestry | Supportive policy framework |
| Financial Partners | Financing agriculture interventions | Supportive business environment |
| Agriculture Processors | - Markets, extension and storage services - Competitive prices - Value addition | Quality products from farmers |
| Agricultural food authority (AFA) | - Marketing - Extension services | Quality products that meets quality standards |
| Training and Research Institutions | - Research and dissemination - New technologies, varieties, documentation, consultancy - Training | - Resources: human and financial; recognition, strong linkage with extension SPs, incubation centers - Supportive policy framework - Political good will |
| Agro-industries | - Manufacture and marketing agriculture products and by products | - Good Infrastructure - Supportive policy framework - Political good will - Quality and adequate input - Financing - Security |
| County Assembly | - Policy approval and amendment - Budget approval and amendment - Oversight role of CG - Constituents representation | - Resources – financial and skilled human resource - Information: context, proposed projects and budgets |
| National Government | - Policy Making - Resources - Capacity building - Infrastructure development - Security provision - Promotion and regulation of International trade - Oversight of CG - Representation of the CG - Domestication of international obligations – treaties - Promote national cohesion - Promote inter-county trade - Arbitration of inter-county disputes | - Collaboration and goodwill from CG - Information and feedback on the sector - Revenue |

Capital and Non-Capital Projects

Table 51: Agriculture, Crop Production & Irrigation Capital projects for the FY 2018/2019

| Programme Name : Agribusiness and Information Management |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Sub Programme | Project name Location (Ward/Sub county/ county wide) | Description of activities | Green Economy consideration | Estimated cost (Ksh.) | Source of funds | Time frame | Performance indicators | Targets | status | Implementing Agency |
| Agribusiness Market Development | Banana collection centre Gatundu North | Establishment of banana collection centers with storage facilities |  | 10M | CGK | 2017- 2020 | No. of collection centres with storage facilities established | 1 | ongoing | Directorate of agribusiness |
| Agricultural inputs and Financing | agro-input disposal collection point in Kikuyu, Lari, Githunguri, Kiambaa, Gatundu South, Juja, Gatundu North and Kiambu | Setting up of agro-input disposal collection point | Reduced water pollution | 3M | CGK Agro chemical companies | 2018-2021 | Number of disposal points set up | 8 | New | Directorate of agribusiness |
| Value Chain development | Coffee nursery at Waruhiu ATC | Coffee nursery establishment | Water management | 5M | CGK | 2018-2019 | No. of coffee nursery established | 1 | New | Agribusiness directorate |
|  | Model Factory in Gatundu North, South and Githunguri | Developing of model Factories | Harness solar energy for use in the factories | 20M | CGK | 2018-2020 | No. of model factories developed | 3 | New | Agribusiness directorate |
|  | Rehabilitation of coffee mill in Komothai Ward | Rehabilitation of coffee mill | Harness solar energy for use in the mill | 2M | CGK | 2018-2019 | No. of coffee mill rehabilitated | 1 | New | Agribusiness directorate |
|  | Coffee Factory in Gatundu North, South and Githunguri | Setting up waste management systems in coffee factories | Produce biogas using coffee waste | 2M | CGK | 2018-2020 | No. of coffee factories with waste management system | 3 | New | Agribusiness directorate |
| Total |  |  |  | 42M |  |  |  |  |  |  |

| Programme Name : Crop Development and Management |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Sub Programme | Project name Location (Ward/Sub county/ county wide) | Description of activities | Green Economy consideration | Estimated cost (Ksh.) | Source of funds | Time frame | Performance indicators | Targets | status | Implementing Agency |
| Irrigation Development and Water Management | Kiruiru Irrigation project –Lari Sub County | Construction of a distribution Line |  | 5M | CGK | 2015-2019 | No. h/h connected to water | 500h/h | 0ngoing | Agriculture |
|  | Wamoro irrigation project – Kikuyu Sub County | Installation of solar system pump |  | 3M | CGK | 2018-2019 | No. h/h connected to water | 100h/h | ongoing | Agriculture |
|  | Kamwamba Irrigation Project – Gatundu North | Construction of a mainline |  | 5M | CGK | 2017-2019 | No h/h connected to water | 1,000h/h | Ongoing | Agriculture |
|  | Githoito Mwiri irrigation Project-Lari Sub County | Construction of a new mainline |  | 10M | CGK | 2018-2019 | No, h/h connected to water | 600h/h | ongoing | Agriculture |
|  | Magawa irrigation project – Gatundu South Sub County | Construction of intake weir and mainline |  | 5M | CGK | 2018-2019 | No, h/h connected to water | 700h/h | Ongoing | Agriculture |
|  | Karia irrigation cannal | Rehabilitation of canal |  | 10M | CGK | 2018-2019 | No, h/h connected to water | 600h/h | Stalled | Irrigation |
|  | Gatina irrigation project in Githunguri sub county | Construction works for distribution lines |  | 10M | CGK | 2018-2019 | No, h/h connected to water | 600h/h | On-going | Agriculture |
|  | Mathuri water pan- Juja Sub County | Construction of waterpan |  | 12M | CGK | 2018-2019 | No, h/h connected to water | 600h/h | ongoing | Agriculture |
|  | Water harvesting structures and drip irrigation demonstrations In all the wards | Installation of drip kits and provision of dam liners |  | 10M | CGK | 2018-2019 | No of demonstration sites | 120 sites | New | Agriculture |
| Land and Crop Management and Productivity Enhancement | Purchase of soil testing kits in all the wards | Purchase of soil testing kits |  | 4M | CGK | 2018-2019 | No of Dumpy levels procured and distributed No of Total station set No of GPS devices purchased | 12 2 20 | New | Agriculture |
|  | Purchase of Walking Farm Tractors Kabete, Limuru, Kikuyu, Gatundu South, Thika, Lari. Kiambaa and Juja Sub counties | Purchase of Walking Farm Tractors |  | 2.5M | CGK | 2018-2019 | No of Youth groups to benefit | 8 | New | Agriculture |
| Upgrading of Waruhiu Agricultural Training Centre (ATC) | Fencing | Construction of a perimeter wall |  | 5M | CGK | 2018-2019 | Length of fence in Meters | 2800 | New | Agriculture |
|  | Storage water tank tower erection | Erection of a storage water tank tower |  | 2M | CGK | 2018-2019 | No. of storage water tank towers erected | 1 | New | Agriculture |
|  | Internet Connection and standby Generator | To procure Computers, Laptops modem and standby Generator |  | 1M | CGK | 2018-2019 | No. of Computers, Laptops modem and standby Generator procured | 2 2 2 1 | New | Agriculture |
| Revitalization of Agricultural Mechanization Services (AMS) | Purchase of farm tractor and accessories | Tractors and Accessories procured |  | 4.2M | CGK | 2018-2019 | No. of tractors and Accessories procured | 2 1 | New | Agriculture |
|  | Purchase of Survey Equipment | Survey Equipment Procured |  | 0.6M | CGK | 2018-2019 | No. of Survey equipment procured | 1 | New | Agriculture |
| Total |  |  |  | 89.3 M |  |  |  |  |  |  |

Table 52: Agriculture, Crop Production & Irrigation Non Capital projects for the FY 2018/2019

| Programme Name : Administration Planning and Support services |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Sub Programme | Project name Location (Ward/Sub county/ county wide) | Description of activities | Green Economy consideration | Estimated cost (Ksh.) | Source of funds | Time frame | Performance indicators | Targets | status | Implementing Agency |
| Administration services | Construction of Sub county offices in Kiambaa | Construction of sub-county offices | Roof water harvesting for utilization in the offices | 5M | CGK | 2018-2019 | Number of offices constructed | 1 | New | Department of Agriculture, crop production, Irrigation & marketing |
|  | Purchase of vehicles at the County headquarters | Procure vehicles for extension services |  | 6 M | CGK | 2018- 2019 | Number of vehicles procured | 2 | New | Department of Agriculture, crop production, Irrigation & marketing |
| Personnel services | Staff promotional courses county wide | Staff sponsorship for promotional and refresher courses |  | 2M | CGK | 2018-2019 | Number of staff sponsored for promotional and refresher courses | 100 | New | Department of Agriculture, crop production, Irrigation & marketing |
| Support services | Staff enhancement | Allocation of budget to personnel emoluments |  | 197M | CGK | 2018-2019 | Amount of money disbursed for personnel emoluments | 197M | New | Department of Agriculture, crop production, Irrigation & marketing |
|  | Office operations | Allocation of budget to operation and maintenance of offices |  | 33M | CGK | 2018-2019 | Amount of money disbursed for operations and maintenance | 33M | New | Department of Agriculture, crop production, Irrigation & marketing |
| Total |  |  |  | 243M |  |  |  |  |  |  |

| Programme Name : Policy, Strategy and Management of Agriculture |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Sub Programme | Project name Location (Ward/Sub county/ county wide) | Description of activities | Green Economy consideration | Estimated cost (Ksh.) | Source of funds | Time frame | Performance indicators | Targets | status | Implementing Agency |
| Policy, strategy and management of agriculture | Policy development county wide | Developing agricultural policies and regulations |  | 0.3M | CGK | 2018- 2019 | Number of policies/regulations developed | 1 | New | Department of Agriculture, crop production, Irrigation & marketing |
|  | Establishment of agricultural committees county wide | Establish of agricultural committees |  | 0.2M | CGK | 2018-2019 | Number of committees formed | 30 | New | Department of Agriculture, crop production, Irrigation & marketing |
| Agricultural planning and financial management | Preparation of financial reports | Prepare financial reports every quarter |  | Budget in O&M | CGK | 2018-2019 | No of Financial Reports done | 4 | Ongoing | Department of Agriculture, crop production, Irrigation & marketing |
|  | Preparation of strategic plan for the department | Prepare a strategic plan for the department |  | 1.5M | CGK | 2018- 2019 | Number of strategic plans prepared | 1 | Ongoing | Department of Agriculture, crop production, Irrigation & marketing |
| Sector working group support (SWG) and Liaison | Convene sector meetings county wide | Convening sector forums |  | 0.2M | CGK | 2018- 2019 | Number of forums convened | 4 | New | Department of Agriculture, crop production, Irrigation & marketing |
| Total |  |  |  | 2.2M |  |  |  |  |  |  |

| Programme Name: Agribusiness and Information management |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Sub Programme | Project name Location (Ward/Sub county/ county wide) | Description of activities | Green Economy consideration | Estimated cost (Ksh.) | Source of funds | Time frame | Performance indicators | Targets | status | Implementing Agency |
| Agricultural inputs and Financing | Capacity building of stockists county wide | Agro dealers training on quality inputs |  | 0.2M | CGK | 2018-2019 | No. of agro dealers trained | 20 | Ongoing | Agribusiness directorate |
|  | Capacity building on entrepreneurship county wide | Training Value chain actors |  | 0.3M | CGK | 2018-2019 | No. of VCAs trained | 100 | Ongoing | ASDSP |
|  | Linking farmers to financial service providers countywide | Linking farmers to financial service providers |  | 0.1M | CGK | 2018-2019 | No. of farmers linked to financial service providers | 50 | Ongoing | ASDSP |
| Value addition and Agro processing of agricultural produce | Capacity building on value addition county wide | Training of farmers and agriprenuers on value addition |  | 0.25M | CGK | 2018-2019 | No. of agriprenuers and farmers trained | 60 | Ongoing | Agribusiness directorate |
|  | Incubation centres at Waruhiu ATC | Setting up incubation centres |  | 5M | CGK | 2018-2020 | No. of incubation centre set up | 1 | New | Agribusiness directorate |
| Value Chain Development | Coffee stakeholders and technical working groups countywide | Formation of Coffee stakeholders and technical working |  | 0.4M | CGK | 2018-2019 | Number of Coffee stakeholders and technical working groups formed | 7 | New | Agribusiness directorate |
|  | Clonal gardens in Githunguri | Establishment of clonal gardens |  | 1M | CGK | 2018-2019 | Number of clonal gardens established | 1 | New | Agribusiness directorate |
|  | Coffee inspectors | Gazettement of coffee inspectors |  | 0.03M | CGK | 2018-2019 | Number of inspector gazetted | 1 | Ongoing | Agribusiness directorate |
|  | Training of licensing of officers in Gatundu South and Gatundu North | Training of licensing officers |  | 0.025M | CGK | 2018-2019 | Number of licensing officers trained | 6 | Ongoing | Agribusiness directorate |
|  | Training of farmers on coffee production management in Kiambaa, Githunguri, Gatundu North , Gatundu South and Kabete | Training of farmers on coffee production management |  | 0.5M | CGK | 2018-2019 | Number of farmers trained on coffee production management | 150 | Ongoing | Agribusiness directorate |
|  | Training of staffs on production management and value addition countywide | Training of staffs on production management and value addition |  | 0.24M | CGK | 2018-2019 | Number of staffs trained on production management and value addition | 20 | Ongoing | Agribusiness directorate |
| Agribusiness Market Development | Marketing groups countywide | Form and strengthen marketing groups |  | 1.25 M | CGK | 2018-2019 | Number of groups formed and strengthened | 10 | New | Agribusiness directorate |
|  | Capacity building on food safety standards countywide | Training of farmer groups on food safety standards |  | 0.3M | CGK | 2018-2019 | Number of farmer groups certified | 2 | Ongoing | Agribusiness directorate |
| Total |  |  |  | 9.595M |  |  |  |  |  |  |

| Programme Name: Crop Development and Management |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Sub Programme | Project name Location (Ward/Sub county/ county wide) | Description of activities | Green Economy consideration | Estimated cost (Ksh.) | Source of funds | Time frame | Performance indicators | Targets | status | Implementing Agency |
| Land and Crop Management and Productivity enhancement | Purchase of Conservation Agriculture equipment and farmer trainings All the wards | Purchase of Conservation Agriculture equipment and farmer trainings |  | 2.02M | CGK | 2018-2019 | No. of Kits purchased No of farmers trained | 120 2,400 farmers | New | Agriculture |
|  | Purchase of certified seed seedlings and pesticides All Wards | Purchase of certified seed seedlings and pesticides |  | 27M | CGK | 2018-2019 | No. of beneficiaries | 13,000 Beneficiaries | Ongoing | Agriculture |
|  | Purchase of Extension services motor cycles All Sub Counties | Purchase of Extension services motor cycles |  | 5M | CGK | 2018-2019 | No. of motorbikes purchased | 20 | New | Agriculture |
|  | Equipping of plant clinics and training plant doctors | Purchase of plant clinic equipments and training plant doctors |  | 1.5M | CGK | 2018-2019 | No. of plant clinics equipped No. of plant doctors trained | 7 14 | New | Agriculture |
|  | Water harvesting structures and drip irrigation demonstrations in all sub counties | Purchase of water pan liners and drip kits |  | 5.5M | CGK | 2018-2019 | No of water pan liners purchased No of drip kits purchased | 40 | New | Agriculture |
| Upgrading of Waruhiu Agricultural Training Centre( ATC) | Development of master plan | Developing master plan |  | 0.5M | CGK | 2018-2019 | No of master plans developed | 1 | New | Agriculture |
|  | Rehabilitation of dairy and biogas units | Rehabilitation of dairy and biogas units |  | 1.5M | CGK | 2018-2019 | No of dairy units rehabilitated No of biogas units rehabilitated | 1 1 | New | Agriculture |
|  | Farmers training | Training farmers on new technologies in agriculture |  | 0.4M | CGK | 2018-2019 | No of farmers trained | 5000 | Ongoing | Agriculture |
|  | Coffee rehabilitation | Coffee rehabilitation works |  | 0.6M | CGK | 2018-2019 | Yield per tree per year | 5 | Ongoing | Agriculture |
|  | Rehabilitation of staff houses | Rehabilitation of staff houses |  | 0.6M | CGK | 2018-2019 | No of staff houses rehabilitated | 5 | New | Agriculture |
| Revitalization of Agricultural Mechanization Services (AMS) | Rehabilitation of AMS structures | Rehabilitation of AMS structures |  | 4M | CGK | 2018-2019 | No. of structures rehabilitated | 2 | New | Agriculture |
|  | Machinery rehabilitation | Rehabilitation of Machinery |  | 3.5M | CGK | 2018-2019 | No. of Machinery Rehabilitated | 1 | New | Agriculture |
| Total |  |  |  | 52.12M |  |  |  |  |  |  |

Cross-Sectoral Implementation Considerations

| Programme Name | Sector | Cross-sector Impact |  | Measures to Harness or Mitigate the Impact |
| --- | --- | --- | --- | --- |
|  |  | Synergies | Adverse impact |  |
| Crop Development and Land Management | Land, Housing & Physical Planning Water and Environment | Secure agricultural land through development control Provide water for irrigation | Crop damage by animals Misuse of agrochemicals River pollution | -ensure IEAs are done -Contractual farming -Facilitate Proper disposal of expired chemicals and containers. - Compliance with NEMA standards on waste disposal |
| Agribusiness and Market information | Trade, Tourism, Cooperatives and Enterprise development Education, Youth, Sports, Gender and Social Development | Registration and Governance of producer groups Markets infrastructure for agricultural produce Income generation through agribusiness activities | Duplication of duties Diminishing land sizes for farming activities | More stakeholder involvement during design of programmes Training on agribusiness and value addition Land zoning |

### 3.2.7 Water, Environment, Energy and Natural Resources

The sector comprises of:

- Water,

- Energy,

- Environment and

- Natural resources directorate:

Vision

To be the leading County in the environmental management and provision of water and sanitation services in Kenya

Mission

To provide a healthy and conducive environment for Kiambu County residents through provision of safe and adequate water, clean towns and improved forest cover.

Strategic Goals

The Sector Goals will be;

- To realize universal access to adequate, affordable, safe water and sanitation services in the County

- To ensure availability of water for irrigation and other agricultural purposes

- To   restore   catchment   areas   and   water   sources   through   Integrated   Water   Resource Management

- To protect, conserve and sustainably manage the environment and natural resources

- To establish and maintain an effective and efficient institutional framework to mainstream climate  change  responses  across  relevant  sectors  and  into  integrated  planning, budgeting,  decision-making  and  implementation,  at  both  the  national  and  county levels.

- To develop alternative cheaper renewable energy for utilization in County Operations and surplus netted to the national grid for revenue generation.

General Information and Key Statistics for the Sector/ Sub-Sector

Water resources

The county has sixteen permanent rivers. The major rivers in the county are; Ndarugũ, Thiririka, Ruiru, Kamiti and Kiu. There are five major wetlands are; Kikuyu, Lari, Theta, Kiganjo and Gacii wetlands. The eastern part of the county is well endowed with surface water while the western part rely on underground water sources mainly boreholes.

Ground Water

Kiambu County is in a sub catchment that has two main aquifers; the Nairobi Suite and Basement Athi Suite. Most of the ground water exploitation is from the Nairobi Suite which is predominantly volcanic.

Water supply schemes

Kiambu County has a total of eight main licensed water management institutions although the county is in the process of emerging to one county water service and sanitation company.

Sanitation

Kiambu County is considered as 60% urban with numerous peri-urban centres mushrooming rapidly due to land use changes. There are twelve main urban centres within the county out which five, namely, Thika, Kiambu, Limuru, Ruiru and Juja urban centres have convectional sewer treatment system.

Garbage collection and disposal around the urban centres within the county of Kiambu is at 75%. The average number of residents in a household is 5persons/household, with an average daily waste discharge of 0.53 to 0.65kg/person/day (JICA, 2010).  Seventy two (72) private firms and 26 registered youth group compliment Kiambu county government in waste collection.

An engineered semi aerobic landfill (Fukuoka method) has been constructed at Kangoki in Thika Sub County, the first of its kind in Kenya and Africa which will handle solid waste from sub-counties after commissioning. The new technology will be accompanied by a modern waste segregation unit and composting facility. A pylorisis plant for recycling plastic waste is in place at Thika Sub County.

Public sanitation facilities in Kiambu county are spread in the various sub counties as follows: one in Juja sub county, two in Gatundu South sub county, two in Lari sub county, three in Ruiru sub county, four in Gatundu North sub county, three in Githunguri sub county, five in Kiambu sub county, three in Kiambaa sub county, four in Limuru sub county, six in Kikuyu sub county, five in Kabete sub county and twenty one in Thika sub county.

Development Needs, Priorities and Strategies

| Development Need | Priority | Strategy |
| --- | --- | --- |
| Institutionalize Legal and regulatory framework | - Realign the existing policies and laws with the 2010 constitution | - Develop and review water, environment, energy and Natural resources policies to conform with the relevant Acts |
| Reversing climate change variability and vulnerability | - Kiambu county has shown commitment to protect the climate system for the benefit of the present and future generations by supporting the United Nations Framework Convention on Climate Change (UNFCCC) process, ratifying the Kyoto Protocol in 2005, and contributing to continental and regional climate change initiatives | - Institutionalize legislative arrangements that governs climate change actions and establish the county environment committee Emca.No.8 of 1999 REVISED 2016 ( 29) - Facilitate Public participation awareness, access to information, ownership and oversight of county’s climate change response efforts and Action Plans. - County government building partnerships with various stakeholders from the public, government, non-governmental organizations, civil society and private sector, as well as vulnerable communities and populations including women and youth, to achieve effective implementation of this goal - Realignment of County’s development model to one that is climate resilient, based on lower GHG emissions, and takes full advantage of the green economy. - County accessing international financing for ambitious climate resilient and low emission development programmes. - Ensure that all sources of finances are mobilized – international, domestic, public and private – including through Public-Private Partnerships (PPPs) - Afforestation and reforestations campaign - User pays and polluter pays” principles. |
| Develop cheaper alternative energy be utilization in County Operations and netted surplus connected to the national grid. | - Mapping areas where alternative energy Sources can be harnessed by zoning wind, solar and hydro power generation through raw water as well as forming joint integration with the countries that have zero wastes as much waste is consumed to generate Energy e.g. Sweden | - Development of County Energy Policy - Capacity building of the department - Enhance Bio mass at homestead levels - Tapping of energy gas (methane) from our Landfills - Energy generation from our wastes - ( bench marking with countries already importing wastes eg Sweden) - Identify areas to invest in wind, solar and small scale hydro power Energy eg deiya has a good corridor for the wind, lower part of county is suitable for solar investment and Kiambu fourteen falls is potential for the hydropower Energy. This will be through public private partnership (PPPs) - Legislation for protecting identified alternative energy sources - Carry out Research on alternative energy sources. |
| Increase access to adequate safe clean affordable water | - To realize universal access to adequate, affordable, safe water - To improve planning, coordination and management of the water sector - Regulate water vendors to ensure quality and consumer protection | - Expand / increase water supply though construction of Dams, Treatments Plants, drilling of boreholes and Rain water harvesting - Investing in additional water distribution infrastructures. - Rehabilitation and augmentation of water system - To promote investment in community water projects to reach more rural communities - Develop and implement guidelines for utilization of funds by community water projects - Promote partnership with Private Sector and Non State Actors - Rehabilitation of stalled water project and improving on governance - Increase investment in development and maintenance of water harvesting structures - Provision of water tanks especially to special groups and institutions - Develop effective human resources for the water sector conducting random checks on water vendors to ensure safety |
| Reduce the level of uncounted for water from the present 45 % to at least 25% | - Work with various agencies and local communities to undertake regular surveillance of county’s water utilities | - Installing meters - To develop a robust monitoring and evaluation mechanism of non-revenue water - Rehabilitation of the dilapidated water distribution networks - Zonal metering |
| Water resources conservation protection | - To restore catchment areas and water sources through Integrated Water management - To ensure availability of water for irrigation and other agricultural purposes - Maintain an updated data base on water resources | - Demarcation and enforcement of riparian areas zones. According to water law, the riparian zone extends 30 metres from the highest water mark of the river flow. - Gazettement of wetlands as public land to prevent encroachment - Rehabilitation of the catchment areas - Work with various agencies and local communities to undertake regular surveillance of county’s water resource - Promote adoption of appropriate technologies in protection and conservation of catchment areas - Work with other stakeholders to undertake water resources management - Strengthen and support Water Users Associations (WRUAs) in catchment conservation and protection - Enhance and promote private sector participation in protection, conservation and utilization of water resources |
| Improve sewerage system Increase the number of the public toilets | - To realize universal access to improved sanitation, sewerage, and drainage system - To increase access and utilization of sewerage system | - Increase/ expand sewerage system - Create public awareness on the importance of connecting to sewer system - Promote appropriate onsite community sanitation system - Enforce the WASH regulation of having toilets in all public facilities such as super markets. Banks etc. - Scaling up of latrine coverage and extension of sewer line - Intensify public health inspections for toilets coverage and hygiene facilities - Support the implementation of Community Led Total Sanitation (CLTS) initiatives |
| Reduce environmental degradation by 50 percent by 2022. | - Increase the current forest cover from16.5% to the targeted 20% Increase - Reclaiming quarry sites - Intensify soil conservation methods | - Promote agroforestry - Mapping - Enforcement - Creating awareness - Afforestation - Creation and adherence of Forest Management plans - Encourage development of community owned tree nurseries; - Re-location of humans on forest and water tower lands - Rehabilitation of quarries - Introduce social cost to quarry owners; - Construction of gabions; - Carry out EIA/EA |
| Improve garbage collection systems and introduce segregation of waste on site Increase waste collection equipment and trucks | - Environment management and protection(solid waste management) - Cleaner environment is a constitutional right) | - Improve garbage collection system.. - Promote recycling of solid waste. - Implement solid waste management plan - Develop and enforce environmental standards - Integrate environmental issues in county development planning - Procure adequate waste collection equipment and trucks. - Construct public toilets. - Recruit more technical staffs - Conducting an environmental sanitation campaign. - Leveraging on technology solid waste management. - Enforcement and policing of environmental regulations - Increase public education and awareness on environment - To promote investments in research and development of green energy solutions |

Stakeholder Analysis

| Stakeholder category | Stakeholder expectation | Sector expectation |
| --- | --- | --- |
| Water Resource Management Authority (WRMA) | Collaboration with the line department | - Management and regulation e.g. to avoid over abstraction upstream - Issuance of permits - Formation and capacity building of WRUAs |
| Water Resources User Association (WRUA) | Collaboration with the line department | - Protection and conservation of catchment areas - Promote controlled and legal water use - Reduce and solve water use conflicts |
| Water services regulatory board | Collaboration with the line department | - National Standards on asset development and water services and economic regulation |
| Water User Associations | Collaboration with the line department Training of Water Resources Users Associations | - Sensitization and awareness to water users Provision of water services in rural areas - Management and maintenance of water systems in rural area |
| Water Service Providers | Collaboration with the line department | - Provision & maintenance of water &sanitation services in urban centres - Building onsite sanitation facilities in low income urban areas through WSTF - Data collection and management of water supply, sewerage and sanitation services information system |
| Civil Society Organizations e.g. KENVO, | Collaboration with the line department | - Water services provision - Community empowerment - Support water supply and sanitation in rural areas |
| Athi Water Services Board | Collaboration with the line department in implementation | - Bulk water supply - Asset development |
| Community Owned Water Operators (COWOs) | Collaboration with the line department | - Community water services provision - Training of Water Resources Users - Associations |
| Line departments Department of Urban Planning and Housing ,roads,Finance National Land Commission Ministry of Lands County Land department department, Kenya Meteorological Department | Collaboration with the line department | - Construction of storm water infrastructure - Approval of building plans - Storm water management - Water Policy development - Development of Water legislations and oversight - Prepares county water investment and financing plan for incorporation in CIDP - Coordination & planning; setting priorities; - CIDP; resource mobilization; (co)financing; - Regulations; capacity building of partners; - Supervision; M&E; internal audits - Coordinates the activities of CSOs in rural areas - Management of information system areas - Financing is WSPs and COWOs through /data for urban and rural Reversion of grabbed catchment areas and riparian land - Land acquisition for creation of dams - Way leaves for transmission lines and sewer trunks - Early warning |
|  | Local communities | - Payment for water services |
| CBO’s / Donors / Private individuals / Private sector | Collaboration in the implementation of the project | - Resource mobilization; capacity building at - grassroots level; direct implementation; support |
| County Assembly | Information: context, proposed projects and budgets | - Policy approval and amendment - Budget approval and amendment - Oversight role of CG - Constituents representation |
| National Government | - Policy Making - Resources - Capacity building - Infrastructure development - Security provision - Promotion and regulation of International trade - Oversight of CG - Representation of the CG - Domestication of international obligations – treaties - Promote national cohesion - Promote inter-county trade - Arbitration of inter-county disputes | - Collaboration and goodwill from CG - Information and feedback on the sector - Revenue |

Capital and Non Capital Projects

Table 53: Water, Environment, Energy & Natural Resources Capital projects for the FY 2018/2019

| Programme Name : Administration planning and support services Objective: To enhance and improve service delivery. Outcome: Improved service delivery. |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Sub Programme | Project name Location (Ward/Sub county/ county wide) | Description of activities | Green Economy consideration | Estimated cost (Ksh.) | Source of funds | Time frame | Performance indicators | Targets | status | Implementing Agency |
| General administration | County wide | Purchase of new vehicles |  | 15M | CGK | 2018- 2019 | Number of vehicles procured | 2 | new | CGK |
|  |  | Servicing and repair of vehicles |  | 20M | CGK | 2018- 2019 | Number of vehicles procured | 2 | ongoing | CGK |
| Personnel and Support services | County wide | Staff Training. |  | 0.5M | CGK | 2018-2019 | Number of staff sponsored for promotional and refresher courses | 10 | Ongoing | CGK |
|  | county wide | staffs Recruitment Registering with staff professional bodies |  | 3.2M | CGK | 2018-2019 | No of staff recruited No of staff registered | 3 6 | 0 | CGK |
|  |  |  |  | 77.5M | CGK | 2018-2019 | Amount of money disbursed for operations and maintenance | 6 | 0 | CGK |
|  |  | Payment of wages and salaries. |  | 160M | CGK | 2018-2019 | Amount allocated to personal Emoluments | 160M | Ongoing |  |
| Total |  |  |  | 276.2M |  |  |  |  |  |  |

| Programme Name: Environment Management and protection |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Objective: To enhance clean environment |  |  |  |  |  |  |  |  |  |  |
| Outcome :reduced Environmental pollution and degradation |  |  |  |  |  |  |  |  |  |  |
| Sub Programme | Project name Location (Ward/Sub county/ county wide) | Description of activities | Green Economy consideration | Estimated cost (Ksh.) | Source of funds | Time frame | Performance indicators | Targets | status | Implementing Agency |
| Environmental management policy | County wide | Establishment of county environment committee |  | 20M | CGK | 2018-2019 | No of environmental committee in place | 1 | 0ngoing | WEENER |
|  | County wide | GIS systems in place |  | 5M |  |  | No of GIS systems in place | 1 | 0ngoing | WEENER |
|  | County wide | Environmental policies in place |  | 6M | CGK | 2018-2019 | No. of policies developed and institutionalized | 3 | 0ngoing | WEENER |
| Solid waste management | County wide | Construction of waste management hub |  | 80M | CGK | 2018-2019 | No.of waste management hub constructed | 1 | 0ngoing | WEENER |
|  | County wide | procure skip loaders |  | 12M | CGK | 2018-2019 | No.of a skip loaders procured | 1 | 0ngoing | WEENER |
|  | County wide | procure skips |  | 5M | CGK | 2018-2019 | No.of skips procured | 20 | 0ngoing | WEENER |
|  | County wide | decommission and rehabilate open dumpsites |  | 100M | CGK | 2018-2019 | No.of decommissioned and rehabilated open dumpsites | 1 | 0ngoing | WEENER |
|  | County wide | Research on solid waste Management |  | 5M | CGK | 2018-2019 | Research on solid waste Management | 4 | 0ngoing | WEENER |
|  | County wide | Construction/rehabilitation of toilets |  | 54M | CGK | 2018-2019 | No of toilets Constructed/rehabilitated | 24 | 0ngoing | WEENER |
| Environmental Education and Awareness | County wide | Hold environmental awareness campaigns |  | 5M | CGK | 2018-2019 | No of awareness campaigns held | 12 | 0ngoing | WEENER |
|  |  |  |  | 3M | CGK | 2018-2019 | No environmental Trainings held | 3 | 0ngoing | WEENER |
| Totals |  |  |  | 295M |  |  |  |  |  |  |

| Programme Name: Water resources management and sanitation |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Objective: To provide adequate, affordable, safe clean water and sanitation services |  |  |  |  |  |  |  |  |  |  |
| Outcome: Increased access to clean and safe water |  |  |  |  |  |  |  |  |  |  |
| Sub Programme | Project name Location (Ward/Sub county/ county wide) | Description of activities | Green Economy consideration | Estimated cost (Ksh.) | Source of funds | Time frame | Performance indicators | Targets | status | Implementing Agency |
| Water policy development and management | County wide | No of policies drafted and developed |  | 1M | CGK | 2018-2019 | No of policies drafted and developed | 1 | 0ngoing | WEENER |
| water storage and flood control | County wide | Pans construction |  | 20M | CGK | 2018-2019 | No of Pans constructed | 5 | 0ngoing | WEENER |
|  | County wide | Procurement of plastic tanks |  | 5.65M | CGK | 2018-2019 | No of plastic tanks Procured and distributed | 50 | 0ngoing | WEENER |
|  | County wide | Construction of Elevated tanks |  | 36M | CGK | 2018-2019 | No of Elevated tanks Constructed | 9 | 0ngoing | WEENER |
|  | County wide | Drilling and equipping boreholes |  | 48M | CGK | 2018-2019 | No of boreholes Drilled and equipped | 12 | 0ngoing | WEENER |
|  | County wide | Procurement of assorted extension pipes, pipe laying |  | 80M | CGK | 2018-2019 | Km laid assorted extension pipes | 50 | 0ngoing | WEENER |
|  | County wide | Constructions of water kiosk |  | 4M | CGK | 2018-2019 | No of water kiosks | 16 | 0ngoing | WEENER |
|  | County wide | Installation signage |  | 0.3M | CGK | 2018-2019 | No of signage erected | 100 | 0ngoing | WEENER |
| Total |  |  |  | 194.95M |  |  |  |  |  |  |

| Programme Name natural resources conservation and management |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Objective: To increase forest cover and sustainable management of natural resources |  |  |  |  |  |  |  |  |  |  |
| Outcome: improved natural resources conservation and management |  |  |  |  |  |  |  |  |  |  |
| Sub programme | Project name Location (Ward/Sub county/ county wide) | Description of activities | Green Economy consideration | Estimated cost (Ksh.) | Source of funds | Time frame | Performance indicators | Targets | status | Implementing Agency |
| natural resources conservation and management | County wide | Tree planting in schools |  | 20M | CGK | 2018-2019 | No of trees planted | 500,000 | 0ngoing | WEENER |
|  |  | Planting of trees in degraded areas of county forest and water catchment areas |  | 20M | CGK | 2018-2019 | No of trees planted in county forests/ water catchment | 500,000 | 0ngoing | WEENER |
|  |  | Giving farmers trees seedlings (Farm forestry) |  | 20M | CGK | 2018-2019 | No of seedlings grown in farms | 500,000 | 0ngoing | WEENER |
|  |  | Planting of trees in highways and county open spaces |  | 8M | CGK | 2018-2019 | No of trees planted in open spaces and road reserves (beautification) | 200,000 | 0ngoing | WEENER |
|  | County wide | Acquiring land to establish county forest |  | 50M | CGK | 2018-2019 | Acreage acquired for establishment of county forest and trees planted | 5 | 0ngoing | WEENER |
|  | County wide | Mapping by use of GIS all sector activities e.g. tree planting, quarrying etc |  | 5M | CGK | 2018-2019 | No of activities mapped | 5 | 0ngoing | WEENER |
|  | County wide | Planting of bamboo trees |  | 30M | CGK | 2018-2019 | No of giant bamboo planted | 100000 | 0ngoing | WEENER |
| Securing habitats for wildlife | County wide | Securing habitats |  | 3M | CGK | 2018-2019 | No of Secured habitats | 4 | 0ngoing | WEENER |
| County policy coordination and support | County wide | Development of Natural resource conservation and management policy |  | 4M | CGK | 2018-2019 | No of policies Developed | 2 | 0ngoing | WEENER |
| Total |  |  |  | 160M |  |  |  |  |  |  |

| Programme Name: Renewable Energy and Climate Change |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Objective :To enhanced use of renewable energy and initiate climate change initiatives |  |  |  |  |  |  |  |  |  |  |
| Outcome :improved climate change initiatives and enhanced use of renewable energy |  |  |  |  |  |  |  |  |  |  |
| Sub Programme | Project name Location (Ward/Sub county/ county wide) | Description of activities | Green Economy consideration | Estimated cost (Ksh.) | Source of funds | Time frame | Performance indicators | Target | Status | Implementing Agency |
| Alternative Energy & Renewable Energy Initiatives | County wide | -Creation of a renewable energy and climate change Centre -Demonstration of production & use of different forms of renewable energy | Creation of employment | 2 M | CGK | 2018-2019 | No of renewable energy and climate change centers established | 1 | New | WEENR |
| Energy Conservation | County wide | -Retro fitting on electrical systems |  | 0.4 M | CGK | 2018-2019 | -No of retro fitting done % reduction on bills | 12 | New | WEENR |
| Conversion of waste into energy (Briquettes and Biogas) | Kiambu & Kikuyu & Sub Counties | -Setting up of briquettes making sites -Procurement of briquettes making machine -Production and sale of briquettes | -Creation of employment/ Income generation -Reduction of environmental impact -Conservation of environment | 2 M | CGK | 2018-2019 | -No of briquettes making machines procured - No of Kgs of briquettes made & sold | 2 | New | WEENR |
|  | County wide | -Promotion of use of biogas in institutions and households -Construction of biogas plants in five major slaughter houses within the county -Procurement and installation of biogas systems -Production and sale of biogas -Production, use and sale of biogas -Demonstration of operation and maintenance of biogas system | -Improved environmental condition | 3.3 M | CGK | 2018-2019 | -No. of biogas plants constructed & in use -No.of facilities using biogas -Reduced discharge of waste from the slaughter houses | 5 | New | WEENR |
| Energy Efficiency | County wide | -Procurement & distribution of energy saving cook stoves, light emitting diode (LED), solar panels and bulbs at subsidized prices | -Savings on money -Employment opportunities | 2.5 M | CGK | 2018-2019 | -No. of cook stoves, bulbs and solar panels procured and distributed -% reduction on electricity bills | 32,000 | New | WEENR |
| Community awareness campaigns use of renewable energy | County wide | -Sensitizing the community on use of renewable energy |  | 0.3 M | CGK | 2018-1019 | -No. of awareness campaigns held | 60 | New | WEENR |
| Mainstreaming of renewable energy and climate change initiatives | County wide | -Conduct an environmental audit in all CGK premises -Report writing | -Reduced carbon footprint/ reduced environmental impact | 0.2M | CGK | 2018-1019 | -No. of premises audited No of Audit reports | 15 premises | New | WEENR |
|  |  | -Enhancement of water storage capacity through roof catchment and storm water harvesting -Strom water management Install rain water harvesting tanks -Construct underground storage tanks -Establishment of carwash facilities | -Environmental sustainability - | 1 M | CGK | 2018-1019 | No. of climate change and renewable energy initiatives done | 1 sub counties | New | WEENR |
|  | County wide | -procurement and Installation of solar panels on county government premises | Income saving | 1.5 M | CGK | 2018-2019 | -No of procured and installed functional solar panels | 2 premises | New | WEENR |
|  | Nachu and Ndeiya Ward | Procurement and Installation of solar powered street lights (pilot project) |  | 2 M | CGK | 2018-2019 | No. procured of solar powered street lights and installed % electricity bill | 2 | New | WEENR |
|  | -County wide | - procurement and installation of incandescent lights in offices to LED lights |  | 0.5 M | CGK | 2018-2019 | No of incandescent lights procured and installed in offices | 12 premises | New | WEENR |
|  | County wide | -Drafting & implementation of sustainability policy -Develop renewable energy master plan | -Environmental sustainability - Financial saving | 1 M | CGK | 2018-2019 | Copies of draft policy in place No of renewable energy master plan | 1 1 | New | WEENR |
| Climate Change Initiatives | County wide | Undertake a climate change vulnerability assessment exercise |  | 0.5 M | CGK | 2018-2019 | Number of vulnerability hotspots identified | 12 | New | WEENR |
|  | County wide | Sensitization of communities on climate change mitigation and adaptation interventions | -Improved resilience | 1 M | CGK | 2018-2019 | -Number of awareness campaigns held -Modes of publicity used | 12 | New | WEENR |
| Eco- schools Projects– Greening of schools | County wide | -Mapping and identification of schools in the county to launch the eco schools programme -Undertake a needs assessment in 5 schools in each sub county |  | 0.3 M | CGK | 2018-2019 | -No of schools mapped No Needs assessment report done | 60 | New | WEENR |
|  |  | Educate and train schools on environmental issues ( waste management , water conservation , tree planting renewable energy and climate change ) -Provision of litter and dust bins in 60 schools | -Environmental sustainability | 0.5 M | CGK | 2018- 2019 | No. of bins procured and installed Number of bins in schools Behavioral change ( waste reduction and separation) -Clean school environment | 60 | New | WEENR |
| Enhancement of Water storage capacity in schools through water harvesting |  | No of procured water tanks to schools | Financial saving | 1 M | CGK | 2018-2019 | -Number of water tanks supplied %Reduction of water bills | 12 schools | New | WEENR |
| Total |  |  |  | 20M |  |  |  |  |  |  |

Cross-sectoral implementation considerations

| Programme Name | Sector | Cross-sector Impact |  | Measures to Harness or Mitigate the Impact |
| --- | --- | --- | --- | --- |
|  |  | Synergies | Adverse impact |  |
| Water storage and flood control | Lands, Health Agriculture | - Provision of land for construction of dams and water pans - Provision of mosquito nets and malaria control - Stabilizing the loose soil formation by compaction, building gabions | - Displacement of residents and land grabbing - Malaria outbreak, pollution, - Accidental drowning of residents and their livestock. Attraction of wildlife to the areas, Loss of biodiversity | - Compensation of the displaced and come up with laws to control grabbing , - Sleeping under mosquito nets ,planting vegetation cover - Fencing of dams and pans to avoid accidents ,stabilizing the loose soil formation by compaction, building gabions |
| Water supply infrastructures | Roads | - Installing appropriate temporary bridges over the pipeline trenches. | - Blocking roads | - Erect warning signs of ongoing works which should be visible even at night. - Expedite construction works so as to reduce the times where roads are blocked. - Access of residents should be facilitated by installing appropriate temporary bridges over the pipeline trenches. - Get maps of the underground infrastructure from the relevant institutions. - Sensitize workers carrying out excavations so that they exercise caution to minimize chances of underground infrastructure damage. - Work closely with the responsible institutions such that incase of damage, the services are restored within the shortest time. - Reroute sensitive infrastructure where possible. |
| Natural resources conservation and management(climate change) | Road department | - Construction road network | - Decrease in forest coverage, rapid deterioration of land cover leading to changing rainfall resulting droughts and flooding, loss of biodiversity, threats to animal and plant species, change in vegetation composition and structure, and depletion of water quality and quantity through the destruction of catchments and underground aquifers. creates a window for invasive species, new pests and diseases | - Enactment of overarching climate change legislation to provide the framework for coordinated implementation of climate change responses and action plans |

### 3.2.8 Health Services

Vision

An efficient, effective and high quality health care system that is accessible, equitable and affordable for every person in Kiambu County.

Mission

To provide health services that is equitable, accessible and accountable to the people of Kiambu County through participatory leadership

Sector Goal

Attaining the highest possible health standards in a manner responsive to the people’s needs.

Key statistics for the sector

The sector has a total of 108 facilities, 70 dispensaries, 24 Health centres, 10 Level 4 hospitals, 3 Level 5 hospitals and 1 Beyond zero mobile clinic. There are 120 Community units. The sector boasts of a total of 2653 Health workers. It also has 651 casual workers, both skilled and unskilled.

Development Needs, Priorities and Strategies

| Needs | Priorities | Strategy |
| --- | --- | --- |
| Reduction of maternal mortality | - Basic Antenatal package - Skilled delivery - Basic Emergency Obstetric Care (BmOC) - Comprehensive Emergency Obstetric Care (CemOC) - Obstetric Complications - Quality of Obstetric Care - Maternal and Perinatal Death Surveillance (MPDSR) | - Capacity building for health workers and community - Health work force - Promote maternal high impact interventions - Health commodity security - Health promotion and hygiene - Infection prevention and control - Linkages and referrals (ambulance central command) - Demand creation and advocacy - Respectful maternity care - Strengthen maternal perinatal death surveillance and response - Increase staffing levels - Construction of more maternity units/Special units - (new born units, Critical Care Unit (CCU), Renal Units) - Support supervision |
| End preventable deaths of new-borns and children under 5 years of age, and reduce neonatal and under-5 mortality | - Emergency Triage and Treatment (ETaT) - Maternal and Perinatal Death Surveillance (MPDSR) - Childhood immunization | - Infection prevention and Control - Commodity security-supply chain management - Health education on hygiene - Capacity building for Health workers and community workforce - Linkages and referrals - Improve infrastructure for the new-borns/special units/ - equipment - Increase Immunization coverage - Improve the nutrition of mothers - Improve the nutrition status of neonates and children - Support supervision - Environmental management - Promote use of Long Lasting Insecticides Treated Nets for under ones and children - Promotion of WASH/CLTS - MPDSR - Improve staffing levels - Scale up IMCI Training at the facility and community. - Partnership and stakeholders engagement |
| End the epidemics of AIDS, tuberculosis, malaria and neglected tropical diseases and combat hepatitis, water-borne diseases and other communicable diseases | - Tackle New HIV Infections - Reduce TB infections - Prevent out breaks of water borne diseases and other communicable diseases - Vector -borne, zoonotic and water-borne diseases | - Ensure allocation of significant HIV/AIDs fund in the county health budget - Reduce of HIV stigma in the county - Strengthen HIV testing and services in the county -All facilities to provide HTS in all departments - Partner with HIV implementing partners-Coordination and planning - Advocacy to institutions to review HIV unit curriculums on HIV -HIV not taught seen as a social problem but a common unit - Multisectoral approach both internally and externally - Strengthen community health strategy in the county - Disseminate and Implement the existing HIV policies strategies and guidelines - Conduct regular client exit interview to monitor client satisfaction |
| Reduce premature mortality from non- communicable diseases and promote mental health and well-being | - Diagnosis and treatment of Elevated blood sugar (Diabetes) - Diagnosis and treatment of high blood pressure (Hypertension) - Screening and early intervention for breast, cervical and prostatic cancers - Non Communicable Diseases surveillance - Childhood and adolescent mental health problems - Access to mental health services at primary health care level - Skilled human resource for mental health | - Develop and implement the Non Communicable Diseases policies and guidelines - in the county - STEPwise Approach to Surveillance (STEPS) - Disseminate and implement mental health policy and - Clinical guidelines - Reduce stigma associated with mental illness - Strengthen and support the community health strategy in the county |
| Prevention and treatment of substance abuse, including narcotic drug abuse and harmful use of alcohol | - Stop harmful use of alcohol - Elimination of second generation alcoholic beverages - Pharmacological, psychosocial and rehabilitation and aftercare services - Diagnosis and treatment of concomitant and/or underlying mental health problems | - Construction of specialised one-stop centre for treatment and rehabilitation for alcohol and substance abuse - Resources mobilization for the County Alcohol Substance Treatment and Rehabilitation Programme (ASATREP) - Public-Private Partnerships - Community based interventions - Access of resources from Directorate of Alcoholic Beverages Control for Treatment and Rehabilitation |
| Reduction of deaths and injuries from road traffic accidents | - Emergency Medical Services - Treatment and Rehabilitation - Capacity building - Public private partnerships - Legislation and policy briefs - Communication and awareness | - Centrally co-ordinated ambulance system and EMS nerve co-ordination centre - Set up Emergency Medical Teams in 4 identified key health facilities that are part of EMS - Construct and/or refurbish and/or equip accident and emergency units in 4 identified health facilities - Training of paramedics and ambulance staff on first response in emergency settings - Community outreaches - Training and certification of health-care workers - Build, renovate and/or upgrade and equip accidents and emergencies - Community and facility based occupational and physical therapy - Media and IEC materials - Policy brief to establish and fund emergency medical services - Establish collaboration with private and other partners in Emergency Medical Services, communication and awareness |
| Ensure universal access to sexual and reproductive health-care services | - Reach Adolescents and Youths with sexual and reproductive health-care services - Family planning services - Communication and awareness - Confront stigma and discrimination associated with sexual health and sex education - Early diagnosis, effective treatment and management of specific reproductive health issues including menstrual disorders, infertility, abortion and post-abortal care - Prevention, early diagnosis and treatment of sexually transmissible infections | - Procurement of Family planning and other commodities for sexual and reproductive health-care - Capacity building for health-care providers on FP, Youth Friendly services, diagnosis and treatment of sexually transmissible diseases and reproductive health problems - Build, renovate and/or upgrade of Youth Friendly Centres - Provide Client Centred Family Planning services |
| Achieve universal health coverage, including financial risk protection, access to quality essential health-care services and access to safe, effective, quality and affordable essential medicines and vaccines for all | - Alternative sources of financial resources for health - Financial protection for the poor - High quality essential care - Essential medicines - Expanded Programme on Immunization - Health information technology and systems | - Mandatory and mass recruitment to National Hospital Insurance Fund (NHIF) - Free NHIF registration for families living below poverty line - Establish County Quality Health Assurance System - Increase routine immunization coverage |
| Reduce the number of deaths and illnesses from hazardous chemicals and air, water and soil pollution and contamination | - Domestication and implementation of a Occupational Safety Health and Administration Policy (OSHA) - Research on death and illnesses from hazardous chemicals and air, water, soil pollution and contamination and occupational hazards - Public health inspections and/or approvals - Improve waste management - Advocacy and awareness on environmental health issues | - Establish a multi sectoral consultative forum to and/or develop OSHA policy for Kiambu County - Launch and dissemination of Kiambu OSHA policy - Formation of the County and sub-County OSHA management committee - Public sensitization on the OSHA policy requirements - Establish a register for deaths and illnesses from chemicals and air, water, soil pollution and contamination, including unintentional deaths and occupational hazards - Conduct a survey of hazardous chemicals, occupational and environmental hazards in the County of Kiambu and level of compliance with OSHA policies - Water sampling - Soil sampling - Legal enforcement of standards and norms - Increase population awareness on the need for clean fuels and alternatives |
| Increase health financing and the recruitment, development, training and retention of the health workforce | - Capacity building - Increase the number of health workers to recommended ratios - Broaden sources of financial resources for health | - Training needs assessment - Use of temporary labour arrangements to bridge human resource for health gaps - Public private partnerships - Mandatory and mass recruitment to the National Hospital Insurance Fund |
| Strengthen the capacity of the county for early warning, risk reduction and management of county, national and global health risks | - Emergency Medical System (EMS) - Disease Surveillance and Control - County Emergency Rapid Response Team | - Centrally co-ordinated ambulance system and Emergency Medical System nerve co-ordination centre - Set up Emergency Medical Teams in 4 identified key health facilities that are part of Emergency Medical System - Construct and/or refurbish and/or equip accident and emergency units in 4 identified health facilities - Training of paramedics and ambulance staff on first response in emergency settings - Emergency medical response training: - Basic Life Support Skills (BLS) - Paediatric Advanced Life Support (PALS) - Advanced Trauma Life Support (ATLS) - Establish a central isolation and/or quarantine facility to handle outbreaks - Ring fenced budget for emergency medical supplies - Co-ordinated procurement of emergency medical supplies targeting common outbreaks |
| Strengthen Health Research and Innovation | - Carry out research and dissemination of of research findings - Act as a repository of data, statistics and information related to heath of the County residents; - Monitor and evaluate the of the implementation of the Kiambu Health Services ACT | - Establish a mechanism for institution Scientific and Ethical Review through partnering with National Commission for Science, Technology and Innovation (NACOSTI) approved Ethical Review Committee in institutions of higher learning and research in the County of Kiambu - Establish at least one Clinical and Public Health Research Centre for the County of Kiambu as a way of mainlining the culture of Health research - Establish and maintain of a registry of all research activities being undertaken in the County - In line with the Kiambu Health Act 2014, establish a County Repository of Health Information that provides readily available health information to all actors in the health sector for the purpose of restoring, improving and maintaining health among residents of Kiambu County - Annually identify key health research priorities in line with the County and National Health Strategic plans - Initiate and/or manage local and international research collaborations on behalf of the County Health Services - Initiate and/or conduct of specific research activities in collaboration with directorates/departments that will guide County Health Management Team and the County Government in key decision making in the following areas: - Basic and applied clinical research to grow centres of clinical excellence - Population and public health research for programmatic and population based interventions - Operational and implementation research to support health administrative services - Rapid Response to Public Health Emergencies (for example Ebola Virus Disease, Cholera, Measles etc.) through the multidisciplinary team of the County Emergency Rapid Response Team (CERRT) - Continuous surveillance of disease and morbidity patterns to identify key and emerging new areas of concern - Assist in the incubation of innovative ideas that have the potential to change healthcare provision - Assist in the adoption and/or evaluation of Health Information Management Systems to ensure they support both health services provision and monitoring and evaluation needs by providing timely, accurate and data that can be analysed - Build research capacity among County Health workers in order to be able to fully question and answer the health challenges that they encounter daily from and evidence point of view - Provide an advisory role in key decisions that the Department of Health may be involved through representation in key KCHMT committees - Organize and conduct the evaluation of the performance of the community, sub-county and county management teams in implementation of the Kiambu Health Services Act 2014. |

Significant capital and non-capital development

The construction and equipping of two level four hospitals i.e. Birioni level 4 and Githunguri level 4 are the department’s significant capital projects.

The significant non capital projects are; increasing HRH levels where a Locum policy is being formulated, ensuring Universal Health Care where the department aims to ensure affordable services for all through registration into NHIF and accreditation of all public health facilities. The department also aims at ensuring efficient and effective Emergency Medical services through refurbishing of existing ambulances and establishing a responsive EMS unit. Primary health care will also be improved through the community Strategy by increasing the no. of Community units and providing a stipend to the Community Health Volunteers.

Stakeholders Analysis

| Stakeholder Category | Stakeholder Expectation | Sector Expectation |
| --- | --- | --- |
| National government | - Timely reports - Implementation of policies | - Timely disbursement of funds - Policy development, guidance and direction |
| Line departments | Health service technical expertise and guidance e.g. in building approvals | Involvement in project planning and implementation |
| Development Partners | - Timely reports - Appropriation of funds and accountability - Achievement of project/programmes goals and objectives | Financial and technical support |

Capital and Non-Capital Projects

In the planning year, the department wishes to improve access to health services through infrastructure refurbishments, completion of facility sections such as the maternity wing, fencing and construction of patient and staff toilets.

There will be non-capital projects focused on staff motivation and capacity building, improved governance through policy formulation and stakeholder engagement and research activities to ensure that the department keeps at par with the current trends. The department is also keen on ensuring proper monitoring and evaluation, provision of adequate drugs and ensuring lowered levels of morbidity and mortality through activities in Primary health care and curative services.

Table 54: Health Services Capital projects for the 2018/19 FY

| Programme Name: Administration, Planning and Support services |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Sub Programme | Project name Location (Ward/Sub county/ county wide) | Description of activities | Green Economy consideration | Estimated cost (Ksh.) | Source of funds | Time frame | Performance indicators | Targets | status | Implementing Agency |
| Administration Services | Completion of maternity unit, construction of fence and Renovation works of the building in Athi dispensary, Kalimoni ward in Juja sub county. | Renovation works finishing and repairs of the buildings | Increase natural lighting | 10,000,000 | KCG | 2018-2019 | % of works completed | 100% | New | Department of Health Services |
| Administration Services | Refurbishment of the OPD and the laboratory unit in Cianda dispensary, Cianda ward and Kiambaa sub county. | Renovation works finishing and repairs of the buildings | Increase natural lighting | 4,000,000 | KCG | 2018-2019 | % of works completed | 100% | New | Department of Health Services |
| Administration Services | Refurbishment works and construction of waiting bay in Escarpment dispensary, Lari/Kirenga ward, Lari sub county | Renovation works finishing and repairs of the buildings | Increase natural lighting | 6,000,000 | KCG | 2018-2019 | % of works completed | 100% | New | Department of Health Services |
| Administration Services | Refurbishment and Rehabilitation of the OPD, laboratory unit and fence in Gachika health centre, Kiganjo ward, Gatundu south sub county | Renovation works finishing and repairs of the buildings | Increase natural lighting | 6,000,000 | KCG | 2018-2019 | % of works completed | 100% | New | Department of Health Services |
| Administration Services | Refurbishment and construction of a covered walk way in Gichuru dispensary, Sigona ward, Kikuyu sub county | Renovation works finishing and repairs of the buildings | Increase natural lighting | 7,000,000 | KCG | 2018-2019 | % of works completed | 100% | New | Department of Health Services |
| Administration Services | Construction of ablution block and renovation works in Cianda dispensary, Cianda ward , Kiambaa sub county | Construction of toilet block and renovation works | Biogas production | 10,000,000 | KCG | 2018-2019 | % of works completed | 100% | New | Department of Health Services |
| Administration Services | Construction of patient toilet block in Wangige level 4 hospital, Kabete ward, Kabete sub county | Construction of toilet block | Biogas production | 4,000,000 | KCG | 2018-2019 | % of works completed | 100% | New | Department of Health Services |
| Administration Services | Refurbishment and rehabilitation of the OPD and the laboratory unit in Juja farm health centre, Kalimoni ward , Juja sub county | Renovation works finishing and repairs of the buildings | Increase natural lighting | 5,000,000 | KCG | 2018-2019 | % of works completed | 100% | New | Department of Health Services |
| Administration Services | Refurbishment works and construction of a covered walkway in Karia dispensary, Ikinu ward, Githunguri sub county | Renovation works finishing and repairs of the buildings | Increase natural lighting | 4,000,000 | KCG | 2018-2019 | % of works completed | 100% | New | Department of Health Services |
| Administration Services | Extension of the OPD building in Kereita forest dispensary, Kijabe ward, Lari sub county | Renovation works of the OPD building | Increase natural lighting | 3,000,000 | KCG | 2018-2019 | % of works completed | 100% | New | Department of Health Services |
| Administration Services | Rehabilitation and refurbishment works in Makongeni health centre, Kamenu ward, Thika sub county | Renovation works finishing and repairs of the buildings | Increase natural lighting | 4,000,000 | KCG | 2018-2019 | % of works completed | 100% | New | Department of Health Services |
| Administration Services | Rehabilitation and refurbishment of the building in Munyu-ini dispensary, Ndarugo ward, Gatundu south sub county | Renovation works finishing and repairs of the buildings | Increase natural lighting | 4,000,000 | KCG | 2018-2019 | % of works completed | 100% | New | Department of Health Services |
| Administration Services | Rehabilitation and refurbishment of the buildings in Mutate dispensary, Kiamwangi ward, Gatundu south sub county | Renovation works finishing and repairs of the buildings | Increase natural lighting | 3,000,000 | KCG | 2018-2019 | % of works completed | 100% | New | Department of Health Services |
| Administration Services | Refurbishment, construction of covered walk way and waiting bay in Ngecha health centre, Tigoni/Ngecha ward, Limuru sub county | Renovation works finishing and repairs of the buildings and walkway | Increase natural lighting | 6,000,000 | KCG | 2018-2019 | % of works completed | 100% | New | Department of Health Services |
| Administration Services | Rehabilitation and refurbishment of the buildings in Ngoliba health center, Ngoliba ward , Thika sub county | Renovation works finishing and repairs of the buildings | Increase natural lighting | 10,000,000 | KCG | 2018-2019 | % of works completed | 100% | New | Department of Health Services |
| Administration Services | Rehabilitation and refurbishment of the buildings in Ngorongo health centre, Chania ward, Gatundu north sub county | Renovation works finishing and repairs of the buildings | Increase natural lighting | 4,000,000 | KCG | 2018-2019 | % of works completed | 100% | New | Department of Health Services |
| Administration Services | Refurbishment works of the buildings in Nyathuna level 4 hospital, Nyathuna ward, Kabete sub county | Renovation works finishing and repairs of the buildings | Increase natural lighting | 4,000,000 | KCG | 2018-2019 | % of works completed | 100% | New | Department of Health Services |
| Administration Services | Expansion of OPD building and renovation of the laboratory unit in Riabai dispensary, Riabai ward, Kiambu sub county. | Construction works, Renovation works finishing and repairs of the buildings | Increase natural lighting | 4,000,000 | KCG | 2018-2019 | % of works completed | 100% | New | Department of Health Services |
| Administration Services | Construction of covered walk way in Rwamburi dispensary, Ndeiya ward, Limuru sub county | Construction works | Increase natural lighting | 1,000,000 | KCG | 2018-2019 | % of works completed | 100% | New | Department of Health Services |
| Administration Services | Refurbishment of the building and construction of maternity in Thigio dispensary, Ndeiya ward, Limuru sub county | Renovation works finishing and repairs of the buildings | Increase natural lighting | 10,000,000 | KCG | 2018-2019 | % of works completed | 100% | New | Department of Health Services |
| Administration Services | Rehabilitation and refurbishment works in Uthiru dispensary, Uthiru ward, Kabete sub county | Renovation works finishing and repairs of the buildings | Increase natural lighting | 3,000,000 | KCG | 2018-2019 | % of works completed | 100% | New | Department of Health Services |
| Administration Services | Construction of wards, theatre, laboratory unit, fence and gate in Gachororo health centre, Juja ward, Juja sub county | Construction works | Increase natural lighting | 60,000,000 | KCG | 2018-2019 | % of works completed | 100% | New | Department of Health Services |
| Administration Services | Construction of a dispensary Kahawa wendani dispensary, Kahawa Wendani ward, Ruiru sub county | Construction of consultation rooms, pharmacy, MCH, laboratory, offices, stores and waiting bay, fence, toilets and incinerator | Increase natural lighting | 12,000,000 | KCG | 2018-2019 | % of works completed | 100% | New | Department of Health Services |
| Administration Services | Construction of a dispensary Ndumberi dispensary, Ndumberi ward, Kiambu sub county | Construction of consultation rooms, pharmacy, MCH, laboratory, offices, stores and waiting bay, fence, toilets and incinerator | Increase natural lighting | 12,000,000 | KCG | 2018-2019 | % of works completed | 100% | New | Department of Health Services |
| Administration Services | Construction of incinerator in Karatu level 4 hospital, Ndarugo, Gatundu south sub county | Supply of incinerator, construction of accessory facilities. | Condensation of the smoke released to the environment | 4,000,000 | KCG | 2018-2019 | % of works completed | 100% | New | Department of Health Services |
|  | Construction of incinerator Kigumo level 4 hospital, Komothai ward, Githunguri sub county | Supply of incinerator, construction of accessory facilities. | Condensation of the smoke released to the environment | 4,000,000 | KCG | 2018-2019 | % of works completed | 100% | New | Department of Health Services |
| Administration Services | Construction of incinerator in Lari level 4 hospital, Lari/Kirenga ward, lari sub county | Supply of incinerator, construction of accessory facilities. | Condensation of the smoke released to the environment | 4,000,000 | KCG | 2018-2019 | % of works completed | 100% | New | Department of Health Services |
| Administration Services | Supply and installation of generator and renovation of the laboratory unit in Gachororo health centre, Juja ward, Juja sub county. | Supply and installation of generator | Increase natural lighting and use of air cleanser | 6,000,000 | KCG | 2018-2019 | % of works completed | 100% | New | Department of Health Services |
| Administration Services | Supply and installation of generator in Wangige level 4 hospital, Kabete ward, Kabete sub county | Supply and installation of generator | use of air cleanser | 4,000,000 | KCG | 2018-2019 | % of works completed | 100% | New | Department of Health Services |
| Administration Services | Supply and installation of generator in Kigumo level 4 hospital, Komothai ward, Githunguri sub county | Supply and installation of generator | use of air cleanser | 4,000,000 | KCG | 2018-2019 | % of works completed | 100% | New | Department of Health Services |
| Administration Services | Supply and installation of generator in Karatu level 4 hospital, Ndarugo ward, Gatundu south sub county | Supply and installation of generator | use of air cleanser | 4,000,000 | KCG | 2018-2019 | % of works completed | 100% | New | Department of Health Services |
| Administration Services | Renovation and refurbishment of OPD, maternity, fence and gate in Mbau-ini dispensary, Kijabe ward, Lari sub county | Renovation works finishing and repairs of the buildings | Increase natural lighting | 4,000,000 | KCG | 2018-2019 | % of works completed | 100% | New | Department of Health Services |
| Administration Services | Construction of theatre and renovation of the laboratory unit in Ndeiya health centre, Ndeiya ward, Limuru sub county | Construction works, Renovation works finishing and repairs of the building | Increase natural lighting | 8,000,000 | KCG | 2018-2019 | % of works completed | 100% | New | Department of Health Services |
| Administration Services | Construction of theatre , renovation of wards and rehabilitation of the access road in Karatina health centre, Nyanduma ward, Lari sub county | Construction works, Renovation works finishing and repairs of the buildings | Increase natural lighting | 10,000,000 | KCG | 2018-2019 | % of works completed | 100% | New | Department of Health Services |
| Administration Services | Renovation of the OPD and the laboratory unit Muchatha dispensary, Muchatha ward, Kiambaa sub county. | Renovation works finishing and repairs of the buildings | Increase natural lighting | 4,000,000 | KCG | 2018-2019 | % of works completed | 100% | New | Department of Health Services |
| Administration Services | Renovation works of the laboratory unit in Gatundu level 5 hospital, Ng’enda ward, Gatundu south sub county. | Renovation works finishing and repairs of the buildings | Increase natural lighting | 10,000,000 | KCG | 2018-2019 | % of works completed | 100% | New | Department of Health Services |
| Administration Services | Renovation works of the laboratory unit in Ngewa health centre, Ngewa ward, Githunguri sub county. | Renovation works finishing and repairs of the buildings | Increase natural lighting | 4,000,000 | KCG | 2018-2019 | % of works completed | 100% | New | Department of Health Services |
| Administration Services | Renovation and rehabilitation of laboratory, offices, stores, laundry and gate in Limuru health centre, Limuru central, Limuru sub county. | Renovation works finishing and repairs of the buildings | Increase natural lighting | 4,000,000 | KCG | 2018-2019 | % of works completed | 100% | New | Department of Health Services |
| Administration Services | Construction of maternity unit and renovation works of the OPD in Kinoo dispensary, Kinoo ward, Kabete ward | Renovation works finishing and repairs of the buildings | Increase natural lighting | 10,000,000 | KCG | 2018-2019 | % of works completed | 100% | New | Department of Health Services |
| Administration Services | Rehabilitation and refurbishment of the buildings and construction of maternity in Thindigua dispensary, township ward, Kiambu sub county | Construction of fence and gate ,Renovation works finishing and repairs of the buildings | Increase natural lighting | 4,000,000 | KCG | 2018-2019 | % of works completed | 100% | New | Department of Health Services |
| Administration Services | Construction of mortuary in Gatundu level 5 hospital, Ng’enda ward, Gatundu south sub county. | Construction of ultra-modern 36 body mortuary, parkings | Increase natural lighting | 50,000,000 | KCG | 2018-2019 | % of works completed | 100% | New | Department of Health Services |
| Administration Services | Construction of Bibirioni level 4 hospital, Bibirioni ward, Limuru sub county. | Construction of 4 storey building with OPD, wards and theatres | Increase natural lighting and installation of solar energy system | 300,000,000 | KCG | 2018-2019 | % of works completed | 100% | Ongoing | Department of Health Services |
| Administration Services | Upgrade of Githunguri level 4 hospital, Githunguri ward, Githunguri sub county | Construction of ultra-modern storey building with OPD, casualty, ICU, wards, orthopaedic ward, theatre special clinics and parking | Increase natural lighting and installation of solar energy system | 780,000,000 | KCG | 2018-2019 | % of works completed | 100% | Ongoing | Department of Health Services |
| Administration Services | Completion of Kikuyu level 4 hospital, Kikuyu ward, Kikuyu sub county | Finishing works and equipping | Increase natural lighting and installation of solar energy system | 142,000,000 | KCG | 2018-2019 | % of works completed | 100% | Ongoing | Department of Health Services |
| Administration Services | Completion of wards in Tigoni level 4 hospital, Tigoni/Ngecha ward, Limuru sub county | Finishing works and equipping | Increase natural lighting and installation of solar energy system | 152,000,000 | KCG | 2018-2019 | % of works completed | 100% | Ongoing | Department of Health Services |
| Administration Services | Completion of wards in Wangige level 4 hospital, Kabete ward, Kabete sub county. | Finishing works and equipping | Increase natural lighting and installation of solar energy system | 140,000,000 | KCG | 2018-2019 | % of works completed | 100% | Ongoing | Department of Health Services |
| Administration Services | Completion of wards in Lari level 4 hospital, Lari/Kirenga ward, Lari sub county | Finishing works and equipping | Increase natural lighting and installation of solar energy system | 122,000,000 | KCG | 2018-2019 | % of works completed | 100% | Ongoing | Department of Health Services |
| Administration Services | Conversion of ECD classes to dispensary, Karura ka nyungu dispensary, Nyathuna ward, Kabete sub county. | Renovation works, construction of toilets, fence and gate. | Increase natural lighting | 5,000,000 | KCG | 2018-2019 | % of works completed | 100% | New | Department of Health Services |
| Administration Services | Construction of patient toilet block, fence and gate, Karura ka nyungu dispensary, Nyathuna ward, Kabete sub county | Construction of toilet block, fence and gate | Increase natural lighting | 3,000,000 | KCG | 2018-2019 | % of works completed | 100% | New | Department of Health Services |
| Administration Services | Conversion of ECD classes to dispensary, Githiga dispensary, Nyathuna ward, Kabete sub county. | Renovation works, construction of toilets, fence and gate. | Increase natural lighting | 4,000,000 | KCG | 2018-2019 | % of works completed | 100% | New | Department of Health Services |
| Administration Services | Construction of patient toilet block, fence and gate, Gathiga dispensary, Nyathuna ward, Kabete sub county | Construction of toilet block, fence and gate | Increase natural lighting | 3,000,000 | KCG | 2018-2019 | % of works completed | 100% | New | Department of Health Services |
| Total |  |  |  | 1,985,000,000 |  |  |  |  |  |  |

Table 55: Health Services Non-Capital Projects 2018/19 FY

| Programme Name: Administration, Planning and Support services |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Sub Programme | Project name Location (Ward/Sub county/ county wide) | Description of activities | Green Economy consideration | Estimated cost (Ksh.) | Source of funds | Time frame | Performance indicators | Targets | status | Implementing Agency |
| Administration Services | Provision of transport services County wide | Servicing and fueling of vehicles | Use of eco-friendly fuels | 213,877 | CGK | July 2018-June 2019 | No. of serviceable vehicles | 39 | New | Department of Health services |
|  |  | Purchase of vehicles |  | 4,800,000 | CGK | July 2018-June 2019 | No. of vehicles purchased | 2 | New | Department of Health services |
|  | Installation of Health Management Information Systems in Health facilities County wide | Automation of facilities |  | 4,002,348 | CGK | July 2018-June 2019 | No. facilities fully automated with the HMIS | 21 | New | Department of Health services |
|  | Customer satisfaction enhancement County wide | Installation and improvement of service charters |  | 559,345 | CGK | July 2018-June 2019 | No. of improved Service charters | 21 | New | Department of Health services |
|  |  | Establishing customer care units |  | 5,700,000 | CGK | July 2018-June 2019 | No. of customer care service units | 19 | New | Department of Health services |
|  |  | Carry out Customer satisfaction surveys |  | 790,654 | CGK | July 2018-June 2019 | No. of customer satisfaction surveys | 36 | New | Department of Health services |
|  | DHIS reporting County wide | Purchase of airtime and internet bundles |  | 720,000 | CGK | July 2018-June 2019 | No. of facilities submitting DHIS reports | 107 facilities | New | Department of Health services |
|  | Support supervision/Monitoring | Support supervision visits |  | 3,000,000 | CGK | July 2018-June 2019 | No. of facilities supervised by CHMT | 107 facilities | New | Department of Health services |
|  |  | Support supervision visits |  | 384,000 | CGK | July 2018-June 2019 | No. of facilities supervised by SCHMTs | 107 facilities | New | Department of Health services |
| Personnel services | Staff enhancement Countywide | Payment of salaries |  | 3,050,000,000 | CGK | July 2018-June 2019 | No. of staff remunerated | 2653 staff | New | Department of Health services |
|  |  | Recruiting more staff |  | 880,000,000 | CGK | July 2018-June 2019 | No. of staff recruited | 172 staff | New | Department of Health services |
|  |  | Promoting staff |  | 1,895,000 | CGK | July 2018-June 2019 | No. of staff promotions done | 379 staff | New | Department of Health services |
|  | Staff performance management County wide | Appraising staff |  | 26,700,000 | CGK | July 2018-June 2019 | No. of staff appraised | 2825 staff | New | Department of Health services |
|  |  | Rewarding Well performing staff |  | 14,000,000 | CGK | July 2018-June 2019 | Annual reward events | 14 | New | Department of Health services |
|  |  | Team building |  | 21,000,000 | CGK | July 2018-June 2019 | No. of team building activities done | 21 | New | Department of Health services |
| Finance Services | Establishment of procurement and disposal systems-Countywide | Putting in place procurement and disposal systems |  | 676,000 | CGK | July 2018-June 2019 | No. of functional procurement committees in place | 13 | New | Department of Health services |
| Total |  |  |  | 4,014,441,224 |  |  |  |  |  |  |

| Programme Name : Curative Services |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Sub Programme | Project name Location (Ward/Sub county/ county wide) | Description of activities | Green Economy consideration | Estimated cost (Ksh.) | Source of funds | Time frame | Performance indicators | Targets | status | Implementing Agency |
| Curative Health Services | Provision of assorted medical equipment County wide | Equipping facilities with assorted medical equipment |  | 14,000,000 | CGK | July 2018-June 2019 | No. of facilities equipped with assorted medical equipment | 107 | Ongoing | CGK |
|  | Provision of non-pharmaceuticals County wide | Provision of non-pharmaceuticals |  | 7,000,000 | CGK | July 2018-June 2019 | No of facilities provided with non- pharmaceuticals | 107 | Ongoing | CGK |
|  | Provision of cleansing and sanitary materials County wide | Provision of cleansing and sanitary materials |  | 5,000,000 | CGK | July 2018-June 2019 | No of facilities provided with cleansing materials and sanitary items | 107 | Ongoing | CGK |
|  | Establishment of baby friendly services in health facilities County wide | Provision baby friendly services |  | 1,000,000 | CGK | July 2018-June 2019 | No of facilities providing baby friendly services | 15 | New | CGK |
|  | Establishment of lactation stations in health facilities County wide | Provision of lactation stations |  | 600,000 | CGK | July 2018-June 2019 | No of facilities with lactation stations | 20 | New | CGK |
|  | Provision of kitchen gardens in health facilities County wide | Provision of kitchen gardens |  | 16,000,000 | CGK | July 2018-June 2019 | No of facilities with kitchen gardens | 4 | New | CGK |
|  | Provision of nutrition services equipment County wide | Equipping facilities with nutrition services equipment |  | 4,000,000 | CGK | July 2018-June 2019 | No of facilities with nutrition service equipment | 107 | Ongoing | CGK |
|  | Screening and treatment medical camps County wide | Conducting screening and treatment medical camps |  | 2,000,000 | CGK | July 2018-June 2019 | No of screening and treatment medical camps conducted | 8 | Ongoing | CGK |
| Curative Health Services | Establishment of PWD friendly centers County wide | Provision of PWD friendly services |  | 4,000,000 | CGK | July 2018-June 2019 | Facilities providing PWD friendly services | 10 | Ongoing | CGK |
|  | Establishment of Dental clinics County wide | Establish dental clinics |  | 1,000,000 | CGK | July 2018-June 2019 | No of dental clinics establishments | 1 | New | CGK |
|  | Installation of CT scan equipment County wide | Install CT scan machines |  | 75,000,000 | CGK | July 2018-June 2019 | No of CT scan equipment installed | 1 | New | CGK |
|  | Installation of diagnostic ultra sound machines County wide | Install diagnostic ultrasound machines |  | 1,000,000 | CGK | July 2018-June 2019 | No of diagnostic ultrasound machined provided | 1 | New | CGK |
|  | Provision of blood gas analyzers County wide | Provide blood gas analyzers |  | 500,000 | CGK | July 2018-June 2019 | No of blood gas analyzers provided | 1 | New | CGK |
|  | Training of health care workers on IMNCI (Integrated management of new-born and childhood illnesses) County wide | Conduct trainings on IMNCI (Integrated management of new-born and childhood illnesses) |  | 3,875,000 | CGK | July 2018-June 2019 | No of health care workers trained on IMNCI | Planned |  | CGK |
|  | Provision of oral rehydration treatment corners County wide | Provide oral rehydration therapy centers |  | 480,000 | CGK | July 2018-June 2019 | No of oral rehydration centres provided | 40 | New | CGK |
|  | Provision of pulse oximeters County wide | Provide pulse oximeters |  | 125,000 | CGK | July 2018-June 2019 | No of pulse oximeters provided | 50 | New | CGK |
|  | Training of health care workers on Emergency Triage and Treatment (ETAT) | Conduct trainings on Emergency Triage and Treatment (ETAT) |  | 3,875,000 | CGK | July 2018-June 2019 | No of health care workers trained on ETAT |  |  | CGK |
| Total |  |  |  | 139,455,000 |  |  |  |  |  |  |

| Programme Name :Pharmaceutical Services |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Sub Programme | Project name Location (Ward/Sub county/ county wide) | Description of activities | Green Economy consideration | Estimated cost (Ksh.) | Source of funds | Time frame | Performance indicators | Targets | status | Implementing Agency |
| County pharmacies | Renovation of pharmacies Countywide | Renovating pharmacies to meet set standards |  | 10,000,000 |  | July 2018-June 2019 | No of pharmacies renovated | 5 |  | CGK |
| County clinic medicine supply and inventory management service | Procurement of pharmaceuticals and storage equipment Countywide | Procure and stock facilities with pharmaceuticals and storage equipment |  | 250,000,000 |  | July 2018-June 2019 | % of facilities fully stocked all year round | 100% |  | CGK |
|  | Inventory management systems in health facilities Countywide | Establish inventory management systems in facilities |  | 10,000,000 |  | July 2018-June 2019 | % of facilities practicing good inventory management | 80% |  | CGK |
| Total |  |  |  | 270,000,000 |  |  |  |  |  |  |

| Programme Name: County Health Policy Development and Management |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Sub Programme | Project name Location (Ward/Sub county/ county wide) | Description of activities | Green Economy consideration | Estimated cost (Ksh.) | Source of funds | Time frame | Performance indicators | Targets | status | Implementing Agency |
| Health Policy, Planning and Financing | National Hospital Insurance Fund (NHIF) coverage County wide | Support National Hospital Insurance Fund (NHIF) coverage for needy families |  | 270,598,800 | CGK | July 2018 – June 2019 | Proportion of population contributing to NHIF | 44% | New | Department of Health Services, County Government of Kiambu |
|  | Improvement of Emergency medical services County wide | Develop policy brief for improving Emergency medical services |  | 150,000 | CGK | July 2018 – June 2019 | No of policy brief developed and adopted for Emergency and disaster preparedness | 1 | New | Department of Health Services, County Government of Kiambu |
| Health Standards and Quality Assurance | Health quality standards improvement County wide | Develop policy for improving the health quality and standards |  | 150,000 | CGK | July 2018 – June 2019 | No of policy brief developed and adopted for improved health quality and standards | 1 | New | Department of Health Services, County Government of Kiambu |
|  |  | Conduct support supervision visits done |  | 450,000 | CGK | July 2018 – June 2019 | No. of support supervision visits done | 30 | New | Department of Health Services, County Government of Kiambu |
|  |  | Conduct patient and health provider satisfaction surveys | Paperless surveys | 500,000 | CGK | July 2018 – June 2019 | Number of patient satisfaction surveys conducted | 1 | New | Department of Health Services, County Government of Kiambu |
|  |  | Conduct health provider satisfaction surveys | Paperless surveys | 500,000 | CGK | July 2018 – June 2019 | Number of health provider satisfaction surveys conducted | 1 | New | Department of Health Services, County Government of Kiambu |
| Health Capacity Building and Training | Skills and competencies enhancement County wide | Further and higher training for health workers |  | 120,000,000 | CGK | July 2018 – June 2019 | Number of health personnel trained | 530 | New | Department of Health Services, County Government of Kiambu |
|  |  | Hold IMAM training |  | 1,000,000 | CGK | July 2018 – June 2019 | No. of IMAM training conducted | 2 | New | Department of Health Services, County Government of Kiambu |
|  |  | Hold HIV & Nutrition training |  | 1,000,000 | CGK | July 2018 – June 2019 | No of Nutrition HIV training conducted | 2 | New | Department of Health Services, County Government of Kiambu |
|  |  | Hold Nutrition & TB training |  | 1,680,000 | CGK | July 2018 – June 2019 | No of Nutrition & TB training conducted | 4 | New | Department of Health Services, County Government of Kiambu |
|  |  | Hold MIYCF training |  | 1,000,000 | CGK | July 2018 – June 2019 | No of MIYCF training conducted | 2 | New | Department of Health Services, County Government of Kiambu |
|  |  | Hold on job training (OJT) on TB sites |  | 5,000,000 | CGK | July 2018 – June 2019 | % of TB sites done OJT | 80% | New | Department of Health Services, County Government of Kiambu |
| County Health Research and Innovation Programme | Medical research and innovation County wide | Conduct health research on priorities areas |  | 5,000,000 | CGK | July 2018 – June 2019 | % funding directed to medical research | 0.3% | New | Department of Health Services, County Government of Kiambu |
| Total |  |  |  | 407,028,800 |  |  |  |  |  |  |

| Programme Name :Reproductive Health |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Sub Programme | Project name Location (Ward/Sub county/ county wide) | Description of activities | Green Economy consideration | Estimated cost (Ksh.) | Source of funds | Time frame | Performance indicators | Targets | status | Implementing Agency |
| Family planning | Provision of family planning services County wide | Provide contraceptives to women of reproductive age |  | 1,000,000 | CGK | 2018/19 | % of women of Reproductive age receiving family planning | 72% | New | Department of Health Services |
| Maternal child health services | Improvement of maternal child health care County wide | Provision of ARVs to HIV+ pregnant mothers |  | 1,000,000 | CGK | 2018/19 | % HIV + pregnant mothers receiving preventive ARV’s | 100 | New | Department of Health Services |
|  |  | Provision of LLITNs to targeted pregnant women | N/A | 600,000 | CGK | 2018/19 | % of targeted pregnant women provided with LLITN’s | 40 | New | Department of Health Services |
|  |  | Conduct skilled deliveries | N/A | 1,000,000 | CGK | 2018/19 | % deliveries conducted by skilled attendant | 90 | New | Department of Health Services |
|  |  | Provision of quality maternal child health care |  | 400,000 | CGK | 2018/19 | % of facility based maternal deaths | 70 | New | Department of Health Services |
|  |  |  |  | 1,000,000 | CGK | 2018/19 | % of newborns with low birth weight | 4 | New | Department of Health Services |
|  |  |  |  | 1,000,000 | CGK | 2018/19 | % of facility based fresh still births | 1 | New | Department of Health Services |
|  |  | Provision of Antenatal care |  | 2,000,000 | CGK | 2018/19 | % of pregnant women attending 4 ANC visits | 55 | New | Department of Health Services |
|  |  | Conduct Cancer cervical screening |  | 3,000,000 | CGK | 2018/19 | % Women of Reproductive age screened for Cervical cancers | 25 | New | Department of Health Services |
|  |  | Provision of BEOC |  | 600,000 | CGK | 2018/19 | % of facilities providing BEOC | 85 | New | Department of Health Services |
|  |  | Provision of CEOC |  | 600,000 | CGK | 2018/19 | % of facilities providing CEOC | 60 | New | Department of Health Services |
|  |  | Conduct immunization in health facilities |  | 5,000,000 | CGK | 2018/19 | % of facilities providing Immunization | 50 | New | Department of Health Services |
|  |  | Carry out maternal audits/deaths |  | 1,000,000 | CGK | 2018/19 | % maternal audits/deaths audits | 100 | New | Department of Health Services |
|  |  | Provision of supplements to pregnant women |  | 1,000,000 | CGK | 2018/19 | % of pregnant women supplemented with Iron and folic | 80% | New | Department of Health Services |
| Immunization services | Provision of immunization services County wide | Conduct immunization services to children |  | 6,000,000 | CGK | 2018/19 | % of fully immunized children | 90 | New | Department of Health Services |
| Total |  |  |  | 25,200,000 |  |  |  |  |  |  |

Cross-Sectoral Implementation Considerations

| Programme Name | Sector | Cross -sector impact |  | Measures to harness or mitigate the impact |
| --- | --- | --- | --- | --- |
|  |  | Synergy | Adverse impact |  |
| Preventive Health Services | Health and Water, Energy, Environment and Natural resources | - Water quality control - Solid waste management - Liquid waste management | Duplication of roles | - Policy to set out mandate as far as water quality control, solid and liquid waste management is concerned |
| Administration, Planning and Support Services | Health and Administration and Public Service | Human Resource Management |  | - Create a conducive environment to progressively recruit staff as need arises to curb staff shortages - Fast track promotions and re-designations - Establish a strong Performance Management system |
| Preventive Health Services Curative Health Services | Health and Administration and Public Service | - Awareness creation and rehabilitation services for drug and substance abusers - Establishment of drop in centres (DICE) in every constituency |  | - Establish Prevention and Treatment programmes within the county - Collaboration in liquor licensing - Training of a health personnel in mental health and psychology (human skill mix) |
| Preventive Health Services | Health and National Government | School health program |  | - Collaboration in health service delivery among school going children and the youth - Vitamin A supplementation, deworming and growth monitoring |
| Curative Health services | Health and Public works and Infrastructure maintenance | Facilitate construction designs and supervision of public facilities |  | - Carry out environmental impact assessment. - Ensure quality infrastructure through supervision and certification of buildings |
|  | Health and Roads and transport | Facilitate upgrading of access roads to health facilities e.g. Kinale, Nyathuna |  | - Multisectoral approach in prioritizing upgrading of access roads |
| Preventive | Health and Agriculture, Livestock and Fisheries | - Animal food quality control - Map out disease zones - Vaccination and treatment of livestock with antibiotics (antimicrobial resistance) - Zoonotic disease surveillance | - Duplication of Food quality control - Humans developing resistance to antibiotic - Human/animal disease transmission | - Establishment of an interdepartmental Committee - Establishment of technical working group |

### 3.2.9 Education, Youth, Sports, Culture and Social Services

Education and Social Services

Subsector composition

The sector comprises of three Directorates

- Early Childhood Development Education(ECDE)

- Vocational Education and Training (VET)

- Social services

Vision

A dynamic and multi skilled society with holistic base and enhanced social welfare actively participating in sustainable development.

Mission

To empower the society through provision of quality education and Social Services.

Sector/ subsector Goal

To develop policies and procedures, infrastructural framework and human capacity as foundation for growth of ECDE, Vocational Training and Social capital of Kiambu County

Key statistics for the sector/ sub-sector

The sector comprises of 510 ECDE centers and 32 operational vocational training centers. There are numbers of social halls, libraries and other culture and social infrastructure.

Development needs, priorities and strategies

| Development need | Priority | Strategy |
| --- | --- | --- |
| Administrative services | - Establish policy and legal framework for department operations - Improve departmental performance and enhance service delivery to the public. | - Develop YP bill, scheme of work and BOG policy - Develop ECDE feeding bill, scheme of service for ECDE teachers and ECDE bill - Develop a sector plan. - Strictly and effectively perform recurrent administrative services such as remuneration of staff, office maintenance, performance contract and appraisal, motor vehicle maintenance, publicity, hospitality, communication, benchmarking, monitoring, team building, music, drama cultural festivals and sports and collaboration with partners |
| Vocational training center’s development | - Increase access to vocation training - Improve quality of training in Vocational Training centres - Integrate ICT into training - Increase the number of jua kali artisans who are certified by National Industrial Training Authority (NITA) and other accredited examining bodies - Improve funding in vocational training centres | - Construction and establishment of new vocational centres - Renovation and refurbishment of existing physical infrastructure in VETCs - Recruit additional VET instructors - Rebrand and introduce new courses like accounts, supply chain, human resource management, project planning and management and secretarial studies to diversify courses offered in vocational centres to match with market demand. - Provide modern training tools and equipment - Transfer county old vehicles to YPs - Develop a curriculum for short courses - Subsidize youth polytechnic training fee - Establish motor vehicle repair centres and garages in vocational centres - Internet connectivity to all vocational training centres - Procure computers for VETs - Construct computer labs - Mobilize jua kali artisan for short courses that lead to certification - Introduce production units/ IGAs to generate extra income for vocational training. |
| Early Childhood Development Education (ECDE) | - Child Care and feeding programme - Increase access to Early Childhood Development Education (ECDE) | - Enhance ECDE feeding programme to cover children up to age nine. - Construct new ECDEs centres and refurbish/renovate existing ones - Recruit more ECDE teachers - Provide play and teaching and learning materials and aids to ECDE children |
| Bursary fund | Increase the number of students retained and completing secondary school and colleges | Increase bursary allocation |

Capital and Non-Capital Projects

Capital Projects

- Babayao ECDE Center in Wetheithie ward in Juja Sub County

- Kariua ECDE Center in Chania ward Gatundu North Sub County

- Muya ECDE Center in Ndenderu ward Ndenderu Sub County

- Bahati ECDE Center in Hospital ward Thika Sub County

- Mountain View ECDE Center in  Thika Sub County

- Ngoliba  ECDE center in Ngoliba ward  in  Thika Sub County

- Matathia ECDE Center in  Thika Sub County

- Maria Magdalene ECDE Center in Gatuanyaga in  Thika Sub County

- Thika primary ECDE Center in  Thika Sub County

- Nyacaba ECDE Center in Wetheithie ward in Juja Sub County

- Gacharage ECDE Center in Ndenderu ward in Kiambaa Sub County

- Ndenderu ECDE Center in Ndenderuward in Kiambaa Sub County

- Thimbigua ECDE Center in Karuri ward in Kiambaa Sub County

- Kibathi ECDE Center in Karuri ward in Kiambaa Sub County

- Muthurwa ECDE Center in   Karuri  ward in Kiambaa Sub County

- Karuri ECDE Center in Karuri ward in Kiambaa Sub County

- Thuraku ECDE Center in Githoboni ward  in  Thika Sub County

- Gakindu ECDE Center in Mangu  ward  in  Thika Sub County

- ThamandaECDE Center in Sigona ward  in  Kikuyu Sub County

- Gathiru ECDE Center in Nachu  ward  in  Thika Sub County

- Karembu ECDE Center in Kiamwangi ward  in  Gatundu North Sub County

- Mutati ECDE Center in Kiamwangi ward  in  Gatundu South Sub County

- PCEA Ngenda ECDE Center in Ngenda ward  in  Gatundu South Sub County

- Mutomo ECDE Center in Ngenda ward  in  Gatundu South Sub County

- Limuru Town ECDE Center in  Limuru Central ward  in  Limuru Sub County

- Mugutha ECDE Center in Murera  ward  in  Juja Sub County

- Kibute ECDE Center in Murera ward  in  juja Sub County

- Nyacaba ECDE Center in Wetheithie ward in Juja Sub County

- Tinganga ECDE Center in Tinganga ward in Kiambu Sub County

- Ihiga-ini  ECDE Center in Githobikoni ward in Gatundu North Sub County

- Gathage VTC in Kiamwangi ward Gatundu South Sub County

- Murera VTC in Murera ward Juja Sub County

- Runda VTC in Witheithie ward Juja Sub County

- Tigoni VTC in NgechaTigoni ward Limuru Sub County

- Cianda VTC in Cianda ward Kiambaa Sub County

- Gakoe VTC in Githobokoni ward Gatundu North Sub County

- Kwihota VTC in Gatongora  ward Ruiru Sub County

- Kamwirigi VTC in Githobokoni Ward in Gatundu North Sub County

- Mwihoko VTC in Mwihoko Ward in Ruiru Sub County

- Karuri VTC in Karuri Ward in Kimbaa Sub County

- Theta VTC in Theta Ward in Juja Sub County

- Kanjuku VTC in Chania ward Gatundu North Sub County

- Modern tools and equipment

- Establishment of modern garages in Four centers

- Upgrading of Nyaga, Mangu and Kamirithu VTCs to centres of excellence

- Establishment of computer labs at Muguga, Uthiru, Juja Farm and KiganjoYps

- Construction of modern toilets at Riabai, Muguga, Ndumberi, Juja Farm and Kanyoni VTCs

Non- capital projects

- Child care and feeding Programme

- Quality Assurance

- Recruitment of ECDE teachers

- Co-curricular activities

- Instructional materials

- Benchmarking

- ECDE Bills and policy making

- Capacity building for instructors

- Quality Assurance

- Recruitment of instructors

- Co-curricular activities for Y/P

- Exhibitions and trade shows

- Benchmarking

- Instructional materials

- Development of policies and regulations

- Alcohol, drug and substance abuse

- Bursary

Table 56: Education, Youths, Sports, Culture & Social Services Capital projects for the FY 2018/19

| Programme Name General administration, Planning and support services |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Sub Programme | Project name Location (Ward/Sub county/ county wide) | Description of activities | Green Economy consideration | Estimated cost (Ksh.) | Source of funds | Time frame | Performance indicators | Targets | status | Implementing Agency |
| Administration services | Office renovation | Renovation of offices |  | 5M | C.G.K | 2018-2019 | No of offices renovated | 1 | Ongoing | Directorate of education |
|  | Office equipment and furniture | Purchase of office equipment and furniture |  | 10.5M | C.G.K | 2018-2019 | No of office Equipment and furniture purchased and maintained | 1 | Ongoing | Directorate of education |
|  | Vehicles purchase | Purchasing, fuelling and maintaining of vehicles |  | 8.5M | C.G.K | 2018-2019 | No of vehicles purchased, fueled and maintained | 3 | ongoing | Directorate of education |
| Total |  |  |  | 24M |  |  |  |  |  |  |

| Programme Name: Early Child Development Education (ECDE) |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Sub Programme | Project name Location (Ward/Sub county/ county wide) | Description of activities | Green Economy consideration | Estimated cost (Ksh.) | Source of funds | Time frame | Performance indicators | Targets | status | Implementing Agency |
| Nursery Infrastructure Development | ECDE Centers and ablution blocks(Countywide) | Construction, renovation and refurbishment of ECDE classrooms and ablution blocks | N/A | 90M | CGK | 2018-2019 | No. of ECDE centers and ablution blocks constructed | 49 | ongoing | Directorate of ECDE |
| Total |  |  |  | 90M |  |  |  |  |  |  |

| Programme Name: Vocational Education and Training (Youth Polytechnics) |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Sub Programme | Project name Location (Ward/Sub county/ county wide) | Description of activities | Green Economy consideration | Estimated cost (Ksh.) | Source of funds | Time frame | Performance indicators | Targets | status | Implementing Agency |
| Vocational training centers development | Vocational Training Centers, Youth Polytechnics, Offices and Ablution blocks (Countywide) | Construction, refurbishment, renovation of VTCs and ablution blocks | N/A | 90M | CGK | 2018- 2019 | No of VTCs and ablution blocks constructed | 40 | On going | Directorate of VTC |
|  | Modern tools and equipment | Procurement, delivery and distribution of modern tools and equipment | N/A | 10M | CGK | 2018-2019 | Percentage equipment | 100 | ongoing | Directorate of VTC |
|  | Modern garages in Four centers | Procurement, delivery and distribution of equipment | N/A | 9.5M | CGK | 2018-2019 | Percentage equipment | 100 | ongoing | Directorate of VTC |
|  | Computer labs(Countywide) | Establishment, equipment delivery and networking | N/A | 10M | CGK | 2018-2019 | Percentage equipment | 100 | ongoing | Directorate of VTC |
| Total |  |  |  | 119.5M |  |  |  |  |  |  |

Table 57: Education, Youths, Sports, Culture & Social Services Non Capital projects for the FY 2018/19

| Programme Name General Administration, Planning and Support services |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Sub Programme | Project name Location (Ward/Sub county/ county wide) | Description of activities | Green Economy consideration | Estimated cost (Ksh.) | Source of funds | Time frame | Performance indicators | Targets | status | Implementing Agency |
| Personnel services | Staff remuneration | Remuneration of staff, allowances and statutory deductions paid |  | 654M | CGK | 2018-2019 | No of staff remunerated, allowances paid and statutory deductions paid. | 1660 | Ongoing | Office of Chief Officer |
| Administration services | Project monitoring | Institutions monitored and benchmarked |  | 11M | CGK | 2018-2019 | No of institutions and projects monitored, bench markings and meetings attended. | 20 | Ongoing | Office of Chief Officer |
|  | Team building | Team building activities held |  | 1M | C.G.K | 2018-2019 | No. of team building activities held | 1 | ongoing | Office of Chief Officer |
|  | Performance contract | Staff under performance contract |  | 2M | C.G.K | 2018-2019 | No. staff under performance contract | 1635 | Ongoing | Office of Chief Officer |
|  | Exhibitions and Media shows | Hold exhibitions, media shows and distribute posters |  | 8M | C.G.K | 2018-2019 | No of exhibitions and media shows done and posters and distributed | 5 | Ongoing | Office of Chief Officer |
|  | Bursary | Disbursement of bursary fund to vulnerable and needy cases |  | 190M | CGK | 2018-2019 | The amount of money disbursed | 30,000 | New | Office of Chief Officer |
| Total |  |  |  | 866 |  |  |  |  |  |  |

| Programme Name: Early Child Development Education (ECDE) |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Sub Programme | Project name Location (Ward/Sub county | Description of activities | Green Economy consideration | Estimated cost (Ksh.) | Source of funds | Time frame | Performance indicators | Targets | status | Implementing Agency |
| Child care and feeding Programme | Feeding Programme | Improve developmental health, learning and psychosocial wellbeing of ECDE going children |  | 240M | CGK | 2018-2019 | No. of ECDE children benefitting from Nutrition programme | 33,000 | New | Directorate of ECDE |
| Quality Assurance and standards | Quality assurance | Improve Quality of early childhood education. |  | 6M | CGK | 2018-2019 | Quality education in ECDE centers | 520 | New | Directorate of ECDE |
| Teacher training and curriculum development | ECDE teachers recruitment | Recruitment, Induction and Deployment |  | 70M | CGK | 2018-2019 | No of ECDE teachers recruited | 400 | New | Directorate of ECDE |
|  | Instructional materials | Procurement, Delivery of the materials |  | 17M | CGK | 2018-2019 | No of ECDE centers instructed with materials | 550 | New | Directorate of ECDE |
| Legal and policy framework | ECDE Bills and policy making | Provide policy guidelines for appointment and operations |  | 7M | CGK | 2018-2019 | No of policies, bills and regulations developed | 3 | New | Directorate of ECDE |
| Total |  |  |  | 340M |  |  |  |  |  |  |

| Programme Name: Vocational Education and Training (Youth Polytechnics) |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Sub Programme | Project name Location (Ward/Sub county/ county wide) | Description of activities | Green Economy consideration | Estimated cost (Ksh.) | Source of funds | Time frame | Performance indicators | Targets | status | Implementing Agency |
| Vocational, Education and Training(Y/P | Recruitment of instructors | Recruitment, Induction and Deployment |  | 30M | CGK | 2018-2019 | No of instructors recruited | 100 | New | Directorate of Vocational Education and Training |
| Total |  |  |  | 30M |  |  |  |  |  |  |

| Programme Name: Social Services |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Sub Programme | Project name Location (Ward/Sub county/ county wide) | Description of activities | Green Economy consideration | Estimated cost (Ksh.) | Source of funds | Time frame | Performance indicators | Targets | status | Implementing Agency |
| Social services | Alcohol, drug and substance abuse | Improved health and economic status to the youth |  | 10M | CGK | 2018-2019 | reduced level of alcohol and drug abuse in the county | 300 | New | Directorate of Gender, Social and Culture |
| Total |  |  |  | 10M |  |  |  |  |  |  |

Sector/sub-sector key stakeholders

| Stakeholder category | Stakeholder expectation | Sector expectation |
| --- | --- | --- |
| Kenya National Examinations Council (KNEC) | Present trainees for certification | To certify trainees as presented for examination |
| Kenya Institute Of Curriculum Development (KICD) | To implement accredited curriculum | Provision of relevant and accredited curriculum |
| Technical Vocational Education and Training Authority (TVETA) | Present documents for purposes of Inspection, Licensing and Accreditation of VTCs | Inspection, Licensing and Accreditation of institutions |
| Council of Governors | To implement policies in line with devolution act 2013 | Updated policies |
| Ministry of Education , Science and Technology | Submission of enrolment for purposes of securing capitation | Provision of capitation as per submitted enrolment |
| Parents | Quality and relevant training | Presentation of children for learning in Educational institutions |

Cross-sectorial Implementation Considerations

The sector will ensure that the nutritional needs of ECDE learners are improved. Retention and access of education opportunities in both ECDE and Youth Polytechnics will be enhanced especially amongst disadvantaged groups. Gender and disability concerns will be mainstreamed and adhering to the 30% rule.

| Programme Name | Sector | Cross-sector Impact |  | Mitigation Measures |
| --- | --- | --- | --- | --- |
|  |  | Synergies | Adverse impact |  |
| Vocational education and training | Vocational Training Centers Development | Development partners in skills enhancement | Duplication of activities | Develop clear rules of undertakings |
|  | Technical trainer and Instructor services | National government | Scheme of service and accreditation | Harmonisation of national scheme of service and accreditation rules with county policy |
| Bursary | Education | National government | Duplication of allocation/Double Allocation | Establish a common bursary committee Fund, with membership from NGO CDF,MOE,& County Govt |
| Development of Early Childhood education | Monitoring and evaluation, school Management and curriculum development | National government | Delay of materials and services, and poor management | Improve communication channels |

### 3.2.10 Youth Affairs, Sports, Gender and Culture

Vision

To be a model department in youth empowerment and sporting excellence

Mission

To transform and inspire the community using platforms that empower the youth and enhance sporting excellence.

Sub-Sector goals

Youth

Capacity building, talent development and marketing, social economic empowerment, sports development, and entrepreneurship funding through the county youth, women and PWDs enterprise fund.

Sports

Promotion of sporting culture through construction of sporting facilities and introduction on new sports in the county

Gender

Social economic empowerment of communities and main streaming gender concerns in all sectors of development

Culture

Heritage management, conservation and promotion of culture.

Key statistics for the sector/ sub-sector

There are six social halls and two culture and social infrastructure. The sector also comprises of eight standard stadiums, three Astroturf fields and sports field in every ward, one amphitheater is still under construction.

Development priorities

| Development need | Priorities | Strategy |
| --- | --- | --- |
| Promotion of sports | Sports facilities management Sports development | - Construction and rehabilitation of sporting facilities - Training and funding of county teams - Establishment of county sports academy - Establishment of sports trust fund - Formulation of a sports management legislative policy to govern sporting activities in the County - Identification and nurturing of sporting talent in the county |
| Youth Affairs | Job creation for the youths | Create jobs through direct investment in agriculture &agro-processing |
|  |  | Create a conducive environment for growth and development of small and medium enterprise sector such as key artisans in mechanics and other Jua Kali operatives in catering and food industries among others. |
|  |  | Create a new brand of entrepreneurs to undertake activities such as road construction, repair and maintenance, water drilling and distribution systems, |
|  |  | Involvement of youths in cleaning and providing sanitary services in key towns, markets and other private and county owned facilities. |
|  |  | Financially empowering youth, women, people living with disabilities and men through sustainable and accessible revolving funds. |
|  |  | Support and advance the formation and inauguration of the proposed Kiambu University of Technical and Innovation Institution( KUTI) a demand driven university that is modelled along the same idea as the MIT (Massachusetts Institute of Technology) an industry demand driven training Institute |
| Gender | Gender mainstreaming | - Construct and equip a GBV rescue and rehabilitation centre - Renovate refurbish and equip existing children homes - Refurbishment renovation and equipping of field offices , mapping conservation and gazettement of cultural and heritage sites, construction of museum cultural and resource centre, construction and equipping of public library |
| culture | Cultural heritage promotion preservation and management | Cultural festival and exchange programs , |

Sector/sub-sector key stakeholders

| Stakeholder Category | Stakeholder Expectation | Sector Expectation |
| --- | --- | --- |
| Football Kenya Federation (FKF) Athletics Kenya Kenya Volleyball Federation (KVF) KICOSCA KYISA National Museums of Kenya UNESCO National Gender and Equality Commission Women Enterprise Development Fund | - Affiliation of teams , standard county stadiums and football equipment’s - Finance competitions, facilitation for national and international competitions. - Affiliation of teams , standard county stadiums and football equipment’s - Participation of county staffs in annual competitions - Participation of county youth in annual competitions - Gazettement of artefacts and historical sites - Promotion of education, science and culture - Providing equal opportunities for all regardless of gender - To empower women economically. | - Partnership in tournaments and competitions in the county - Promotion of county athletes in national and international competitions - Partnership in tournaments and competitions in the county - Motivation of county staffs through sporting activities - Exposure of county youth to national sporting arenas. - To identify all historical sites and artefacts - Identification of cultural practices worth preservation - Ensuring opportunities equal opportunities for all genders. - To ensure that women engage in income generating activities. |

Capital and Non-Capital Projects

Capital projects: Construction of Limuru high altitude training centre, construction of Lari Kirenga, Kirigiti stadium, Kanjeru stadium, Ruiru stadium, Thika stadium, upgrade of one field per ward, completion of Kirigiti amphitheater, construction of a museum cultural and resource centre, refurbish renovate and equip community halls  and field offices ,conservation of cultural and heritage sites, construct and equip a GBV center, renovate children home, construct and equip a rehab center, completion of community hall, Karuri social hall, completion and equipping of Lusingeti library, renovation, refurbishing and equipping Jamhuri children’s home

Non-capital projects: Capacity building and skill enhancement, human resource development, marking of international days relevant to the department, GBV sensitization, participating in Kenya music and cultural festival and UNESCO national cultural celebrations, cultural festivals and exchange program

Table 58: Youths Affairs, Sports, Gender & Culture capital projects for the FY 2018/19

| Programme Name General Administration, Planning and Support Services |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Sub Programme | Project name Location (Ward/Sub county | Description of activities | Green Economy consideration | Estimated cost (Ksh.) | Source of funds | Time frame | Performance indicators | Targets | status | Implementing Agency |
| Administration services | Office equipment | Purchase of equipment |  | 12M | CGK | 2018-2019 | No. of offices equipped | 3 | new | Department of youth and sports |
|  | Field offices | Equipping and refurbishing of field offices |  | 100M | CGK | 2018-2019 | No of offices equipped and refurbished | 12 | new | Directorate of gender and culture |
|  | Motor vehicles | Purchasing, fuelling and maintenance of vehicles |  | 40M | CGK | 2018-2019 | No of motor vehicles purchased, fuelled and maintained | 4 | new | Directorate of gender and culture |
|  | General operation and maintenance | Maintenance of operations and current expenditure |  | 57M | CGK | 2018-2019 |  |  | ongoing | Directorate of gender and culture |
| Personnel services | Staff renumeration | Remuneration of staff, allowances and statutory deductions paid |  | 88M | CGK | 2018-2019 | No of staff remunerated, allowances paid and statutory deductions paid | 40 | ongoing | Department of youth and sports |
|  | Authority to Incure expenditure(A.I.E) | Paying of A.I.Es to field officers |  | 3M | CGK | 2018-2019 | No of officers paid | 30 | ongoing | Directorate of gender and culture |

| Programme Name: Sports |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Sub Programme | Project name Location (Ward/Sub county/ county wide) | Description of activities | Green Economy consideration | Estimated cost (Ksh.) | Source of funds | Time frame | Performance indicators | Targets | status | Implementing Agency |
| Development and management of sports facilities | Limuru | fencing and construction of WC/changing rooms |  | 10.M | KCG | 2018-2019 | Percentage completion | 1 | ongoing | KCG |
|  | Lari-kirenga | fencing and construction of WC/changing rooms |  | 10.M | KCG | 2018-2019 | Percentage completion | 1 | New | KCG |
|  | Kirigiti stadium | Construction of modern Amphitheatre |  | 30.M | KCG | 2018-2919 | Percentage completion | 30% | ongoing | KCG |
|  | Kanjeru stadium | Construction of changing rooms/WC and upgrading |  | 30.M | KCG | 2018-2019 | Percentage completion |  | ongoing | KCG |
|  | Githunguri stadium | Fencing and construction of WC and changing room |  | 10M | KCG | 2018-2019 | Percentage completion | 100% | new | KCG |
|  | Ruiru stadium | Fencing and terraces |  | 100M | KCG | 2018-2018 | Percentage completion | 100% | Ongoing | KCG |
|  | Thika stadium | Terraces |  | 20M | KCG | 2018-2019 | Percentage completion | 100% | Ongoing | KCG |
|  | One field per ward/ youth empowerment centres | Development /construction |  | 48M | KCG | 2018-2019 | Percentage completion | 20% | Ongoing | KCG |
| Sports training and competition | Athletics | Participation of county athletes in local, regional, and international competitions |  | 10M | KCG | 2018-2019 | NO. of athletes participating | 500 | Ongoing | KCG |
|  | Kicosca games | Staff teams and cultural dancers participating in inter county competition |  | 30.M | KCG | 2018-2019 | NO. of staff participating in Kicosca games | 500 | Ongoing | KCG |
|  | Kyisa games | County youth participating in Kenya inter county youth association games |  | 5M | KCG | 2018-2019 | No of teams participating in Kyisa games | 200 | Ongoing | KCG |
| Total |  |  |  | 303M |  |  |  |  |  |  |

| Programme Name: Gender and Culture |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Sub Programme | Project name Location (Ward/Sub county/ county wide) | Description of activities | Green Economy consideration | Estimated cost (Ksh.) | Source of funds | Time frame | Performance indicators | Targets | status | Implementing Agency |
| Gender and Culture | GBV rescue and rehab center in Thika Sub County | Construction and equipping of a rehabilitation center |  | 10M | CGK | 2018 - 2019 | Percentage Completion | 100 | New | Directorate of culture |
|  | Museum and resource center in Githunguri Sub County | Construction of museum and resource center |  | 10M | CGK | 2018 - 2019 | Percentage Completion | 100 | New | Directorate of culture |
|  | Mugumuini Gardens in Thika Sub County | Rehabilitation and conservation of mugumuini gardens |  | 7M | CGK | 2018 - 2019 | Percentage | 100 | New | Directorate of Culture |
|  | Cultural and heritage sites in Githunguri sub County | Rehabilitation and conservation of cultural and heritage sites |  | 7M | CGK | 2018 - 2019 | Percentage | 100 | New | Directorate of Culture |
|  | Jamhuri children’s home in Thika Sub County | Rehabilitation and equipping of Jamhuri children home |  | 7M | CGK | 2018 - 2019 | Percentage | 100 | New | Directorate of Culture |
|  | Community Library | Construction and equipping of a community library |  | 10M | CGK | 2018 - 2019 | Percentage Completion | 100 | New | Directorate of culture |
|  | Karuri Social hall | rehabilitation and equipping of karuri social hall |  | 3M | CGK | 2018 - 2019 | Percentage Completion | 100 | Ongoing | Directorate of culture |
|  | Kiambu Community Hall | Rehabilitation and equipping of Kiambu community hall |  | 5M | CGK | 2018 - 2019 | Percentage Completion | 100 | New | Directorate of culture |
|  | Lussigetti Community Library in Nachu ward | Construction and equipping of the library |  | 3M | CGK | 2018 - 2019 | Percentage Completion | 100 | Ongoing | Directorate of culture |
|  | Historical monument at Kirangari, Kiambaa and Kiambu | Construction and erecting of monuments |  | 5M | CGK | 2018 - 2019 | Percentage Completion | 100 | New | Directorate of Culture |

Table 59: Youth Affairs, Sports, Gender and Culture non-capital projects for the FY 2018/19

| Programme Name: Youth Affairs |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Sub Programme | Project name Location (Ward/Sub county/ county wide) | Description of activities | Green Economy consideration | Estimated cost (Ksh.) | Source of funds | Time frame | Performance indicators | Targets | status | Implementing Agency |
| Youth Empowerment | Capacity buildings | County wide skills enhancement programs |  | 124.M | KCG | 2018-2019 | No. of youth trained | 6,000 | On going | KCG |

| Programme Name: Gender and Culture |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Sub Programme | Project name Location (Ward/Sub county/ county wide) | Description of activities | Green Economy consideration | Estimated cost (Ksh.) | Source of funds | Time frame | Performance indicators | Targets | status | Implementing Agency |
| Gender and Culture | Gender and Disability | Mainstreaming and Economic empowerment. |  | 1M | CGK | 2018-2019 | No of women, youth and PWDs groups funded. | 300 | New | Directorate of Gender, Social and Culture |
|  | Alcohol, drug and substance abuse | Implement the alcohol and drug abuse policy |  | 5M | CGK | 2018-2019 | No of youths rehabilitated from alcohol and drug abuse | 300 | Ongoing | Directorate of Gender, Social and Culture |
|  | Street families | Rehabilitation of street families |  | 5M | CGK | 2018-2019 | No of street families rehabilitated | 50 | New | Directorate of Gender, Social and Culture |
|  | Cultural development | Upcoming artists mentorship |  | 1M | CGK | 2018-2019 | No of youth trained | 60 | New | Directorate of Gender, Social and Culture |
|  | Kenyan music and dance | Participation in Kenyan music and cultural festivals and UNESCO National Celebrations |  | 5M | CGK | 2018-2019 | No of upcoming artist mentored | 60 | New | Directorate of Gender, Social and Culture |
|  | Cultural and Heritage | Conservation and heritage management sensitization |  | 5M | CGK | 2018-2019 | No of sensitization programs held | 1 | New | Directorate of Gender, Social and Culture |
|  | Gender Based Violence | Prevention response and management |  | 1M | CGK | 2018-2019 | No of multi-stakeholders technical working groups formed, No of sensitization forums held | 2 | New | Directorate of Gender, Social and Culture |
|  | Community Development | Provision of assistive devices ,sanitary wear, blankets and food stuff |  | 5M | CGK | 2018-2019 | No of assistive devices issued | 100 | New | Directorate of Gender, Culture |
|  | International Day of Old persons | Celebrations, awareness on tailor made health programs for old persons |  | 3M | CGK | 2018-2019 | No of old persons reached | 1,200 | New | Directorate of Gender and Culture |
|  | Cultural exchange program | Procurement of transport services and accommodation services for the exchange program |  | 2M | CGK | 2018-2019 | No of programs held no of officers participating | 3 | New | Directorate of Gender and Culture |

Cross-sectoral Implementation Considerations

The sector will embark on a campaign to ensure that youth, women and people with disability affirmative action is considered in other sectors.

Where expertise from other department is required the department won’t hesitate to involve the concerned department

| Program Name | Sector | Cross-sector Impact |  | Measures to Harness or Mitigate the Impact |
| --- | --- | --- | --- | --- |
|  |  | Synergies | Adverse impact |  |
| Youth affairs, sports, gender and culture | education | Youth empowerment |  | Recommendation to youth polytechnics Recommendation for funding |
|  | agriculture | Youth Training |  | Training on Agri-business, value addition Recommendation for funding |
|  | Health | Reproductive health and adolescence health and GBV | Drug and substance abuse, HIV& AIDS | Rehabs, seminars and peer training Improve communication channel and harmonize efforts in both sectors |
|  | Finance | Youth training on financial management |  | Facilitation, expert opinion |
|  | Lands and Housing | Job creation |  | Recommendation to available job networks |
|  | Roads | Job creation |  | Recommendation to available job networks |
|  | Agriculture | Social economic empowerment |  | Improve communication channel and harmonize efforts in both sectors |

### 3.2.11 Lands, Physical Planning and Housing

Sector composition

This sector comprises of

- Physical Planning

- Urban development and management

- Land Survey and Geo Informatics

- Housing and Community Development

- Land Valuation and Asset Management

Vision

Planned & Managed Land Resource for Sustainable Development

Mission

To promote an integrated framework of spatial planning and development for the social, Economic well-being and environmental sustainability of the County

Sector goal

Make Kiambu county and its human settlements safe, resilient and sustainable for development through provision of decent, adequate and housing, affordable transportation, sustainable urban areas and basic infrastructure services and facilities.

Sector Mandate and Functions

- Provision and implementation of spatial  plans  to promote sustainable  rural and urban management and development;

- Development of a GIS/LIMS database for spatial data management and determination of property boundaries;

- Provision of efficient land and property valuation and management for effective county asset documentation and land taxation;

- Promotion and facilitation of development

- Formulation, implementation and review of various policies in the Department

Development needs, priorities and strategies

Capital and Non-Capital Projects

Table 60: Lands, Physical Planning & Housing ousing Capital projects for the 2018/19FY

| Programme Name : County Land Information Management Services |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Objective: To have and efficient spatial data management system |  |  |  |  |  |  |  |  |  |  |
| Outcome: Improved revenue, Ease in access, use archival and retrieval of County Land Data |  |  |  |  |  |  |  |  |  |  |
| Sub Programme | Project name Location (Ward/Sub county/ county wide) | Description of activities | Green Economy consideration | Estimated cost (Ksh.) | Source of funds | Time frame | Performance indicators | Targets | status | Implementing Agency |
| County Land Information Service | County Land Information Service | Digitilization of county land parcels information |  | 4M | CGK | 2018/2019 | Number of land parcels digitized -Existence of | 35,000 |  | Department of land Housing and Physical Planning |
|  | Property rates register | Establishment of property rates register |  | 48M | CGK | 2018/19 | No. of property rates registered | 160,000 |  | Department of land Housing and Physical Planning |
| Valuation of county property | Valuation of county property | Valuation of county property |  | 15.4M | CGK | 2018/2019 | No. of county properties valued | 200 |  | Department of land Housing and Physical Planning |
| Management of county property | County property management | management of county property |  | 4M | CGK | 2018/19 | No. of properties managed | 300 |  | Department of land Housing and Physical Planning |
| Total |  |  |  | 71.4M |  |  |  |  |  |  |

| Programme Name: Planning, Land Survey and Mapping |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Objective: To provide an overall spatial framework for the county to guide development |  |  |  |  |  |  |  |  |  |  |
| Outcome: Updated, spatial plans and maps for the county |  |  |  |  |  |  |  |  |  |  |
| Sub Programme | Project name Location (Ward/Sub county/ county wide) | Description of activities | Green Economy consideration | Estimated cost (Ksh.) | Source of funds | Time frame | Performance indicators | Targets | status | Implementing Agency |
| County Spatial Planning and Development | Preparation of County spatial plan | Preparation of County spatial plan |  | 100M | CGK | 2018/19 | Number of County Spatial Structure Plan | 1 |  | Department of land Housing and Physical Planning |
|  | Preparation of ISUDPS | Preparation of ISUDPS |  | 100M | CGK | 2018/19 | Number of ISUDPS prepared -Defined urban edges -Building guidelines and planning regulation | 1 |  | Department of land Housing and Physical Planning |
| Development Control | Development application county wide | Approval of development applications |  | 20M | CGK | 2018/19 | Percentage of developers submitting development application Percentage Increase in revenue generation | 10% |  | Department of land Housing and Physical Planning |
|  | Enforcement and compliance to development regulations | Enforcement and compliance to development regulations |  | 10M | CGK | 2018/19 | Percentage increase in compliance to development regulations | 20% |  | Department of land Housing and Physical Planning |
| County Land Survey, Mapping, Boundaries establishment | Reestablishment and documentation of public land and boundaries | Reestablishment and documentation of public land and boundaries |  | 2M | CGK | 2018/19 | Number of parcel boundaries reestablished and beacons placed. | 100 |  | Department of land Housing and Physical Planning |
|  | Identification and acquiring of title deeds for registered public land | Identification and acquiring of title deeds for registered public land |  | 2M | CGK | 2018/19 | Number of title deeds acquired | 200 |  | Department of land Housing and Physical Planning |
|  | Preparation of base maps | Preparation of base maps |  | 6M | CGK | 2018/19 | Number of base maps prepared | 30 |  | Department of land Housing and Physical Planning |
|  | Completion of Digital topographical mapping | Completion of Digital topographical mapping |  | 20M | CGK | 2018/19 | Percentage area of the County completed | 20% |  | Department of land Housing and Physical Planning |
| Total |  |  |  | 260M |  |  |  |  |  |  |

| Programme Name: County Urban Planning and Housing |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Objective: To ensure sustainable urban growth and development |  |  |  |  |  |  |  |  |  |  |
| Outcome: Livable well managed urban areas with adequate, safe, decent and affordable housing |  |  |  |  |  |  |  |  |  |  |
| Sub Programme | Project name Location (Ward/Sub county/ county wide) | Description of activities | Green Economy consideration | Estimated cost (Ksh.) | Source of funds | Time frame | Performance indicators | Targets | status | Implementing Agency |
| Urban Planning and Development | Formation and operationalization of Municipal and Town management boards | Formation and operationalization of Municipal and Town management boards |  | 10M | CGK | 2018/19 | Number of Operational Municipal and Towns Management Boards | 6 |  | Department of land Housing and Physical Planning |
|  | Establishment of municipal boundaries | Define boundaries of the new municipalities |  | 10M | CGK | 2018/19 | Number of well-defined boundaries of the new municipalities | 6 |  | Department of land Housing and Physical Planning |
| County Urban Institutional Program | Operationalization of County Urban Institutional Program | Operationalization of County Urban Institutional Program |  | 1.8B | CGK | 2018/19 | Amount in Kshs allocated to CIUDS program | 1.8B |  | Department of land Housing and Physical Planning |
| County Informal settlement upgrading | Improve social economic environment security of land tenure | Improve social economic environment security of land tenure |  | 0.5B | CGK | 2018/19 | No. of upgraded settlements And basic facilities provided in the upgraded settlements | 2 |  | Department of land Housing and Physical Planning |
| Promotion of appropriate building technology | adopting appropriate building technology | adopting appropriate building technology |  | 30.8M | CGK | 2018/19 | Number of building technologies adopted | 1 |  | Department of land Housing and Physical Planning |
| Urban renewal | Increase access to decent housing | Increase access to decent housing |  | 2.5B | CGK | 2018/19 | Number of households accessing the decent houses | 500 |  | Department of land Housing and Physical Planning |
| Total |  |  |  | 4.8B |  |  |  |  |  |  |

Table 61: Lands, Physical Planning & Housing non ousing capital projects for the 2018/19FY

| Programme Name: Administration, Planning and Support Services |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Objective: To improve service delivery |  |  |  |  |  |  |  |  |  |  |
| Outcome: Improved efficiency and effectiveness in service delivery |  |  |  |  |  |  |  |  |  |  |
| Sub Programme | Project name Location (Ward/Sub county/ county wide) | Description of activities | Green Economy consideration | Estimated cost (Ksh.) | Source of funds | Time frame | Performance indicators | Targets | status | Implementing Agency |
| Administration Services | offices | Construction of new offices |  | 5M | CGK | 2018/19 | Number of offices constructed | 2 |  | Department of land Housing and Physical Planning |
|  | offices | Equipping offices |  | 0.4M | CGK | 281/2019 | Number of offices equipped |  |  | Department of land Housing and Physical Planning |
|  | vehicles | Purchase vehicles |  | 10M | CGK | 2018/2019 | Number of vehicles purchased | 2 |  | Department of land Housing and Physical Planning |
| Personnel | personnel | Personnel employed |  | 4M | CGK | 2018/19 | No. of personnel employed |  |  | Department of land Housing and Physical Planning |
|  | Capacity building | Training sessions |  | 2M | CGK | 2018/2019 | No. of training sessions | 2 |  | Department of land Housing and Physical Planning |
|  | Performance Appraisals | Performance appraisals |  | 1M | CGK | 2018/2019 | No. of performance appraisals done | 1 |  | Department of land Housing and Physical Planning |
| Finance Services | Perfomance reports | Preparation of Quartery reports |  | 0.4M | CGK | 2018/19 | No. of reports prepared | 4 |  | Department of land Housing and Physical Planning |
| Total |  |  |  | 22.8M |  |  |  |  |  |  |

Key stakeholders

Cross-sectoral Implementation Considerations.

| Programme Name/ Location | Sector | Cross Sector Impact |  | Measures to Harness or Mitigate the Impact |
| --- | --- | --- | --- | --- |
|  |  | Synergies | Adverse Impact |  |
| Land Survey, Mapping and Geographical Information Systems | - Physical Planning - Urban Development and Management - Housing - Valuation and Asset Management - Education - Sports - Administration - Public Service - Finance - Water, Environment and Natural Resources | - Securing of public land - Efficient storage and retrieval of land information - Timely and efficient update of land information | - May lead to displacement of people - Negative public perception | - Undertake public participation - Public-private partnership - Collaboration with NLC and other government agencies |
| Urban renewal and upgrading of informal settlements | - Physical Planning, - Urban Development and Management - Valuation and Asset Management - Land Survey and GI - Water, Environment and Natural Resources - Roads, Transport and Public Works - Trade, Tourism, Industry and Enterprise Development - Administration - Public Service - Finance | - Provision of adequate social and physical infrastructure within the housing development programme - Optimal utilization of space through land use planning - Accurate land valuation for preparation of housing models and future rating - Appropriate boundary establishment - Integration of trade and enterprise to facilitate community development - Incorporation of environmental considerations in housing development | - Risk of gentrification | - Transparency and accountability from project planning to house allocation and project monitoring - Capping of house selling prices and rent to values that are affordable by the targeted beneficiaries |
| Land valuation and property management | - Physical Planning - Urban Development and Management - Land Survey and GI - Finance - Education - Health - Sports - Administration - Public Service - Water, Environment and Natural Resources | - Updated valuation register of county properties - Enhanced revenue generation from land rates - Efficient management of county properties | - Risk of poor public perception | - Undertake proper public participation - Continuous public sensitization |
| Plan Preparation and Implementation | - Land Survey and GI - Valuation and Asset Management Finance - Education, Gender, Culture and Social Services - Health - Youth, Sports, ICT and Communication - Administration - Public Service - Water, Environment and Natural Resources - Roads, Transport and Public Works - Trade, Tourism, Industry and Enterprise Development - Agriculture, Livestock and Fisheries | - Controlled development - Increased revenue generation - Clear zoning and building guidelines - Protection of wetlands and ecologically fragile areas - Encourage investments - Enhanced land values - Conserve agricultural and forest areas | - Risk of poor public perception | - Undertake proper public participation - Continuous public sensitization |

### 3.2.12 Trade, Tourism, Industry and Co-operative

Vision:

A destination of choice for investors and tourists

Mission:

To provide an enabling environment for investors and tourists for sustainable development

Sub-sector goals and targets

The sector works towards achievement of goals that are geared towards promotion and facilitating investments in Trade, Tourism, Cooperative and Enterprise Development in Kiambu County. The strategic goals for the subsectors are:

- Promotion and development of trade and  markets

- Promotion and Development of Enterprise Development

- Promotion and development of Tourism and Marketing

- Promotion and Development of Co-operative Societies

Development Needs, Priorities and Strategies

| Development needs | Priority | Strategies |
| --- | --- | --- |
| Institutional Legal and regulatory framework | Realign the existing policies and laws with the constitution and harmonize them | Develop and review various policies and relevant Acts |
| Employment Creation | To facilitate the creation of productive employment | - Give incentives to spur investments - Expand markets to encourage more businesses - Develop and encourage tourism activities - Promote dispersal of cottage industries in rural areas |
| Value addition and product diversification | - Industrial development and promotion of value addition in the County - To promote product diversification | - Embrace OVOP initiative in the County - Capacity building and training on value addition and entrepreneurship - Coming up of special programmes for the Youth and Women targeting value addition - Creation of Small Processing Units through formation of Cooperatives - Developing a unique value added product in each ward - Development of niche products |
| Growth of MSMEs | Development of a vibrant micro and small enterprise sector | - Resource mobilization - Provide right infrastructure - Developing an SME Park - Undertake research on existing opportunities - Capacity building and training in entrepreneurship - Enhance skill and technological development - Setting aside land for micro and small enterprise activities - Establish technology and business incubators and strengthening of CIDCs - Establish strengthen existing Micro and Small Enterprise Fund - Construction of Jua Kali sheds in major towns of the County. - Promotion of cottage industries |
| Establishment of Modern markets | Establishment and development of markets | - Refurbishment of existing markets - Establishment of social amenities within the markets - Starting of new markets at designated places - Construction of BodaBoda Sheds - Establishment of special markets |
| Investments in the Enterprise and Cooperative sectors | Providing an enabling environment for the accelerated growth of a dynamic, modern and progressive Cooperative sector in the County | - Sensitize the community on the importance of investments in Enterprise and Cooperatives sectors - Capacity building and training - Reviving the dormant cooperative societies and industries |
| Mobilization of savings and investments | Promote and encourage a saving culture | Sensitizations on saving mobilization and investments Exchange Programmes |
| Market research and innovation | Promote research and Development | - Create strong partnerships with research institutions - Offer incentives for research and development - Reward creativity and innovation - Create innovation centres - Documentation of new innovations and research findings - Link industries with research institutions |
| Capacity for quality service delivery | To enhance capacity for quality service delivery | - Prepare and implement service charters - Establish customer care desk - Customer satisfaction surveys - Conducive working environment - Provide necessary tools and equipment - Motivate staff - Matching responsibilities to skills - Good governance - Institutional capacity building - Continuous training |
| Conformity to standards and quality infrastructure | Promote Fair Trade practices and consumer protection | - Anti-counterfeit laws - Strengthen quality assurance institutions - Verification of weighing and measuring instruments - Pre-package control in factories, warehouses and along the distribution chain - Awareness creation, enforcement of legal metrology Act - Enhance protection of intellectual rights - Enhance conformity |
| Enhancing productivity and competitiveness | Enhance productivity and competitiveness | - Human resource development - Review tax regimes - Use of modern technology - Develop a local competitiveness program - Address under-utilization of installed capacity |
| Creating favourable business environment for the private sector growth and competitiveness | Promote private sector development through enterprise development | - Incentives - Conducive environment - PSDS for the County |
| Development of tourism products | Development and Promotion of tourism in the County | - Mapping of tourism attractions and activities - Product development and Diversification - Marketing of tourism products - identifying the niche products within the county - protect natural resources - promotion of cultural and historical heritage - encourage investments in the tourism sector |
| Staff motivation | Development of effective staff motivational structures | - Developing of policies on staff motivation - Carrying out a Training Needs Assessment and an implementation of the same - Developing and full implementation of proper schemes of service - Staff involvement in decision making in matters affecting the department. |

Description of significant capital and non-capital development

The sector has partnered with development partner; World Bank to construct modern markets with modern social amenities. The markets include Kihara market, Kikuyu market, Ruiru market and Juja markets. Estimated project costs for these markets are Kes. 800 million

Key stakeholders

To achieve its objectives, the sector receives a lot of support from many stakeholders as shown in table below. These are either internal or external customers whose involvement is central in the formulation of policies, implementation, monitoring and evaluation of Programmes and projects as well as promotion and development of the sector. They range from public sector institutions, private sector, learning institutions, Business Associations, Regional Trading Blocs and Development Partners.

Key Stakeholders analysis

| Stakeholder | Stakeholders expectations | Sector expectation |
| --- | --- | --- |
| The Governor | - To realign ourselves with the Governors manifesto - To implement the enacted laws | - To provide the general leadership and political goodwill - To assent to bills. - To release the Executive Orders that give Department’s Mandates and core functions |
| The County Treasury | - To ensure efficient utilization of resources - Ensure proper budget reports are handed over in time - Ensure proper utilization and maintenance of resources | - To provide guideline and leadership in the budget making process - Releases finances as per budget and in time - Resource mobilization. |
| Different Ministries and Departments at the National Government and | - To ensure there is collaboration of policies - To ensure there is a linkages to the government programmes and projects | - To formulate policy and generation of national development agenda - Ensure implementation of Government Programmes and projects - To monitor and evaluate of Programmes and projects - To Provide the public with security, enabling legal and regulatory frameworks (Police service, Judiciary and AG’s Office) - Ensure mobilization of resources. |
| Departments at the County Government | - To offer collaboration and synergy - Ensure easy access to information and proper storage of available data - Ensure the data collected is correct and fairly done | - To offer collaboration and synergy - To assist in data collection, collation, analysis, storage and dissemination - Ensure provision of technical, managerial & entrepreneurship training |
| Parastatal & Institutions KEBS, KEPHIS, NEMA, KIPI, KITI, ICDC, EPZA, KIE, KENINVEST, PORTLAND CEMENT, KENAS, KIRDI, KWAL, IDB KARI, KTB, TFC, TRA, KUC, CAK | - To ensure standards and regulations are strictly adhered to. - To utilize information provided to increase competency. - Ensure adoption of technologies | - To set standards and regulations - Ensure verification of goods for conformity - To provide Information - To keeps up to date with the latest technologies |
| Technical Institutions like KIST, JKUAT, MKU, UMMA, ZETEC, Thika Technical, Thika, Kabete Technical, TIBs | To implement recommendations from research | - To offer Technical Research & Development - To offer Policy research - To fund research activities - Ensure technology transfer - To promote Innovations - To offer assistance in Research. |
| General Public | - Offer a conducive environment for the entrepreneurs. - Ensure timely implementation of programmes and projects | - To Participate in consultative forums - To Owner and be the beneficiaries of the Programmes and projects |
| Financial Institutions Banks, MFIs, SACCOs, Table Banking, KUSCCO, CIC, CAK, KCCE, KPCU, KERRUSO | - To ensure efficient utilization of resources - Advice the relevant sectors accordingly - To offer training and financial services | - To provide financial assistance. - To provide advisory services - To provide data on financial sector |

Capital and Non-Capital Projects

Capital projects for the sector will focus on ensuring enabling environment for investors and tourists. These will entail; local market development, promotion of export market, enterprise and industrial development, co-operation development and research, tourism promotion and marketing as well as enactment of supporting legislations. Non capital expenditure will incorporates emolument of staffs as well as administration expenses in the department.

Table 62: Trade, Tourism, Industry and Co-operative ousing capital projects for the 2018/19FY

| Programme: Trade Development and Promotion |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Sub Programme | Project name Location (Ward/Sub county/ county wide) | Description of activities | Green Economy consideration | Estimated cost (Ksh.) | Source of funds | Time frame | Performance indicators | Targets | status | Implementing Agency |
| Local market Development | Markets across the county | Construction of markets |  | 60M | CGK/ development partners / Treasury Grants | 2018/19 | No. of Markets constructed/ Renovated/ Rehabilitated | 15 | ongoing | Trade |
|  | Modern Stalls across major town | Construction of modern stalls |  | 3 M | CGK | 2018/19 | No of modern stalls | 25 | new |  |
|  | Bodaboda sheds across all wards | Construction of bodaboda sheds |  | 30 M | CGK | 2018/19 | Number of BodaBoda sheds constructed | 60 | ongoing |  |
|  | Shoe shiner Kiosk is /cobbler | Construction of shoe shiner |  | 0.5 M | CGK | 2018/19 | No. of shoe shiners sheds constructed | 2 | new |  |
| County Trade and Exports Market Development | Trade fairs/exhibitions | Attending trade fairs / Exhibitions |  | 12 M | CGK | 2018/19 | Number of Trade fair / exhibitions attended / done | 3 | new | trade |
|  | Trade database | Creation of Trade database |  | 10M |  |  | Number of Information Database in place | 1 | new |  |
| Competition Policy and Consumer Protection | Weight and Measures workshop | Construction of weight and measures workshop |  | 15M | CGK | 2018/19 | No of Workshops constructed | 1 | new | trade |
|  | Consumer awareness creation |  |  | 8M |  |  |  |  | ongoing | trade |
| Regulations | market policy, Market Act, PPP Policy, Investment Policy | Enactment of relevant legislations; market policy, Market Act, PPP Policy, Investment Policy |  | 16 M | CGK | 2018/19 | Number of legislations in place | 3 | ongoing | trade |
| Total |  |  |  | 154.5M |  |  |  |  |  |  |

| Programme Name; Enterprise Development and Promotion |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Sub Programme | Project name Location (Ward/Sub county/ county wide) | Description of activities | Green Economy consideration | Estimated cost (Ksh.) | Source of funds | Time frame | Performance indicators | Targets | status | Implementing Agency |
| Industrial Development and Investment Promotion | Industrial parks | Facilitation of establishment of an industrial parks |  | 5M | CGK | 2018/19 | No, of industrial parks established | 1 | new | Enterprise |
|  | Local and international exhibitions/ expo/ forums | Attendance of Industrial exhibitions/ expo/ forums |  | 6M | CGK | 2018/19 | No. of exhibitions /expo/forums undertaken | 2 | ogoing |  |
|  | Incubation / start – up development centres | Creation of Incubation / start – up development centres |  | 7M | CGK | 2018/19 | No of Incubation / start – up development centres created | 1 | new |  |
|  | SME Data base | Establishment of SME Data base |  | 5M | CGK | 2018/19 | No of SME database created | 1 | new |  |
|  | Branding of new directorates | Marketing and Branding of new directorates |  | 4M | CGK | 2018/19 | No of Branding done | 1 | new |  |
| Capacity Building | MSMEs across the County | Promotion of entrepreneurship and Innovation among the MSMEs |  | 4M | CGK | 2018/19 | No of MSMEs trained | 90 | new |  |
|  | Kiambu County Biashara Sacco | Establishment of Kiambu County Biashara Sacco |  | 10M | CGK | 2018/19 | Establishment of Kiambu Biashara Sacco | 1 | new |  |
|  | Circular Economy | To facilitate a circular economy Maximize on product use & reuse |  | 6M | CGK | 2018/19 | Number of circular economies created | 1 | new |  |
|  | Promotion of value addition in MSMES | Enhancement of value chain |  | 12M | CGK | 2018/19 | No of value addition in MSMES | 1 | new |  |
|  | Training and mentorship programme | Training and mentorship on startup businesses |  | 5M | CGK | 2018/19 | No of trainings and mentorship on startup businesses | 1 | new |  |
| Infrastructural Development | Juakali sheds | Promotion of Establishment of Juakali sheds |  | 12M | CGK | 2018/19 | No of Juakali sheds constructed | 12 | ongoing |  |
| Total |  |  |  | 76M |  |  |  |  |  |  |

| Co-operative Development and Management |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Sub Programme | Project name Location (Ward/Sub county/ county wide) | Description of activities | Green Economy consideration | Estimated cost (Ksh.) | Source of funds | Time frame | Performance indicators | Targets | status | Implementing Agency |
| Co-operative development | Capacity building | Carring out capacity building on Cooperatives |  | 9M | CGK | 2018/19 | No. of cooperatives management members trained / educated | 200 | Ongoing | Co-operative |
|  | central County Coffee warehouse | Construction of a central County Coffee warehouse |  | 20M | CGK | 2018/19 | No. of warehouse created | 1 | New | Co-operative |
|  | Coffee parchment milling machines | Purchase of Coffee parchment milling machines to be installed at Komothai area |  | 500M | CGK | 2018/19 | No. of Machines purchased | 1 | new | Co-operative |
|  | Milk collection centres | Construction of milk collection centres for cooperative |  | 7M | CGK | 2018/19 | No. of Milk collection centers constructed | 16 | new | Co-operative |
|  | Co-operatevs revolving fund | Creation of Co-operatives revolving fund |  | 300M | CGK | 2018/19 | No of revolving fund in place | 1 | new | Co-operative |
| Cooperative Society, Research and Advisory | Digitalization of cooperatives | Digitalization of cooperative activities |  | 5M | CGK | 2018/19 | No. Digitalized system in place | 1 | new | Co-operative |
| Total |  |  |  | 841M |  |  |  |  |  |  |

| Tourism Development and Promotion |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Sub Programme | Project name Location (Ward/Sub county/ county wide) | Description of activities | Green Economy consideration | Estimated cost (Ksh.) | Source of funds | Time frame | Performance indicators | Targets | status | Implementing Agency |
| Tourism expo/events/ forums/ | Local and international | Carrying out Tourism expo/events/ forums |  | 20M | CGK | 2018/19 | Number of tourism expo / events done | 4 | new | Tourism |
| Mapping and Profiling | Across the county | Mapping, Inventory and profiling of tourist sites |  | 25M | CGK | 2018/19 | Existence of a mapping and profiling report | 1 | new |  |
| Tourism Infrastructure Development | Across the county | Construction/rehabilitation/landscaping and development of tourist sites across the county |  | 250M | CGK | 2018/19 | Number of tourist sites rehabilitated/ landscaped/ developed | 6 | ongoing |  |
| Legislation |  | Enactment of Tourism Policy, Bills, Acts and Regulations |  | 10M | CGK | 2018/19 | number of legal instruments in place | 1 | ongoing |  |
| Improvement of Local heritage sites | Across the County | To facilitate preservation and gazettement of local heritage sites |  | 5M | CGK | 2018/19 | Number of sites preserved / local heritage sites gazette | 5 |  |  |
| Total |  |  |  | 310 |  |  |  |  |  |  |

Table 63: Trade, Tourism, Industry and Co-operative ousing Non-Capital Projects FY 2018/19

|  | Programme Name; Administration, Planning and Support Services |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Sub Programme | Project name Location (Ward/Sub county/ county wide) | Description of activities | Green Economy consideration | Estimated cost (Ksh.) | Source of funds | Time frame | Performance indicators | Targets | status | Implementing Agency |
| Administration Services | Improved performance in service delivery |  |  | 63.1M | CGK | 2018/2019 | Number of offices supported | 20 |  |  |
|  | Purchase of 6 Vehicles | Acquisition of 4*4 double cabin for enterprise development directorate | Efficient delivery of directorate | 42M | CGK | 2018/2019 | No of vehicles purchased | 6 |  |  |
| Personnel Services |  |  |  | 56.5M | CGK | 2018/2019 | Personnel Emolument supported | 64 |  |  |
| Total |  |  |  | 161.6M |  |  |  |  |  |  |

Cross-sectoral Implementation Considerations

The programmes and projects within the sector cross cut and affect the performance and output of other sectors through forward and backward linkages. The linkages are explained in the table below;

| Programme Name | Sector | Cross-sector Impact |  | Mitigation Measures |
| --- | --- | --- | --- | --- |
|  |  | Synergies | Adverse impact |  |
| Trade promotion and Development | Agriculture | Creation of markets for agricultural produce |  |  |
| Tourism Promotion and Development | Agriculture Education | Creation of markets for agricultural produce | Erosion of existing positive African culture |  |
| Enterprise Development | Education (TVETs) Environment | Provision of technical skills to MSMEs | Pollution from industrial development | Working together with Environment department to ensure relevant bylaws are adhered too. |
| Co-operative Development | Finance Land and Housing | Support financial deepening in the county Support the 4th National Agenda of Affordable Housing |  |  |

### 3.2.13 Roads, Transport and Public Works

The Roads, Transport, Public Works & Utilities Department aspire to develop, operate and maintain an efficient, cost effective, safe and integrated transport system in Kiambu County, in order to achieve County, National and international development objectives in a socially, economically and environmentally sustainable manner. The department is guided by it principles in its undertakings which are; Value for money, Continuous improvement and Equitable distribution resources and it adheres to the following core values; Professionalism, Integrity, Focus, Excellence, Team Work.

Vision

A regional leader in quality, sustainable and environmental friendly infrastructural development

Mission

To provide and regulate quality technical service in Roads, Transport Public Works, Fire & Rescue and Energy

Composition and Mandate

The department has three Directorates with mandates are as outlined here below;

- County Roads & Transport Directorate;

Planning, development and maintenance of County roads and transport infrastructure. Management of public transport, parking bus parks.

- County Public Works Directorate:

Planning Development and maintenance of all County public works buildings and other installation.

- County Utilities Directorate:

County lighting and promotion of renewable energy. Fire prevention, emergency response, public sensitization and disaster response.

Development Goals and Targets

- To ensure the county is well connected with an efficient, safe and reliable all weather road network and Busparks.

- To provide safe, clean energy lighting and fire, disaster and emergency response in the  county

- To provide and maintain safe, healthy and efficient green buildings, civil works and rural footbridges

Infrastructure Development needs, Priorities and Strategies

| Development needs | Priority | Strategies |
| --- | --- | --- |
| Poor maintenance of Roads, Non-motorised Tracks, bridges and Busparks | Maintain infrastructure to avoid huge costs in reconstruction | - Boresha barabara |
| Quality control | -Maintain drainage of all constructed roads and keep the road camber off storm water -Rehabilitate fair surface roads to motorable state | - Effective supervision and laboratory test for materials in use - Maintenance of road drains |
| Poor connectivity of road network | -To facilitate designs and construction of roads, Non motorized Traffic, storm water drains | - Labour based works to be introduced - Rehabilitating the already done projects - Opening up of new access roads |
| Congestion | To facilitate designs and construction of missing links to ease congestion | - Provision of ample parking by construction of busparks, busbays and bypasses in CBDs. |
| Security | Street lighting urban and shopping centres and highmast in densely populated areas | - Installation of flood masts and streetlights - Use of alternative sources of energy to expand the coverage |

Stakeholders Analysis

| Stakeholders Categories | Stakeholder Expectations | Sector Expectations |
| --- | --- | --- |
| Line Departments | - Provision and sharing of necessary information - Interdepartmental relationship driving towards achieving the sector mandate | - Interdepartmental relationship driving towards achieving the sector mandate |
| Development Partners | - Sharing of information - Sharing of workplans - Proper management of the provided resources and proper reporting | - Support the Government to deliver its mandate to the residents - Share challenges in implementations and how to curb them - Sharing a reporting template for proper monitoring and sharing of information |
| Beneficiaries | - Sharing of information - Service delivery with value for money | - Sharing of information - Share challenges - Give priority projects and programme to facilitate proper planning |

Capital and Non Capital Projects

Table 64: Roads, Transport and Public Works ousing capital projects for the 2018/19FY

| Programme Name: P1;Administration, Planning and Support Services |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Objective: To facilitate efficient service delivery by the Department |  |  |  |  |  |  |  |  |  |  |
| Outcome: Improved service delivery and staff motivation |  |  |  |  |  |  |  |  |  |  |
| Sub Programme | Description of Activities | Project Name/ Location(Ward/ Sub County) | Green Economy consideration | Estimated cost (Kshs.) | Source of funds | Time Frame | Key performance Indicators | Planned Targets | Status | Implementation Agency |
| SP 1.1 Administration Services | Development of service charter (County) | Development of service charter (County) | N/A | 100M | CGK | 1 year | Number of service charter developed | 1 | Ongoing | CGK |
|  | Construction of office block | Construction of office block | Green building | 15M | CGK | 1Year | Number of office block constructed | 1 | Designs to start | CGK |
| SP 1.2 Personnel Services | Staff recruitment | Staff recruitment | N/A | 1M | CGK | 1 year | No. of staff recruited | 4 | Ongoing | CGK |
|  | Staff training | Staff training | N/A | 4M | CGK | 1 year | No. of staff Trained | 50 | Ongoing | CGK |
|  | Performance appraisal | Performance appraisal | N/A | N/A | CGK | 1 Year | Performance reviews and contracts | 259 | Ongoing | CGK |
| SP 1.3 Finance Services | Acquisition of machineries; Excavator, Roller, Trucks | Acquisition of machineries; Excavator, Roller, Trucks | N/A | 100M | CGK | 1Year | No. of Excavators acquired Rollers Trucks Manlift | 1 1 3 2 | Ongoing | CGK |

| Programme Name: P2;Public works and Infrastructure maintenance |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Objective:To develop quality, reliable, sustainable and resilient infrastructure, to support economic development |  |  |  |  |  |  |  |  |  |  |
| Outcome: Improved connectivity and accessibility |  |  |  |  |  |  |  |  |  |  |
| Sub Programme | Description of Activities | Project Name/ Location(Ward/ Sub County) | Green Economy consideration | Estimated cost (Kshs.) | Source of funds | Time Frame | Key performance Indicators | Planned Targets | Status | Implementation Agency |
| SP 2.1 Maintenance of County Roads and Bridges (Boreshabarabara) -Roads -Bridges -Non Motorised Traffic -Busparks | Maintenance of roads | Maintenance of county roads are not motorable | Protection of erosion through planting of grass/ gabions | 450M | CGK | 1 year | No. of Kilometers of roads maintained | 300 | Ongoing | CGK |
|  | Maintenance of bridges | Maintenance of bridges | Protection of erosion through gabions | 6M | CGK | 1Year | No. of bridges maintained | 2 | Ongoing | CGK |
|  | Maintenance of Non motorised Traffic | Maintenance of Non motorised Traffic | Protection of erosion through planting of grass and trees | 2M | CGK | 1year | No. of Kilometers of Non MotorisedTraffic maintained | 10KM | Designs ongoing | CGK |
|  | Maintenance of Busparks | Maintenance of Busparks |  | 6M | CGK | 1Year | No. of Busparks maintained | 2 | Ongoing | CGK |
|  | Maintenance of Storm water drain | Maintenance of Storm water drain | Protection of erosion by planting of grass and trees | 2M | CGK | 1 Year | No. of Kilometers of Storm water drains maintained | 2 | Ongoing | CGK |
| SP 2.2 Rehabilitation of county roads, bridges and -Busparks -Roads Busparks | Rehabilitation of roads | Rehabilitation of county roads to motorable |  | 650M | CGK | 1 Year | No. of Kilometers of roads rehabilitated | 260 | Ongoing | CGK |
|  | Rehabilitation of Busparks | 10No. Busparks in the county |  | 4M | CGK | 1Year | No. of Busparks rehabilitated | 12 | Ongoing | CGK |

| Programme Name: P3: Roads Transport |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Objective:To develop quality, reliable, sustainable and resilient infrastructure to support economic development |  |  |  |  |  |  |  |  |  |  |
| Outcome: Improved roads connectivity and accessibility |  |  |  |  |  |  |  |  |  |  |
| Sub Programme | Description of Activities | Project Name/ Location(Ward/ Sub County) | Green Economy consideration | Estimated cost (Kshs.) | Source of funds | Time Frame | Key performance Indicators | Planned Targets | Status | Implementation Agency |
| SP 3.1 Design and Construction of County Roads and Bridges | Design and Construction of County Roads | Improvement to bitumen standards | Planting of trees/ gabion erection | 750M | CGK | 1 year | No. of Kilometers of roads designed and contracted | 25km | Ongoing | CGK |
|  | Design and Construction of Bridges | Design and Construction of Bridges | gabion erection | 60M | CGK | 1 Year | No. of bridges designed and contracted | 2No. | Ongoing | CGK |
|  | Design and Construction of Non Motorised Traffic | Design and Construction of Non Motorised Traffic | Planting of trees/ grass | 40M | CGK | 1 Year | No. of Kilometers Non motorised Traffic designed and contructed | 10KM | Ongoing | CGK |
|  | Design and Construction ofBuspark | Design and Construction ofBuspark | Planting of trees | 60M | CGK | 1year | No. of Busparks designed and contracted | 2 No. | Ongoing | CGK |

| Programme Name: P4;Energy, Disaster Management, Fire, Safety and Rescue |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Objective: Improved security and safety of people and property |  |  |  |  |  |  |  |  |  |  |
| Outcome: Promote 24 hour economy and attraction of investors |  |  |  |  |  |  |  |  |  |  |
| Sub Programme | Description of Activities | Project Name/ Location(Ward/ Sub County) | Green Economy consideration | Estimated cost (Kshs.) | Source of funds | Time Frame | Key performance Indicators | Planned Targets | Status | Implementation Agency |
| SP 4.1 Electricity Distribution | Installation of Streetlights | Installation of Streetlights | Use of alternative energy | 30M | CGK | 1Year | No. of Streetlights installed | 300 | Ongoing | CGK |
|  | Installation of | Installation of | Use of alternative energy | 100M | CGK | 1Year | No. of Flood masts Installed | 60 | Ongoing | CGK |
| SP 4.2 Fire, Safety and Rescue -Construction and Rehabilitation of Fire stations -Equipping of Fire stations and academy | Construction and Rehabilitation of Fire stations | Construction and Rehabilitation of Fire stations | Use of alternative energy | 48M | CGK | 1 Year | No. of Fire stations constructed and rehabilitated | 4 | Ongoing | CGK |
|  | Equipping of Fire stations and academy | Equipping of Fire stations and academy |  | 9M | CGK | 1Year | No. of Academy and fire stations equipped | 2 | Ongoing | CGK |
| SP 4.3 Disaster Management Trainings | Increased disaster awareness | Staff trained | N/A | 1M | CGK | 1Year | No. of staff trained | 50 | Ongoing | CGK |

Cross-Sectoral Implementation Considerations

| Programme Name | Sector | Cross-sector Impact |  | Measures to Harness or Mitigate the Impact |
| --- | --- | --- | --- | --- |
|  |  | Synergies | Adverse impact |  |
| Public works and Infrastructure maintenance | Roads - All departments | Facilitate Designs and construction supervision of public facilities |  | Consultative forums to ensure delivery of the focus target |
| Roads Transport | Roads - Trade | Facilitate trade by enhancing accessibility | Heavy commercial trucks overload roads designed for light traffic | - Multisectoral approach in prioritizing infrastructure developments. - Designate particular roads particularly designed for heavy traffic to minimize Maintenance costs on roads |
|  | Roads -Agriculture | Facilitate Agriculture by enhancing accessibility |  | Multisectoral approach in prioritizing infrastructure developments. |
| Energy, Disaster Management, Fire, Safety and Rescue Programme | Roads- Administration | Enhancing security by provision of flood masts |  | Identification of priority area to provide lighting |
|  | Roads-Trade | - By enhancing security business can run for 24hours - Safety of businesses enables conducive environment |  | Linking up/consulting with the stakeholders in identification of areas that needs lighting |

### 3.2.14 Livestock, Fisheries and Marketing

Sector composition

The sector comprises of three directorates namely

- Livestock production,

- Veterinary services,

- Fisheries development

- Marketing.

Vision

A Healthy, Food secure and Prosperous County

Mission

To promote food security through capacity building on livestock and fishery productivity, availing of safe food of animal origin, value addition, marketing, extension and infrastructural development.

Sector goal

- To create a favourable framework for sustainable development of the livestock, fisheries sector and provide support services that increase productivity, value addition and market access for the sector products

- To provide sustainable livelihoods, household food and nutritional security to families while contributing to socio economic development of Kiambu County.

General information

Livestock

Dairy industry is the leading enterprise with nearly 70% of the farm families keeping an average of 2-3 cows under zero grazing systems. Milk is the major livestock product in Kiambu county and currently leading in Kenya. Production has increased from 264,773,621 litres in 2013 to 308,818,919 litres in 2016. In order to facilitate milk value addition, eleven bulk milk coolers with a cumulative capacity of 39,000 litres have been procured and issued to farmer dairies including Muguga, Kiriita, Mangu, Karatu, Gatamaiyu, Ndumberi,  Bibirioni, Githiga and Ngewa. Two pasteurizers procured; one of 5000 litres installed in Muguga and another of 5000 litres per hour capacity for Kiambaa.

Poultry and pig keeping continue to take precedence after dairy farming. Egg production and pig production is the second, more so, in income generation. According to 2017 data provided by the department of Agriculture, Livestock and Fisheries Kiambu County, the numbers of livestock in the county were as follows: 247,706 cattle, 139605 Sheep, 102366 goats, 2,550,523 poultry, 52588 pigs and 10227 donkeys. Agro-processing industries in the County include Brookside Dairies, Githunguri Dairies, Ndumberi Dairies, Limuru Milk and Palmside Dairies and local food processing factories such as Farmers Choice Ltd and Kenchic Co. Ltd. The county has 216 Communal cattle dips, out of which 7 are functional and 209 are non-functional.The presence of Wangige wholesale market and Gitaru market for eggs; and Ndumbu-ini slaughter house for pigs continue to provide market outlet that favour the enterprises.

Fisheries

The main fish species farmed in the county is Tilapia and cat fish which are warm water species. Recreational fishery (sport fishing) is practiced mainly in Gatamaiyu fishing camp in Lari Sub County. The county has potential for cold water fish e.g. trout in Lari sub county.

Apiculture (bee keeping)

Apiculture (bee keeping; )Having known the importance of honey to human health, adoption of bee keeping in the county has gradually increased leading to an increase in the Kgs of honey produced as well as the farmers’ income. Beekeeping is scattered in the county and most farmers use Langsroth hives, Top Bar Hive and Log Hives. The production of honey has risen from 102,397 Kgs of honey produced in 2014 to 114,000 Kgs in 2017. The value of honey in Kshs has also increased from Kshs 51.2 Million in 2014 to 56 Million shillings in 2017.

Development needs, Priorities and Strategies

| Development Need | Priority | Strategy |
| --- | --- | --- |
| Extension services | Provide quality and efficient technical services to farmers across the County | - E-extension - Village Based Advisory services - New innovative technologies - Field days/ farmer field schools/farmer groups/ demonstrations/ shows and exhibitions/ symposium/ |
| Accessible, quality and affordable inputs | sexed semen, quality livestock breeds, fingerlings, fingerlings, herbicides and pesticides. | - Smart Subsidy programmes - Appropriateness of inputs - Agricultural inputs fund - Quality regulation-animal feed law - Input distribution system |
| Marketing | Livestocks and fisheries products | Infrastructure and information development - collection centers - organized marketing system - value addition - Real time market information platforms - Information Resource Centres |
| Processing |  | - Leather industry - Animal feeds - Dairy |
| Reduce post-harvest losses | livestock and fisheries products | - Cold storage chains |
| Animal pests and Diseases | livestock and fisheries | Disease surveillance and control - Vaccination - Livestock movement control - Meat inspection - cattle dips |
| Research | Livestock and fisheries research | - Research liaison meetings - Linkage with research institutions - Research agenda setting - Lobby for representation in research institutions |

Stakeholder Analysis

| Stakeholders | Needs of the stakeholder from the sector | Sector expectations from the stakeholder |
| --- | --- | --- |
| Farmers | - Extension services and capacity building services - Subsidized (quality inputs) - Affordable Credit - Good infrastructure - Reliable markets for produce | - Quality production - Adherence to safety standards & - MRLs(maximum residue levels) |
| Farmer Organizations | - Stimulating market demands - Extension information - Enabling policy and legal framework | - Marketing - Lending - Quality inputs at affordable rates i.e. through their bargaining power - Capacity building (extension services) on value addition - Bulking of produce |
| Consumers | - Availability of products - Quality &quantity products - Good prices - Clean accessible markets | - Demand quality & safe products |
| Regulators (KEPHIS, Kenya Vet Board, PCPB, KDB, KEBS, WRMA, NEMA, WHO, FAO, OIE, MOH etc.) | - Compliance to the set standards - Political good will - Food policies & effective policy implementation structures - Financing/funding - Sufficient human resource | - Ensure only quality products get to the market - Enforcing compliance to the set standards |
| County Government | - Political goodwill from the national government, CSOs, farmers - Compliance to tax remissions - Funding - Cooperation & support from the County Assembly, private partners/NGOs | - Develop &implement policies - Provide sufficient extension services - Facilitate capacity building of the staff |
| Veterinary Directorate | - Disease control including notifiable diseases - Advisory services on animal health - Regulatory role, information dissemination of research findings, identification of farmers needs | - Resources: transport, equipment, vaccines, good remuneration/facilitation - More human resource - Adherence to vaccination regimes by farmers |
| Private Agricultural Health Service Providers | - Clinical Service - AI - Extension/ Advisor services on animal health | - Enabling policy environment - Resources: transport, equipment, vaccines, good remuneration/facilitation - More human resource |
| County Department of Agriculture | - Animal husbandry training - Dairy Cow - Dairy Goat - Pig - Beekeeping - Hair Goat - Meat Goat - Sheep - Poultry - Emerging livestock: Donkey, guinea fowl, guinea pig, quail, - Marketing support, regulatory role, information dissemination, identification of farmers needs - Compliance and regulation | - Resources: transport, equipment, vaccines, good remuneration/facilitation - More human resource |
| Fisheries Directories | Aquaculture training, identification of farmers needs | - Resources: transport, equipment, vaccines, good remuneration/facilitation - More human resource |
| Agrochemical service providers | - Production and production of the products. - Training on use of inputs, agrochemical production, provision of agro-chemicals, research, identification of farmers’ needs | - Supportive policy framework - Security |
| Development Partners | Advisory, resource provision | - Supportive policy framework - Security - Political good will |
| Media | - Market information - SPs information - Advisory - Activism | - Supportive policy framework - Political good will |
| Financial Partners | Financing agriculture interventions | Supportive business environment |
| Lobby Groups |  | Supportive policy framework |
| Civil Society organisations | - Marketing - Advisory - Inputs provision - Quality Assurance – DFCS - Extension services | - Supportive policy framework - Political good will - Empowerment on governance issues |
| Kiambu Veterinary Society |  |  |
| Agriculture/ Dairy Processors | - Markets, extension and storage services - Value addition - Competitive prices | Quality products from farmers |
| Certification Bodies | - Good governance - Ensures compliance | Cooperation and observation to the standards |
| Training and Research Institutions e.g.; ACADEMIA ILRI | - Research and dissemination - New technologies, breeds, varieties, documentation, consultancy - Training of human resources | - Resources: human and financial; recognition, strong linkage with extension SPs, incubation centres - Supportive policy framework - Political good will |
| Agro-industries | - Manufacture and marketing agriculture products and by-products - Supply of inputs | - Good Infrastructure - Supportive policy framework - Political good will - Quality and adequate input - Financing - Security |
| County Assembly | - Policy approval and amendment - Budget approval and amendment - Oversight role of CG - Constituents representation | - Resources – financial and skilled human resource - Information on context, proposed projects and budgets |
| National Gov. | - Policy Making - Resources - Capacity building - Infrastructure development - Security provision - Promotion and regulation of International trade - Oversight of CG - Representation of the CG - Domestication of international obligations – treaty - Promote national cohesion - Promote inter-county trade - Arbitration of inter-county | - Collaboration and goodwill from CG - County information on the sector - Revenue |

Capital and Non-Capital Projects

This section provide a summary of the capital and non-capital projects to be implemented during the plan period. Details of the projects are presented in table below.

Table 65: Livestock, Fisheries & Marketing ousing capital projects for the 2018/19FY

| Programme name; Fisheries Development And Management Objective; To Increase Fisheries Productivity Outcome; Increased Fisheries Production And Utilization |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Sub Programme | Project name Location (Ward/Sub county/ county wide) | Description of activities | Green Economy consideration | Estimated cost (Ksh.) | Source of funds | Time frame | Performance indication | Targets | status | Implementing Agency |
| Fisheries Policy, Strategy and Capacity Building | Farmers trainings on current technologies county wide | Competent officers trained on modern appropriate technologies |  | 2.3M | CGK | 2018/2019 | Number of trainings on current technologies done | 1 |  | Livestock, Fisheries and marketing Dept |
|  | Purchase of aquaculture kits county wide |  |  | 0.6M | CGK | 2018/2019 | Number of aquaculture kits issued | 4 |  | Livestock, Fisheries and marketing Dept |
|  | Training of farmers countywide |  |  | 0.4M | CGK | 2018/2019 | Number of farmer trainings conducted | 36 |  | Livestock, Fisheries and marketing Dept |
|  | Equipping of modern aquaculture technologies to the farmers |  |  | 0.8M | CGK | 2018/2019 | No. of farmers equipped with modern aquaculture technologies | 960 |  | Livestock, Fisheries and marketing Dept |
| Management and Development of Capture fish | Stocking of rivers with fingerlings | Increased capture fisheries productivity |  | 2M | CGK | 2018/2019 | Number of fingerlings stocked in rivers | 200,000 |  | Livestock, Fisheries and marketing Dept |
| Research Application | Farmers and dealers training | Improved Adoption of ornamental and sport fishing (angling) activities |  | 0.1M | CGK | 2018/2019 | Number of farmers and dealers trained on recreational fisheries | 20 |  | Livestock, Fisheries and marketing Dept |
| Market development | fish marketing establishment | establishment of fish marketing outlets,fish farms and issuance of freezers |  | 0.1M | CGK | 2018/2019 | Number of fish marketing outlets established in collaboration with stakeholders | 2 |  | Livestock, Fisheries and marketing Dept |
|  | Freezers issuance |  |  | 0.4M | CGK | 2018/2019 | Number of freezers issued | 4 |  | Livestock, Fisheries and marketing Dept |
|  | Establishment of fish farms |  |  | 0.1M | CGK | 2018/2019 | Number of facilities/farms established | 10 |  | Livestock, Fisheries and marketing Dept |
| Total |  |  |  | 6.8M |  |  |  |  |  |  |

| Programme Name: Livestock Resources Management and Development Objective: To increase livestock productivity Outcome: Increased livestock production and increased income |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Sub Programme | Project name Location (Ward/Sub county/ county wide) | Description of activities | Green Economy consideration | Estimated cost (Ksh.) | Source of funds | Time frame | Performance indication | Targets | status | Implementing Agency |
| Livestock Policy Development and Capacity Building | Policy development and guidelines | Development of policies, guidelines for livestock and fishery production as well as capacity building of staff |  | 0.4M | CGK | 2018/2019 | Number of policies, guidelines and strategies reviewed, developed and rolled out | 1 |  | Livestock, Fisheries and marketing Dept |
|  |  |  |  | 5M | CGK | 2018/2019 | Number of staff whose capacity needs have been addressed | 160 |  | Livestock, Fisheries and marketing Dept |
|  | Dairy farmers training | Training of dairy farmers and provision of A.I. |  | 0.3M | CGK | 2018/2019 | Number of farmers trained | 25000 |  | Livestock, Fisheries and marketing Dept |
|  | Dairy platform establishment per subcounty |  |  | 0.2M | CGK | 2018/2019 | Number of dairy platform & Farmers field school (1 per sub county) | 1 |  | Livestock, Fisheries and marketing Dept |
|  | Subsidized AI |  |  | 20M | CGK | 2018/2019 | Uptake of subsidized AI (no. of doses) | 10,000 |  | Livestock, Fisheries and marketing Dept |
|  | Livestock research | Livestock Research |  | 0.2M | CGK | 2018/2019 | Number of research and Linkages | 1 |  | Livestock, Fisheries and marketing Dept |
|  | Training in each subcounty | Training of pig farmers and provision on of pig A.I. |  | 4M | CGK | 2018/2019 | Number of trainings per sub county per year | 12 |  | Livestock, Fisheries and marketing Dept |
|  | Piggery unit establishment | Construction of a piggery unit |  | 2M | CGK | 2018/2019 | % completion of piggery unit |  |  | Livestock, Fisheries and marketing Dept |
|  | Pig AI |  |  | 5M | CGK | 2018/2019 | Number of pig Artificially Inseminated | 5000 |  | Livestock, Fisheries and marketing Dept |
|  | Entrepreneurial training | Trainining of farmers on enterprenuership and market access |  | 5M | CGK | 2018/2019 | Number of farmers trained on market access and entrepreneurship skills | 100 |  | Livestock, Fisheries and marketing Dept |
|  | Indigenous chicken procurement | Improvement of Poultry production |  | 5M | CGK | 2018/2019 | Number of Indigenous chicken procured and distributed | 20,000 |  | Livestock, Fisheries and marketing Dept |
|  | Poultry unit construction |  |  | 0.4M | CGK | 2018/2019 | % completion of poultry unit | 1 |  | Livestock, Fisheries and marketing Dept |
|  | Farmers training |  |  | 1M | CGK | 2018/2019 | Number of farmers trained per year | 3000 |  | Livestock, Fisheries and marketing Dept |
|  | Value chain actors training | Improve milk resilience to climatic changes |  | 1M | CGK | 2018/2019 | No. of value chain actors trained on Climate Smart technologies | 30000 |  | Livestock, Fisheries and marketing Dept |
|  | Milk Pasteurizers |  |  | 26M | CGK | 2018/2019 | Number of pasteurizers availed to farmers | 3 |  | Livestock, Fisheries and marketing Dept |
|  | Pork factory construction | Construction of a pork factory |  | 1M | CGK | 2018/2019 | % completion of the pork factory | 1 |  | Livestock, Fisheries and marketing Dept |
|  | Farm inspection |  |  | 1M | CGK | 2018/2019 | Number of Stock route, abattoir and farm inspections | 52 |  | Livestock, Fisheries and marketing Dept |
|  | Disease reporting books |  |  | 3M | CGK | 2018/2019 | No. of disease reporting books procured | 300 |  | Livestock, Fisheries and marketing Dept |
|  | FMD Vaccination campaigns | Decreased livestock disease outbreaks |  | 2M | CGK | 2018/2019 | Number of FMD vaccination campaigns done | 3 |  | Livestock, Fisheries and marketing Dept |
|  | LSD vaccination campaigns |  |  | 4M | CGK | 2018/2019 | Number of LSD vaccination campaign done | 1 |  | Livestock, Fisheries and marketing Dept |
|  | Anthrax vaccination campaign |  |  | 9M | CGK | 2018/2019 | Number of Anthrax vaccination campaign done | 2 |  | Livestock, Fisheries and marketing Dept |
|  | Movement permits | Reduced incidences of contagious animal diseases |  | 0.8M | CGK | 2018/2019 | Number of movement permits procured and issued | 500 |  | Livestock, Fisheries and marketing Dept |
|  | Vaccination |  |  | 1.6M | CGK | 2018/2019 | Number of vaccination | 12 |  | Livestock, Fisheries and marketing Dept |
|  | Cattle dip rehabilitation | Reduced incidences of vector borne animal diseases |  |  | CGK | 2018/2019 | Number of rehabilitated dips | 0 |  | Livestock, Fisheries and marketing Dept |
|  | Procument of arcaricide |  |  | 1M | CGK | 2018/2019 | Number of Litres of arcaricide procured | 200 |  | Livestock, Fisheries and marketing Dept |
|  | Vector control trainings |  |  | 1M | CGK | 2018/2019 | Number of trainings of farmers in vector control and arcaricide | 24 |  | Livestock, Fisheries and marketing Dept |
|  | Inseminator licensing | Reduced livestock reproductive diseases |  | 0.1M | CGK | 2018/2019 | Number of Inseminators licensed | 200 |  | Livestock, Fisheries and marketing Dept |
|  | Inseminator licensing |  |  | 1.6M | CGK | 2018/2019 | Number of trainings of inseminators and farmers | 12 |  | Livestock, Fisheries and marketing Dept |
|  | Veterinary staff training | Assurance to Healthy human and livestock |  | 0.4M | CGK | 2018/2019 | No. of trainings of veterinary staff on veterinary drug trade and reports | 12 |  | Livestock, Fisheries and marketing Dept |
| Food Safety and Animal Products Development | Poultry and rabbit slaughter house completion | Ensure safe foods of animal origin |  | 6M | CGK | 2018/2019 | % Completion Thika Poultry and Rabbit slaughter house | 50% |  | Livestock, Fisheries and marketing Dept |
|  |  | Mainstream animal welfare requirements |  | 0.2M | CGK | 2018/2019 | Animal welfare bill developed and rolled out | 20% |  | Livestock, Fisheries and marketing Dept |
|  | Staff and farmers training |  |  | 0.6M | CGK | 2018/2019 | Number of training of staff and farmers on animal welfare issue | 12 |  | Livestock, Fisheries and marketing Dept |
|  | Electricity installation in gatundu slaughter house |  |  | 2M | CGK | 2018/2019 | % completion of the installation | 1 |  | Livestock, Fisheries and marketing Dept |
|  | Meat inspection kits |  |  | 0.4M | CGK | 2018/2019 | Number of Meat inspection kit | 60 |  | Livestock, Fisheries and marketing Dept |
|  | Slaughter house licensing |  |  | 0.6M | CGK | 2018/2019 | Number of Slaughter houses licensed and inspected | 54 |  | Livestock, Fisheries and marketing Dept |
|  | Farmers enlightening |  |  | 0.2M | CGK | 2018/2019 | No of Farmers enlightened on drug residues milk, eggs and meat | 1200 |  | Livestock, Fisheries and marketing Dept |
|  | Leather farmers empowerment | Higher incomes from leather products |  | 1M | CGK | 2018/2019 | No of Farmers empowered with leather products and production technology | 24 |  | Livestock, Fisheries and marketing Dept |
|  | leather production training |  |  | 0.2M | CGK | 2018/2019 | No of flayers and, bandas and tanneries owners trained on proper leather production techniques | 24 |  | Livestock, Fisheries and marketing Dept |
|  |  |  |  | 0.2M | CGK | 2018/2019 | Number. of Inspections of bandas | 12 |  | Livestock, Fisheries and marketing Dept |
| Total |  |  |  | 113.4M |  |  |  |  |  |  |

Table 66: Livestock, Fisheries & Marketing non ousing capital projects for the 2018/19

| Programme Name: Administration, Planning and Support Services Objective: To enhance effective and efficient service delivery Outcome: Enhanced effective and efficient service |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Sub Programme | Project name Location (Ward/Sub county/ county wide) | Description of activities | Green Economy consideration | Estimated cost (Ksh.) | Source of funds | Time frame | Performance indicators | Targets | status | Implementing Agency |
| Administration Services | Office construction in (Kiambaa and Kabete | Construction and equipping of new offices |  | 5M | CGK | 2018/19 | No. of Sub county offices constructed and equipped | 50 percent completion | New | LiFiVe |
|  | County wide Extension services | Extension services |  | 1M | CGK | 2018/19 | No. of Farmers reached with extension services | 10,000 farmers | On going | LiFiVe |
|  |  | Procurement of vehicles |  | 9M | CGK | 2018/19 | No. of vehicles procured and issued to Subcounties | 3 vehicles | New | LiFiVe |
| Personnel Services | Capacity building | Staff training |  | 1M | CGK | 2018/19 | No. of Staff undertaking promotional and refresher courses | 100 officers trained | On going | LiFiVe |
| Support Services | Staff enhancement | Personal emoluments |  | 197M | CGK | 2018/19 | Amount in Kshs allocated per personal emoluments |  |  |  |
|  | Office operations | Operation and maintenance |  | 32M | CGK | 2018/19 | Amount allocated operation and maintenance. |  |  |  |
| Total |  |  |  | 245M |  |  |  |  |  |  |

Cross-sectoral Implementation Considerations

| Programme Name | Sector | Cross-sector Impact |  | Measures to Harness or Mitigate the Impact |
| --- | --- | --- | --- | --- |
|  |  | Synergies | Adverse impact |  |
| Livestock Diseases Management and Control | Land, Housing & Physical Planning Water and Environment | Secure land for livestock development Provision of water for livestock | Encroachment of livestock development land by estate developers Water pollution | - Land use control - Control water pollution |
| Fisheries | Water and Environment Trade and industry, maritime | Well managed and safe water bodies for fish industry Provide better markets for fish | - Water pollution - Environmental pollution | Control water pollution Compliance with NEMA standards |

## 3.3 Payments of Grants, Benefits and Subsidies

This section provides information on proposed payment of Grants, Benefits and Subsidies to be done by the county government during the plan period.

Table 67: Payments of Grants, Benefits and Subsidies

| Type of payment (e.g. Education bursary, biashara fund etc.) | Amount (Ksh.) | Beneficiary | Purpose |
| --- | --- | --- | --- |
| DANIDA | 17,851,856 | Gazetted level 2 and 3 health facilities | Supplement day to day health facilities’ operations |
| Compensation for user fee foregone | 34,671,542 | Gazetted level 2 and 3 health facilities | Supplement day to day health facilities’ operations |
| THS(Transforming Health for Universal care project) | 22,000,000 | Primary Health care | Improve healthcare at community level |
| Conditional grant | 538,716,763 | Thika level 5 | Health Infrastructural Development |
| Facility improvement fund(FIF) | 600,000,000 | All level 4 and 5 Hospitals | Purchase of medicine, drugs and equipment |
| Emergency fund | 35,000,000 | Disaster victims | Disaster response |
| Youth, Women and Persons with Disability Fund | 100,000,000 | Youth, Women and Persons with Disability | Empower Youth, Women and PWDs |
| Education Bursary Fund | 190M | Vulnerable students in society | Assist needy students in paying school fees |

# CHAPTER FOUR: RESOURCE ALLOCATION

This section presents a summary of the proposed budget by programme and sector/ sub sector as indicated in table 68 and table 69. The chapter has also provided a description of how the county government is responding to changes in the financial and economic environment.

## 4.0 Resource allocation criteria

The resource allocation for the FY 2018/2019 budget estimates were based on the county priorities as guided by the County Integrated Development Plan 2018-2022, United for Kiambu Manifesto and Big four Agenda. These priorities also took into considerations public priorities which were identified through vigorous and extensive public consultation forums.

## 4.1 Proposed budget by programme

The proposed budget for the programmes is as summarized in table 68.

Table 68: Summary of proposed budget by programme

| Department | Programme | Amount |
| --- | --- | --- |
| County Assembly | General Administration and support services | 1.32B |
|  | Legislative oversight and Oversight Services | 0.03M |
|  | Total | 1.35B |
| Executive | Administration, Planning and Support Services | 211.5M |
|  | Government Advisory Services | 1M |
|  | Leadership and Co-ordination of County Administration and Departments | 6.5M |
|  | Total | 219M |
| County public service board | General Administration and support services | 83.8M |
|  | Total | 83.8M |
| Finance, ICT and Economic Planning | General Administration, Planning And Support Services | 1.361B |
|  | Financial Management Services | 18M |
|  | Economic Planning And Budgetary Services | 34M |
|  | Resource Mobilization And Revenue | 50M |
|  | ICT | 165M |
|  | Total | 1.628B |
| Administration, Public Service and communication | Administration, planning and support services. | 646.2M |
|  | Alcohol, Drugs & substance abuse control and rehabilitation. | 37.2M |
|  | Betting, license and control. | 1.87M |
|  | Public participation and Citizen Petition. | 10.88M |
|  | Human Resource management. | 3.4M |
|  | Communication. | 20.5M |
|  | Total | 720M |
| Agriculture, Crop production , Irrigation and Marketing | Administration, Planning and Support Services | 243M |
|  | Policy strategy and management of Agriculture | 2.2M |
|  | Agribusiness and information management | 51.6M |
|  | Crop Development and Management | 141.4M |
|  | Total | 438.2M |
| Water Environment Energy And Natural Resource | General administration and support services | 276.2M |
|  | Environment management | 295M |
|  | Water provision and management | 194.95M |
|  | Natural resource | 160M |
|  | Renewable energy and Climate change | 20M |
|  | Total | 946.15M |
| Health Services | Administration, Planning and Support services | 5.99B |
|  | Curative Services | 139.4M |
|  | Pharmaceutical Services | 270M |
|  | County Health Policy Development and Management | 407M |
|  | Reproductive Health | 25.2M |
|  | Total | 6.841B |
| Education, Youth, Sports, Culture, & Social Services | General administration and support services | 1.190B |
|  | Pre-primary education ECDE | 430M |
|  | Vocational Training Centers (VTC) - Youth polytechnics | 149.5M |
|  | Social Services | 10M |
|  | Sports | 303M |
|  | Youth empowerment | 124M |
|  | Gender and Culture | 100M |
|  | Total | 2.306B |
| Lands Housing and Physical Planning | County Land Information Management Services | 71.4M |
|  | Planning, Land Survey and Mapping | 260M |
|  | County Urban Planning and Housing | 4.8B |
|  | Administration, Planning and Support Services | 22.8M |
|  | Total | 5.154B |
| Trade, Tourism, Industry & Co-operative | Trade promotion and Development | 154.5M |
|  | Enterprise Development and Promotion | 76M |
|  | Co-operative Development and Promotion | 841M |
|  | Tourism Promotion and Development | 310M |
|  | General Administration and support | 161.6M |
|  | Total | 1.543B |
| Roads, Transport, Public Works and Utilities | Administration, Planning and Support Services | 220M |
|  | Public works and Infrastructure maintenance | 1.112 B |
|  | Roads Transport | 910 M |
|  | Energy, Disaster Management, Fire, Safety and Rescue Programme | 188 M |
|  | Total | 2.43B |
| Livestock, Fisheries and Marketing | General Administration, Planning and support services | 245M |
|  | Fisheries development and management | 6.8M |
|  | Livestock development and management | 113.4M |
|  | Total | 365.37M |

## 4.2 Proposed budget by sector/ sub-sector

The proposed budget for the sector/ sub-sector is as summarized in table 69.

Table 69 : Summary of proposed budget by sector/sub-sector

| Vote No. | Sector/Sub-Sector/Department Name | Amount (Kshs. Billions) | As a percentage (%) of the Total Budget |
| --- | --- | --- | --- |
| 4061 | County Assembly | 1.35 | 5.45 |
| 4062 | County Executive | 0.219 | 0.88 |
| 4063 | County Public Service Board | 0.838 | 3.38 |
| 4064 | Finance, Economic Planning & ICT | 1.628 | 6.58 |
| 4065 | Administration And Public Service | 0.72 | 2.91 |
| 4066 | Agriculture, Crop Production Irrigation And Marketing | 0.438 | 1.77 |
| 4067 | Water Environment Energy And Natural Resource | 0.946 | 3.82 |
| 4068 | Health Services | 6.841 | 27.63 |
| 4069 | Education, Youth, Sports, Culture, & Social Services | 2.306 | 9.31 |
| 4071 | Lands, Physical Planning & Housing | 5.154 | 20.82 |
| 4072 | Trade, Tourism, Co-Operative And Enterprise Development | 1.543 | 6.23 |
| 4073 | Roads, Transport, Public Works And Utilities | 2.43 | 9.82 |
| 4074 | Livestock, Fisheries And Marketing | 0.365 | 1.47 |
|  | Totals | 24.778 | 100 |

## 4.3 Financial and Economic Environment

The County government has allocated more resources to physical infrastructure improvement with the aim to stimulating economic performance while addressing the real issues that affect the lives of the county residents. Further  the  County will  be partnering  with  the National  Government  with a view  to  review  the  revenue sharing formulae to take  into  account the  county government  status.

The county government will further maximize its revenue mobilization by strengthening and reforming revenue administration and collection processes already in place and through re-engineering various ongoing structural reforms.

4.4 Risks, Assumptions and Mitigation measures

Table 70 below provides a summary of the range and types of risk the County anticipates during the course of the implementation of this Annual development plan and how the county intends to mitigate the risks

Table 70: Risks, Assumptions and Mitigation measures

| Risk | Assumption | Mitigation measures |
| --- | --- | --- |
| Under performance in revenue collection |  | Revenue mobilization |
| County’s high wage bill |  | Carry out the recommendations under the CARPs programme and the SRC’s job evaluation exercise |
| Over reliance on national government transfers |  | Increase internal revenues Cost effective measures to reduce expenditure |
| Heightened expectation of the Department to solve all development challenges due to extended mandate |  | Continuous information, dissemination and communication |
| Bureaucracies in procurement procedures which lead to delays and inefficiencies |  | Continuous review and rationalization of public procurement procedures and regulations |
| Weak institutional frameworks at all levels of government making the planning aspect or mandate fairly unpredictable |  | Continuous strengthening of implementing institutions at all levels of government |
| Prevailing social and economic inequalities within individuals and regions in the county |  | Initiate support and profile equity based planning and programme implementation on a continuous and participatory basis |
| Poor flow of information |  | Continuous enhancement of communication channels at all levels of the department |

# CHAPTER FIVE: MONITORING AND EVALUATION

This chapter discusses the county monitoring and evaluation framework as outlined in the County Integrated Monitoring and Evaluation System (CIMES). It focuses on development of the monitoring and evaluation framework for specific projects and programmes for the sectors that will be implemented during the planned period. The chapter also specifies the objectively verifiable indicators that shall be used to monitor projects/programmes implemented by various sectors.

## 5.1 Institutional Framework for Monitoring and Evaluation in Kiambu County

The monitoring and evaluation framework in the county is anchored under the Finance, ICT and Economic Planning department in the county. The County Monitoring and Evaluation Committee (CM&EC) will spearhead monitoring and evaluation at the County level. The committee will be made up of members representing county government agencies, civil society organizations and the private sector. The committee will coordinate monitoring and evaluation activities for all the sectors and government agencies and through the preparation of the Annual Monitoring and Evaluation reports, provide necessary information and feedback to be captured at the national level. This will require training on a continuous basis on monitoring and evaluation At the County level, the monitoring committee will continue to build the capacity of departments and agencies on monitoring and evaluation.

The Monitoring and Evaluation system will take cognizance of the projects and programmes included in the County Integrated Development Plan as well as indicators facilitating the MTEF process, and development aspects in the county. Monitoring will be continuous through the planned period whereas evaluation has been planned at two stages; midterm evaluation and end term evaluation. In addition, there will be annual and quarterly reports at the end of each year to assess the progress made in implementing the plan and provide necessary information and feedback.

## 5.2 Data collection, Analysis and Reporting mechanisms

The monitoring and evaluation committee shall collect raw data through observation, field visits, questionnaires etc. and submit the data to the monitoring unit for analysis. After the analysis, the economic planning unit shall be produce annual reports which shall be disseminated through social media, websites, prints etc. as a feedback mechanism.

## 5.3 Monitoring and Evaluation Performance Indicators

Table 71 gives a summary of the monitoring and evaluation indicators for sector programmes.

Table 71: Summary of M&E Outcome indicators

| Sector | Programme | Outcome indicators | Baseline | Planned target | Achieved target | Remarks |
| --- | --- | --- | --- | --- | --- | --- |
| County assembly | Legislation, Oversight and Representation in the county | % Construction and Completion of structural and infrastructural development projects and utilities |  | 10% |  |  |
|  |  | Personal Emoluments (Amount allocated for personnel emoluments) |  | 465M |  |  |
|  |  | Amount allocated to Operations & Maintenance |  | 735M |  |  |
|  |  | No. of vehicles Purchased |  | 2 |  |  |
|  |  | No. of ward offices constructed and equipped |  | 11 |  |  |
|  |  | No of capacity building forums held |  | 2 |  |  |
|  |  | No. of County Assembly staff Trained, |  | 86 |  |  |
|  |  | No. of Performance appraisals done. |  | 86 |  |  |
|  |  | Number of legislations/ bills processed and passed |  | 15 |  |  |
|  |  | Number of oversight reports produced |  | 30 |  |  |
|  |  | Number of bi-annual committee reports produced |  | 2 |  |  |
|  |  | No. of Budgets approved and Appropriation Act enacted |  | 2 |  |  |
| County executive | Administration, Planning and Support Services | Amount allocated to office operations and maintenance |  | 141M |  |  |
|  |  | No. of vehicles purchased |  | 1 |  |  |
|  |  | Number of staff trained |  | 20 |  |  |
|  |  | Amount allocated to personal Emoluments |  | 64M |  |  |
|  | Government Advisory Services | Number of collaboration and cooperation meetings with other counties |  | 1 |  |  |
|  | Leadership and Coordination of Departments | Reduction in time used on transacting a service |  | 2 |  |  |
|  |  | Number of service charters developed |  | 1 |  |  |
|  |  | Number of MOUs and agreements signed with the National Government |  | 1 |  |  |
|  |  | Number of employees under performance contracting |  | 10 |  |  |
| County Public Service Board | General Administration, Planning and Support Services | % of successful recruitments and promotions done |  | 30 |  |  |
|  |  | Amount in Kshs allocated per annum for personal emoluments |  | 23M |  |  |
|  |  | % of disciplinary cases successfully resolved |  | 40 |  |  |
|  |  | % of staff satisfaction |  | 20 |  |  |
|  |  | Number of competence inventory |  | 1 |  |  |
|  |  | No. of Manuals developed. |  | 1 |  |  |
|  |  | Number of constitution sensitization forums held(Article 10 and 232) |  | 12 |  |  |
|  |  | Number of human resource advisory meetings held |  | 4 |  |  |
|  |  | Number of capacity building /Trainings conducted |  | 2 |  |  |
| Finance, ICT and Economic Planning | General Administration, Planning and Support Services | No of finance and Appropriation bills drafted and tabled to the county assembly |  | 2 |  |  |
|  |  | CBEF committee formed and functional |  | 1 |  |  |
|  |  | No. of CBEF trainings conducted |  | 2 |  |  |
|  |  | No of office blocks constructed |  | 2 |  |  |
|  |  | Number of officers capacity built |  | 806 |  |  |
|  |  | Number of HR audit done |  | 1 |  |  |
|  | financial management services | Amount in Kshs allocated per personal emoluments |  | 806 |  |  |
|  |  | % compliance to IPSAS |  | 40% |  |  |
|  |  | Number of quarterly financial statements prepared and submitted |  | 4 |  |  |
|  |  | Number of annual financial statements prepared and submitted |  | 1 |  |  |
|  |  | % compliance to Procurement laws and regulations |  | 40% |  |  |
|  |  | Number of annual procurement plans prepared |  | 1 |  |  |
|  |  | % compliance |  | 45% |  |  |
|  |  | Number of quarterly audit reports prepared |  | 4 |  |  |
|  |  | Number of internal annual audit reports prepared and submitted |  | 1 |  |  |
|  |  | Number of capacity building sessions on audit committee |  | 2 |  |  |
|  | Economic Planning And Budgetary Services | Number of CIDP prepared and submitted to the county assembly |  | 1 |  |  |
|  |  | Number of ADP prepared and submitted to the county assembly |  | 1 |  |  |
|  |  | No of ward public participation meetings held |  | 60 |  |  |
|  |  | Number of monitoring and evaluation reports |  | 4 |  |  |
|  |  | Number of surveys done and quality assessment |  | 1 |  |  |
|  |  | Number of county fact sheets develop, updated and disseminated |  | 1 |  |  |
|  |  | Percentage of development budget to total county budget |  | 31 |  |  |
|  |  | Number of CBROP prepared and submitted to the county assembly |  | 1 |  |  |
|  |  | Number of CFSP prepared and submitted to the county assembly |  | 1 |  |  |
|  |  | Number of PBB prepared and submitted to the county assembly |  | 1 |  |  |
|  | Resource Mobilization And Revenue | Amount in kshs(million ) collected annually as internal revenue |  | 2.6B |  |  |
|  |  | Number of automated Revenue streams |  | 1 |  |  |
| Administration and Public Service | administration, planning and support services | Number of Office blocks constructed |  | 1 |  |  |
|  |  | Number of Gate constructed |  | 1 |  |  |
|  |  | Number of Lounge constructed and furnished |  | 1 |  |  |
|  |  | Number of One stop county service centre constructed |  | 1 |  |  |
|  |  | Number of ablution block constructed |  | 1 |  |  |
|  |  | Number of motor vehicles purchased. |  | 3 |  |  |
|  | Alcohol, drug and substance abuse control and rehabilitation | Number of completed rehabilitation and treatment centre. |  | 1 |  |  |
|  |  | Number of prevention and treatment programmes initiated and implemented through partnerships. |  | 24 |  |  |
|  |  | Number of drop in centres operationalized. |  | 12 |  |  |
|  |  | Percentage increase in the number of people accessing treatment and rehabilitative services. |  | 10% |  |  |
|  |  | Percentage reduction on illicit, substandard, counterfeit and illegal alcohol. |  | 16% |  |  |
|  |  | Number of people engaged in alternative businesses/ programme/ projects initiated. |  | 300 |  |  |
|  |  | Number of people sensitized on dangers of harmful use of alcohol, drugs and substances. |  | 12,000 |  |  |
|  |  | Number of status reports prepared. |  | 1 |  |  |
|  |  | Percentage increase in the number of intervention strategies put in place. |  | 5 |  |  |
|  | administration, planning and support services | Number of offices renovated |  | 5 |  |  |
|  |  | Number of staffs remunerated, and allowances paid |  | 357.9M |  |  |
|  |  | Number of financial operations carried out |  | 146.5M |  |  |
|  |  | Number of uniforms and equipment purchased. |  | 300 |  |  |
|  | betting and gaming | Percentage reduction in the number of illegal betting outlets. |  | 30% |  |  |
|  |  | Number of public awareness forums held. |  | 13 |  |  |
|  |  | Percentage reduction on illegal betting and gaming machines and outlets. |  | 30% |  |  |
|  | public participation and citizen petitions | Number of information, education and communication (IEC) materials disseminated. |  | 12000 |  |  |
|  |  | Number of public participation forums held. |  | 60 |  |  |
|  |  | Number of guidelines / policies developed. |  | 1 |  |  |
|  |  | Number of complaints and feedback mechanisms formulated. |  | 1 |  |  |
|  | human resource management services | Number of human resource policies developed. |  | 1 |  |  |
|  |  | Number of staff surveys conducted. |  | 1 |  |  |
|  |  | Number of performance contracts. Number of staff trained. Number of staff appraised. Number of staff rationalization reports prepared. |  | 1 150 150 1 |  |  |
|  |  | Number of staff training needs assessments done. |  | 1 |  |  |
|  |  | Percentage reduction on unethical and corrupt practices. |  | 10% |  |  |
|  |  | Number of officers trained |  | 1500 |  |  |
|  | communication | Number of Monthly newspaper copies printed and distributed. |  | 1000 |  |  |
|  |  | Number of active digital platforms |  | 6 |  |  |
|  |  | Number of customer care desks and information boxes established. |  | 12 |  |  |
|  |  | Number of adverts featured in newspaper, radio and TV platforms. |  | 250 |  |  |
| Agriculture, crop production, irrigation & marketing | Agribusiness and information management | No. of collection centres with storage facilities established |  | 1 |  |  |
|  |  | Number of disposal points set up |  | 8 |  |  |
|  |  | No. of coffee nursery established |  | 1 |  |  |
|  |  | No. of model factories developed |  | 3 |  |  |
|  |  | No. of coffee mill rehabilitated |  | 1 |  |  |
|  |  | No. of coffee factories with waste management system |  | 3 |  |  |
|  | Crop Development and Management | No. h/h connected to water |  | 500h/h |  |  |
|  |  | No. h/h connected to water |  | 100h/h |  |  |
|  |  | No h/h connected to water |  | 1,000h/h |  |  |
|  |  | No, h/h connected to water |  | 600h/h |  |  |
|  |  | No, h/h connected to water |  | 700h/h |  |  |
|  |  | No, h/h connected to water |  | 600h/h |  |  |
|  |  | No of demonstration sites |  | 120 sites |  |  |
|  |  | No of Dumpy levels procured and distributed No of Total station set No of GPS devices purchased |  | 12 2 20 |  |  |
|  |  | No of Youth groups to benefit |  | 8 |  |  |
|  |  | Length of fence in Meters |  | 2800 |  |  |
|  |  | No. of storage water tank towers erected |  | 1 |  |  |
|  |  | No. of Computers, Laptops modem and standby Generator procured |  | 2 2 2 1 |  |  |
|  |  | No. of tractors and Accessories procured |  | 2 1 |  |  |
|  |  | No. of Survey equipment procured |  | 1 |  |  |
|  | Administration planning and support services | Number of offices constructed |  | 1 |  |  |
|  |  | Number of vehicles procured |  | 2 |  |  |
|  |  | Number of staff sponsored for promotional and refresher courses |  | 100 |  |  |
|  |  | Amount of money disbursed for personnel emoluments |  | 197M |  |  |
|  |  | Amount of money disbursed for operations and maintenance |  | 33M |  |  |
|  | Policy, Strategy and management of Agriculture | Number of policies/regulations developed |  | 1 |  |  |
|  |  | Number of committees formed |  | 30 |  |  |
|  |  | No of Financial Reports done |  | 4 |  |  |
|  |  | Number of strategic plans prepared |  | 1 |  |  |
|  |  | Number of forums convened |  | 4 |  |  |
|  | Agribusiness and information management | No. of agro dealers trained |  | 20 |  |  |
|  |  | No. of VCAs trained |  | 100 |  |  |
|  |  | No. of farmers linked to financial service providers |  | 50 |  |  |
|  |  | No. of agriprenuers and farmers trained |  | 60 |  |  |
|  |  | No. of incubation centre set up |  | 1 |  |  |
|  |  | Number of Coffee stakeholders and technical working groups formed |  | 7 |  |  |
|  |  | Number of clonal gardens established |  | 1 |  |  |
|  |  | Number of inspector gazette |  | 1 |  |  |
|  |  | Number of licensing officers trained |  | 6 |  |  |
|  |  | Number of farmers trained on coffee production management |  | 150 |  |  |
|  |  | Number of staffs trained on production management and value addition |  | 20 |  |  |
|  |  | Number of groups formed and strengthened |  | 10 |  |  |
|  |  | Number of farmer groups certified |  | 2 |  |  |
|  | Crop Development and Management | No. of Kits purchased Conservation Agriculture equipment No of farmers trained |  | 120 2,400 |  |  |
|  |  | No. of beneficiaries |  | 13,000 |  |  |
|  |  | No. of motorbikes purchased |  | 20 |  |  |
| Water energy environment and natural resource | Administration planning and support services | Number of vehicles procured |  | 2 |  |  |
|  |  | Number of vehicles serviced |  | 20 |  |  |
|  |  | Number of staff sponsored for promotional and refresher courses |  | 10 |  |  |
|  |  | No of staff recruited No of staff registered |  | 3 6 |  |  |
|  |  | Amount of money disbursed for operations and maintenance |  | 6 |  |  |
|  |  | Amount allocated to personal Emoluments |  | 160M |  |  |
|  | Environment Management and protection | No of environmental committee in place |  | 1 |  |  |
|  |  | No of GIS systems in place |  | 1 |  |  |
|  |  | No. of policies developed and institutionalized |  | 3 |  |  |
|  |  | No. of waste management hub constructed |  | 1 |  |  |
|  |  | No. of a skip loaders procured |  | 1 |  |  |
|  |  | No. of skips procured |  | 20 |  |  |
|  |  | No. of decommissioned and rehabilated open dumpsites |  | 1 |  |  |
|  |  | Research on solid waste Management |  | 4 |  |  |
|  |  | No of toilets Constructed/rehabilitated |  | 24 |  |  |
|  |  | No of awareness campaigns held |  | 12 |  |  |
|  |  | No environmental Trainings held |  | 3 |  |  |
|  | Water resources management and sanitation | No of policies drafted and developed |  | 1 |  |  |
|  |  | No of Pans constructed |  | 5 |  |  |
|  |  | No of plastic tanks Procured and distributed |  | 50 |  |  |
|  |  | No of Elevated tanks Constructed |  | 9 |  |  |
|  |  | No of boreholes Drilled and equipped |  | 12 |  |  |
|  |  | Km laid assorted extension pipes |  | 50 |  |  |
|  |  | No of water kiosks |  | 16 |  |  |
|  |  | No of signage erected |  | 100 |  |  |
|  | natural resources conservation and management | No of trees planted |  | 500,000 |  |  |
|  |  | No of trees planted in county forests/ water catchment |  | 500,000 |  |  |
|  |  | No of seedlings grown in farms |  | 500,000 |  |  |
|  |  | No of trees planted in open spaces and road reserves (beautification) |  | 200,000 |  |  |
|  |  | Acreage acquired for establishment of county forest and trees planted |  | 5 |  |  |
|  |  | No of activities mapped |  | 5 |  |  |
|  |  | No of giant bamboo planted |  | 100000 |  |  |
|  |  | No of Secured habitats |  | 4 |  |  |
|  |  | No of policies Developed |  | 2 |  |  |
|  | Renewable Energy and Climate Change | No of renewable energy and climate change centers established |  | 1 |  |  |
|  |  | -No of retro fitting done % reduction on bills |  | 12 |  |  |
|  |  | -No of briquettes making machines procured - No of Kgs of briquettes made & sold |  | 2 |  |  |
|  |  | -No. of biogas plants constructed & in use -No.of facilities using biogas -Reduced discharge of waste from the slaughter houses |  | 5 |  |  |
|  |  | -No. of cook stoves, bulbs and solar panels procured and distributed -% reduction on electricity bills |  | 32,000 |  |  |
|  |  | -No. of awareness campaigns held |  | 60 |  |  |
|  |  | -No. of premises audited No of Audit reports |  | 15 |  |  |
|  |  | No. of climate change and renewable energy initiatives done |  | 12 |  |  |
|  |  | -No of procured and installed functional solar panel |  | 2 |  |  |
|  |  | No. procured of solar powered street lights and installed % electricity bill |  | 2 |  |  |
|  |  | No of incandescent lights procured and installed in offices |  | 12 |  |  |
|  |  | No of policy in place No of renewable energy master plan |  | 1 1 |  |  |
|  |  | Number of vulnerability hotspots identified |  | 12 |  |  |
|  |  | -Number of awareness campaigns held -Modes of publicity used |  | 12 |  |  |
|  |  | -No of schools mapped No Needs assessment report done |  | 60 |  |  |
|  |  | No. of bins procured and installed Number of bins in schools Behavioral change ( waste reduction and separation) -Clean school environment |  | 60 |  |  |
|  |  | No of water tanks supplied %Reduction of water bills |  | 12 schools |  |  |
| Health | Administration, Planning and Support services | % of works completed Completion of maternity unit, construction of fence and Renovation works of the building in Athi dispensary, Kalimoni ward in Juja sub county |  | 100 |  |  |
|  |  | % of works completed Refurbishment of the OPD and the laboratory unit in Cianda dispensary, Cianda ward and Kiambaa sub county |  | 100 |  |  |
|  |  | % of works completed Refurbishment works and construction of waiting bay in Escarpment dispensary, Lari/Kirenga ward, Lari sub county |  | 100 |  |  |
|  |  | % of works completed Refurbishment and Rehabilitation of the OPD, laboratory unit and fence in Gachika health centre, Kiganjo ward, Gatundu south sub county |  | 100 |  |  |
|  |  | % of works completed Refurbishment and construction of a covered walk way in Gichuru dispensary, Sigona ward, Kikuyu sub county |  | 100 |  |  |
|  |  | % of works completed Construction of ablution block and renovation works in Cianda dispensary, Cianda ward , Kiambaa sub county |  | 100 |  |  |
|  |  | % of works completed Construction of patient toilet block in Wangige level 4 hospital, Kabete ward, Kabete sub county |  | 100 |  |  |
|  |  | % of works completed Refurbishment and rehabilitation of the OPD and the laboratory unit in Juja farm health centre, Kalimoni ward , Juja sub county |  | 100 |  |  |
|  |  | % of works completed Refurbishment works and construction of a covered walkway in Karia dispensary, Ikinu |  | 100 |  |  |
|  |  | % of works completed Extension of the OPD building in Kereita forest dispensary, Kijabe ward, Lari sub county |  | 100 |  |  |
|  |  | % of works completed Rehabilitation and refurbishment works in Makongeni health centre, Kamenu ward, Thika sub county |  | 100 |  |  |
|  |  | % of works completed Rehabilitation and refurbishment of the building in Munyu-ini dispensary, Ndarugo ward, Gatundu south sub county |  | 100 |  |  |
|  |  | % of works completed Rehabilitation and refurbishment of the buildings in Mutate dispensary, Kiamwangi ward, Gatundu south sub county |  | 100 |  |  |
|  |  | % of works completed Refurbishment, construction of covered walk way and waiting bay in Ngecha health centre, Tigoni/Ngecha ward, Limuru sub county |  | 100 |  |  |
|  |  | % of works completed Rehabilitation and refurbishment of the buildings in Ngoliba health center, Ngoliba ward , Thika sub county |  | 100 |  |  |
|  |  | % of works completed Rehabilitation and refurbishment of the buildings in Ngorongo health centre, Chania ward, Gatundu north sub county |  | 100 |  |  |
|  |  | % of works completed Refurbishment works of the buildings in Nyathuna level 4 hospital, Nyathuna ward, Kabete sub county |  | 100 |  |  |
|  |  | % of works completed Expansion of OPD building and renovation of the laboratory unit in Riabai dispensary, Riabai ward, Kiambu sub county |  | 100 |  |  |
|  |  | % of works completed Construction of covered walk way in Rwamburi dispensary, Ndeiya ward, Limuru sub county |  | 100 |  |  |
|  |  | % of works completed Refurbishment of the building and construction of maternity in Thigio dispensary, Ndeiya ward, Limuru sub county |  | 100 |  |  |
|  |  | % of works completed Rehabilitation and refurbishment works in Uthiru dispensary, Uthiru ward, Kabete sub county |  | 100 |  |  |
|  |  | % of works completed Construction of wards, theatre, laboratory unit, fence and gate in Gachororo health centre, Juja ward, Juja sub county |  | 100 |  |  |
|  |  | % of works completed Construction of a dispensary Kahawa wendani dispensary, Kahawa Wendani ward, Ruiru sub county |  | 100 |  |  |
|  |  | % of works completed Construction of a dispensary Ndumberi dispensary, Ndumberi ward, Kiambu sub county |  | 100 |  |  |
|  |  | % of works completed Construction of incinerator in Karatu level 4 hospital, Ndarugo, Gatundu south sub county |  | 100 |  |  |
|  |  | % of works completed Construction of incinerator Kigumo level 4 hospital, Komothai ward, Githunguri sub county |  | 100 |  |  |
|  |  | % of works completed Construction of incinerator in Lari level 4 hospital, Lari/Kirenga ward, lari sub county |  | 100 |  |  |
|  |  | % of works completed Supply and installation of generator and renovation of the laboratory unit in Gachororo health centre, Juja ward, Juja sub county. |  | 100 |  |  |
|  |  | % of works completed Supply and installation of generator in Wangige level 4 hospital, Kabete ward, Kabete sub county |  | 100 |  |  |
|  |  | % of works completed Supply and installation of generator in Kigumo level 4 hospital, Komothai ward, Githunguri sub |  | 100 |  |  |
|  |  | % of works completed Supply and installation of generator in Karatu level 4 hospital, Ndarugo ward, Gatundu south sub county |  | 100 |  |  |
|  |  | % of works completed Renovation and refurbishment of OPD, maternity, fence and gate in Mbau-ini dispensary, Kijabe ward, Lari sub county |  | 100 |  |  |
|  |  | % of works completed Construction of theatre and renovation of the laboratory unit in Ndeiya health centre, |  | 100 |  |  |
|  |  | % of works completed Construction of theatre , renovation of wards and rehabilitation of the access road in Karatina health centre, Nyanduma ward, Lari sub county |  | 100 |  |  |
|  |  | % of works completed Renovation of the OPD and the laboratory unit Muchatha dispensary, Muchatha ward, Kiambaa sub county. |  | 100 |  |  |
|  |  | % of works completed Renovation works of the laboratory unit in Gatundu level 5 hospital, Ng’enda ward, Gatundu south sub county |  | 100 |  |  |
|  |  | % of works completed Renovation works of the laboratory unit in Ngewa health centre, Ngewa ward, Githunguri sub county. |  | 100 |  |  |
|  |  | % of works completed Renovation and rehabilitation of laboratory, offices, stores, laundry and gate in Limuru health centre, Limuru central, Limuru sub county |  | 100 |  |  |
|  |  | % of works completed Construction of maternity unit and renovation works of the OPD in Kinoo dispensary, Kinoo ward, Kabete ward |  | 100 |  |  |
|  |  | % of works completed Rehabilitation and refurbishment of the buildings and construction of maternity in Thindigua dispensary, township ward, Kiambu sub county |  | 100 |  |  |
|  |  | % of works completed Construction of Bibirioni level 4 hospital, Bibirioni ward, Limuru sub county |  | 100 |  |  |
|  |  | % of works completed Upgrade of Githunguri level 4 hospital, Githunguri ward, Githunguri sub county |  | 100 |  |  |
|  |  | % of works completed Completion of Kikuyu level 4 hospital, Kikuyu ward, Kikuyu sub county |  | 100 |  |  |
|  |  | Completion of wards in Tigoni level 4 hospital, Tigoni/Ngecha ward, Limuru sub county |  | 100 |  |  |
|  |  | % of works completed Completion of wards in Wangige level 4 hospital, Kabete ward, Kabete sub county |  | 100 |  |  |
|  |  | % of works completed Completion of wards in Lari level 4 hospital, Lari/Kirenga ward, Lari sub county |  | 100 |  |  |
|  |  | % of works completed Conversion of ECD classes to dispensary, Karura ka nyungu dispensary |  | 100 |  |  |
|  |  | % of works completed Construction of patient toilet block, fence and gate, Karura ka nyungu dispensary, Nyathuna ward, Kabete sub county |  | 100 |  |  |
|  |  | % of works completed Conversion of ECD classes to dispensary, Githiga dispensary, Nyathuna ward, Kabete sub county. |  | 100 |  |  |
|  |  | % of works completed Construction of patient toilet block, fence and gate, Gathiga dispensary |  | 100 |  |  |
|  |  | No. of serviceable vehicle |  | 39 |  |  |
|  |  | No. of vehicles purchased |  | 2 |  |  |
|  |  | No. facilities fully automated with the HMIS |  | 21 |  |  |
|  |  | No. of improved Service charters |  | 21 |  |  |
|  |  | No. of customer care service units |  | 19 |  |  |
|  |  | No. of customer satisfaction surveys |  | 36 |  |  |
|  |  | No. of facilities submitting DHIS reports |  | 107 facilities |  |  |
|  |  | No. of facilities supervised by CHMT |  | 107 facilities |  |  |
|  |  | No. of facilities supervised by SCHMTs |  | 107 facilities |  |  |
|  |  | No. of staff remunerated |  | 2653 staff |  |  |
|  |  | No. of staff recruited |  | 172 staff |  |  |
|  |  | No. of staff promotions done |  | 379 staff |  |  |
|  |  | No. of staff appraised |  | 2825 staff |  |  |
|  |  | Annual reward events |  | 14 |  |  |
|  |  | No. of team building activities done |  | 21 |  |  |
|  |  | No. of functional procurement committees in place |  | 13 |  |  |
|  | Curative Services | No. of facilities equipped with assorted medical equipment |  | 107 |  |  |
|  |  | No of facilities provided with non- pharmaceuticals |  | 107 |  |  |
|  |  | No of facilities provided with cleansing materials and sanitary items |  | 107 |  |  |
|  |  | No of facilities providing baby friendly services |  | 15 |  |  |
|  |  | No of facilities with lactation stations |  | 20 |  |  |
|  |  | No of facilities with kitchen gardens |  | 4 |  |  |
|  |  | No of facilities with nutrition service equipment |  | 107 |  |  |
|  |  | No of screening and treatment medical camps conducted |  | 8 |  |  |
|  |  | Facilities providing PWD friendly services |  | 10 |  |  |
|  |  | No of dental clinics establishments |  | 1 |  |  |
|  |  | No of CT scan equipment installed |  | 1 |  |  |
|  |  | No of diagnostic ultrasound machined provided |  | 1 |  |  |
|  |  | No of blood gas analyzers provided |  | 1 |  |  |
|  |  | No of health care workers trained on IMNCI |  | Planned |  |  |
|  |  | No of oral rehydration centres provided |  | 40 |  |  |
|  |  | No of pulse oximeters provided |  | 50 |  |  |
|  |  | No of health care workers trained on ETAT |  |  |  |  |
|  | Pharmaceutical Services | No of pharmacies renovated |  | 5 |  |  |
|  |  | % of facilities fully stocked all year round |  | 100% |  |  |
|  |  | % of facilities practicing good inventory management |  | 80% |  |  |
|  | County Health Policy Development and Management | Proportion of population contributing to NHIF |  | 44% |  |  |
|  |  | No of policy brief developed and adopted for Emergency and disaster preparedness |  | 1 |  |  |
|  |  | No of policy brief developed and adopted for improved health quality and standards |  | 1 |  |  |
|  |  | No. of support supervision visits done |  | 30 |  |  |
|  |  | Number of patient satisfaction surveys conducted |  | 1 |  |  |
|  |  | Number of health provider satisfaction surveys conducted |  | 1 |  |  |
|  |  | Number of health personnel trained |  | 530 |  |  |
|  |  | No. of IMAM training conducted |  | 2 |  |  |
|  |  | No of Nutrition HIV training conducted |  | 2 |  |  |
|  |  | No of Nutrition & TB training conducted |  | 4 |  |  |
|  |  | No of MIYCF training conducted |  | 2 |  |  |
|  |  | % of TB sites done OJT |  | 80% |  |  |
|  |  | % funding directed to medical research |  | 0.3% |  |  |
|  | Reproductive Health | % of women of Reproductive age receiving family planning |  | 72% |  |  |
|  |  | % HIV + pregnant mothers receiving preventive ARV’s |  | 100 |  |  |
|  |  | % of targeted pregnant women provided with LLITN’s |  | 40 |  |  |
|  |  | % deliveries conducted by skilled attendant |  | 90 |  |  |
|  |  | % of facility based maternal deaths |  | 70 |  |  |
|  |  | % of newborns with low birth weight |  | 4 |  |  |
|  |  | % of facility based fresh still births |  | 1 |  |  |
|  |  | % of pregnant women attending 4 ANC visits |  | 55 |  |  |
|  |  | % Women of Reproductive age screened for Cervical cancers |  | 25 |  |  |
|  |  | % of facilities providing BEOC |  | 85 |  |  |
|  |  | % of facilities providing CEOC |  | 60 |  |  |
|  |  | % of facilities providing Immunization |  | 50 |  |  |
|  |  | % maternal audits/deaths audits |  | 100 |  |  |
|  |  | % of pregnant women supplemented with Iron and folic |  | 80% |  |  |
|  |  | % of fully immunized children |  | 90 |  |  |
| Education Youth Sports Culture and Social services | general administration, planning and support services | No. of offices equipped |  | 3 |  |  |
|  |  | No of offices equipped and refurbished |  | 12 |  |  |
|  |  | No of motor vehicles purchased, fueled and maintained |  | 4 |  |  |
|  |  | No of staff remunerated, allowances paid and statutory deductions paid. |  | 1660 |  |  |
|  |  | No of institutions and projects monitored, bench markings and meetings attended. |  | 20 |  |  |
|  |  | No. of team building activities held |  | 1 |  |  |
|  |  | No. staff under performance contract |  | 1635 |  |  |
|  |  | No of exhibitions and media shows done and posters and distributed |  | 5 |  |  |
|  |  | The amount of money disbursed |  | 30,000 |  |  |
|  |  | No of instructors recruited |  | 100 |  |  |
|  |  | No. of ECDE children benefitting from Nutrition programme. |  | 33,000 |  |  |
|  |  | Quality education in ECDE centers |  | 520 |  |  |
|  | Vocational Education and Training (Youth Polytechnics | No of ECDE teachers recruited |  | 400 |  |  |
|  |  | No of ECDE centers instructed with materials |  | 550 |  |  |
|  |  | No of policies, bills and regulations developed |  | 3 |  |  |
|  |  | Percentage completion Construction of modern Amphitheatre Kirigiti stadium |  | 30 |  |  |
|  |  | Percentage completion Construction of changing rooms/WC and upgrading Kanjeru stadium |  | 100 |  |  |
|  |  | Percentage completion Fencing and construction of WC and changing room Githunguri stadium KCG |  | 100 |  |  |
|  |  | Percentage completion of fencing and construction WC/changing rooms Limuru |  | 100 |  |  |
|  |  | Percentage completion of fencing and construction WC/changing rooms in Lari Kirenga |  | 100 |  |  |
|  |  | No. of athletes participating |  | 500 |  |  |
|  | Gender and Culture | No. of staff participating in Kicosca games |  | 500 |  |  |
|  |  | No of teams participating in Kyisa games |  | 200 |  |  |
|  |  | Percentage Completion of Construction and equipping a rehabilitation center in Thika Sub County |  | 100 |  |  |
|  |  | Percentage Completion Construction of museum and resource center Githunguri Sub County |  | 100 |  |  |
|  |  | Percentage completetion Rehabilitation and conservation of mugumuini gardens |  | 100 |  |  |
|  |  | Percentage completion Rehabilitation and conservation of cultural and heritage sites Cultural and heritage sites in Githunguri sub County |  | 100 |  |  |
|  |  | Percentage Rehabilitation and equipping of Jamhuri children home |  | 100 |  |  |
|  |  | Percentage Completion Construction and equipping of a community library |  | 100 |  |  |
|  |  | Percentage Completion of Karuri Social hall |  | 100 |  |  |
|  |  | Percentage Completion Rehabilitation and equipping of Kiambu community hall |  | 100 |  |  |
|  |  | Percentage Completion Construction and equipping Lussigetti Community Library in Nachu ward of the library |  | 100 |  |  |
|  |  | Percentage Completion Construction and erecting of monuments Historical monument at Kirangari, Kiambaa and Kiambu |  | 100 |  |  |
|  |  | No of assistive devices issued |  | 100 |  |  |
|  |  | No of women, youth and PWDs groups funded. |  | 300 |  |  |
|  |  | No of youths rehabilitated from alcohol and drug abuse |  | 300 |  |  |
|  | Youth Affairs | No of old persons reached |  | 1,200 |  |  |
|  |  | No of programs held no of officers participating |  | 3 |  |  |
|  |  | No of youths rehabilitated from alcohol and drug abuse |  | 300 |  |  |
|  |  | No of street families rehabilitated |  | 50 |  |  |
|  |  | No of youth trained |  | 60 |  |  |
|  |  | No of upcoming artist mentored |  | 60 |  |  |
|  |  | No of sensitization programs held |  | 1 |  |  |
|  |  | No of multi-stakeholders technical working groups formed, No of sensitization forums held |  | 2 |  |  |
|  |  | No of assistive devices issued |  | 100 |  |  |
|  |  | No of women, youth and PWDs groups funded. |  | 300 |  |  |
|  |  | No of youths rehabilitated from alcohol and drug abuse |  | 300 |  |  |
|  |  | No of programs held no of officers participating |  | 3 |  |  |
| Lands | County Land Information Management Services | Number of land parcels digitized -Existence of |  | 35,000 |  |  |
|  |  | No.of property rates registered |  | 160,000 |  |  |
|  |  | No. of county properties valued |  | 200 |  |  |
|  |  | No. of properties managed |  | 300 |  |  |
|  | Planning, Land Survey and Mapping | Number of County Spatial Structure Plan |  | 1 |  |  |
|  |  | Number of ISUDPS prepared -Defined urban edges -Building guidelines and planning regulation |  | 1 |  |  |
|  |  | Percentage of developers submitting development application Percentage Increase in revenue generation |  | 10 |  |  |
|  |  | Percentage increase in compliance to development regulations |  | 20 |  |  |
|  |  | Number of parcel boundaries reestablished and beacons placed. |  | 100 |  |  |
|  |  | Number of title deeds acquired |  | 200 |  |  |
|  |  | Number of base maps prepared |  | 30 |  |  |
|  |  | Percentage area of the County completed |  | 20 |  |  |
|  | County Urban Planning and Housing | Number of Operational Municipal and Towns Management Boards |  | 6 |  |  |
|  |  | Number of well defined boundaries of the new municipalities |  | 6 |  |  |
|  |  | Amount in Kshs allocated to CIUDS program |  | 1.8B |  |  |
|  |  | No. of upgraded settlements And basic facilities provided in the upgraded settlements |  | 2 |  |  |
|  |  | Number of building technologies adopted |  | 1 |  |  |
|  |  | Number of households accessing the decent houses |  | 500 |  |  |
|  | Administration, Planning and Support Services | Number of offices constructed |  | 2 |  |  |
|  |  | Number of offices equipped |  |  |  |  |
|  |  | Number of vehicles purchased |  | 2 |  |  |
|  |  | No. of personnel employed |  |  |  |  |
|  |  | No. of training sessions |  | 2 |  |  |
|  |  | No. of performance appraisals done |  | 1 |  |  |
| Trade, Tourism, Co-operative and Enterprise Development |  | No. of plant clinics equipped No. of plant doctors trained |  | 7 14 |  |  |
|  |  | No of water pan liners purchased No of drip kits purchased |  | 40 |  |  |
|  |  | No of master plans developed |  | 1 |  |  |
|  |  | No of dairy units rehabilitated No of biogas units rehabilitated |  | 1 1 |  |  |
|  |  | No of farmers trained |  | 5000 |  |  |
|  |  | Yield per tree per year |  | 5 |  |  |
|  |  | No of staff houses rehabilitated |  | 5 |  |  |
|  |  | No. of structures rehabilitated |  | 2 |  |  |
|  |  | No. of Machinery Rehabilitated |  | 1 |  |  |
|  | Trade Development and Promotion | No. of Markets constructed/ Renovated/ Rehabilitated |  | 15 |  |  |
|  |  | No of modern stalls |  | 25 |  |  |
|  |  | Number of BodaBoda sheds constructed |  | 60 |  |  |
|  |  | No. of shoe shiners sheds constructed |  | 2 |  |  |
|  |  | Number of Trade fair / exhibitions attended / done |  | 3 |  |  |
|  | Enterprise Development and Promotion | No, of industrial parks established |  | 1 |  |  |
|  |  | No. of exhibitions /expo/forums undertaken |  | 2 |  |  |
|  |  | No of Incubation / start – up development centres created |  | 1 |  |  |
|  |  | No of SME database created |  | 1 |  |  |
|  |  | No of Branding done |  | 1 |  |  |
|  |  | No of MSMEs trained |  | 90 |  |  |
|  |  | Establishment of Kiambu Biashara Sacco |  | 1 |  |  |
|  |  | Number of circular economies created |  | 1 |  |  |
|  |  | No of value addition in MSMES |  | 1 |  |  |
|  |  | No of trainings and mentorship on startup businesses |  | 1 |  |  |
|  |  | No of Juakali sheds constructed |  | 12 |  |  |
|  | Co-operative Development and Management | No. of cooperatives management members trained / educated |  | 200 |  |  |
|  |  | No. of warehouse created |  | 1 |  |  |
|  |  | No. of Machines purchased |  | 1 |  |  |
|  |  | No. of Milk collection centers constructed |  | 16 |  |  |
|  |  | No of revolving fund in place |  | 1 |  |  |
|  |  | No. Digitalized system in place |  | 1 |  |  |
|  | Tourism Development and Promotion | Number of tourism expo / events done |  | 4 |  |  |
|  |  | Existence of a mapping and profiling report |  | 1 |  |  |
|  |  | Number of tourist sites rehabilitated/ landscaped/ developed |  | 6 |  |  |
|  |  | number of legal instruments in place |  | 1 |  |  |
|  |  | Number of sites preserved / local heritage sites gazette |  | 5 |  |  |
|  | Administration, Planning and Support Services | Number of offices supported |  | 20 |  |  |
|  |  | No of vehicles purchased |  | 6 |  |  |
|  |  | Personnel Emolument supported |  | 64 |  |  |
| Roads, Transport, Public Works & Utilities | Administration, Planning and Support Services | Number of service charter developed |  | 1 |  |  |
|  |  | Number of office block constructed |  | 1 |  |  |
|  |  | No. of staff recruited |  | 4 |  |  |
|  |  | No. of staff Trained |  | 50 |  |  |
|  |  | Performance reviews and contracts |  | 259 |  |  |
|  |  | No. of Excavators acquired Rollers Trucks Manlift |  | 1 1 3 2 |  |  |
|  | Public works and Infrastructure maintenance | No. of Kilometers of roads maintained |  | 300 |  |  |
|  |  | No. of bridges maintained |  | 2 |  |  |
|  |  | No. of Kilometers of Non Motorised Traffic maintained |  | 10 |  |  |
|  |  | No. of Busparks maintained |  | 2 |  |  |
|  |  | No. of Kilometers of Storm water drains maintained |  | 2 |  |  |
|  |  | No. of Kilometers of roads rehabilitated |  | 260 |  |  |
|  |  | No. of Busparks rehabilitated |  | 12 |  |  |
|  | Roads Transport | No. of bridges designed and contracted |  | 2 |  |  |
|  |  | No. of Kilometers Non motorised Traffic designed and constructed |  | 10 |  |  |
|  |  | No. of Busparks designed and contracted |  | 2 No. |  |  |
|  | Energy, Disaster Management, Fire, Safety and Rescue | No. of Streetlights installed |  | 300 |  |  |
|  |  | No. of Flood masts Installed |  | 60 |  |  |
|  |  | No. of Fire stations constructed and rehabilitated |  | 4 |  |  |
|  |  | No. of Academy and fire stations equipped |  | 2 |  |  |
|  |  | No. of staff trained |  | 50 |  |  |
| Livestock | Fisheries Development and Management | Number of trainings on current technologies done |  | 1 |  |  |
|  |  | Number of aquaculture kits issued |  | 4 |  |  |
|  |  | Number of farmer trainings conducted |  | 36 |  |  |
|  |  | No. of farmers equipped with modern aquaculture technologies |  | 960 |  |  |
|  |  | Number of fingerlings stocked in rivers |  | 200,000 |  |  |
|  |  | Number of farmers and dealers trained on recreational fisheries |  | 20 |  |  |
|  |  | Number of fish marketing outlets established in collaboration with stakeholders |  | 2 |  |  |
|  |  | Number of freezers issued |  | 4 |  |  |
|  |  | Number of facilities/farms established |  | 10 |  |  |
|  | Livestock Resources Management and Development | Number of policies, guidelines and strategies reviewed, developed and rolled out |  | 1 |  |  |
|  |  | Number of staff whose capacity needs have been addressed |  | 160 |  |  |
|  |  | Number of farmers trained |  | 25000 |  |  |
|  |  | Number of dairy platform & Farmers field school (1 per sub county) |  | 1 |  |  |
|  |  | Uptake of subsidized AI (no. of doses) |  | 10,000 |  |  |
|  |  | Number of research and Linkages |  | 1 |  |  |
|  |  | Number of trainings per sub county per year |  | 12 |  |  |
|  |  | % completion of piggery unit |  | 1 |  |  |
|  |  | Number of pig Artificially Inseminated |  | 5000 |  |  |
|  |  | Number of farmers trained on market access and entrepreneurship skills |  | 100 |  |  |
|  |  | Number of Indigenous chicken procured and distributed |  | 20,000 |  |  |
|  |  | % completion of poultry unit |  | 1 |  |  |
|  |  | Number of farmers trained per year |  | 3000 |  |  |
|  |  | No. of value chain actors trained on Climate Smart technologies |  | 30000 |  |  |
|  |  | Number of pasteurizers availed to farmers |  | 3 |  |  |
|  |  | % completion of the pork factory |  | 1 |  |  |
|  |  | Number of Stock route, abattoir and farm inspections |  | 52 |  |  |
|  |  | No. of disease reporting books procured |  | 300 |  |  |
|  |  | Number of FMD vaccination campaigns done |  | 3 |  |  |
|  |  | Number of LSD vaccination campaign done |  | 1 |  |  |
|  |  | Number of Anthrax vaccination campaign done |  | 2 |  |  |
|  |  | Number of movement permits procured and issued |  | 500 |  |  |
|  |  | Number of vaccination |  | 12 |  |  |
|  |  | Number of rehabilitated dips |  | 0 |  |  |
|  |  | Number of Litres of arcaricide procured |  | 200 |  |  |
|  |  | Number of trainings of farmers in vector control and arcaricide |  | 24 |  |  |
|  |  | Number of Inseminators licensed |  | 200 |  |  |
|  |  | Number of trainings of inseminators and farmers |  | 12 |  |  |
|  |  | No. of trainings of veterinary staff on veterinary drug trade and reports |  | 12 |  |  |
|  |  | % Completion Thika Poultry and Rabbit slaughter house |  | 50% |  |  |
|  |  | Animal welfare bill developed and rolled out |  | 20% |  |  |
|  |  | Number of training of staff and farmers on animal welfare issue |  | 12 |  |  |
|  |  | % completion of the installation |  | 1 |  |  |
|  |  | Number of Meat inspection kit |  | 60 |  |  |
|  |  | Number of Slaughter houses licensed and inspected |  | 54 |  |  |
|  |  | No of Farmers enlightened on drug residues milk, eggs and meat |  | 1200 |  |  |
|  |  | No of Farmers empowered with leather products and production technology |  | 24 |  |  |
|  |  | No of flayers and, bandas and tanneries owners trained on proper leather production techniques |  | 24 |  |  |
|  |  | Number. of Inspections of bandas |  | 12 |  |  |
|  | Administration, Planning and Support Services | No. of Sub county offices constructed and equipped |  | 50 percent completion |  |  |
|  |  | No. of Farmers reached with extension services |  | 10,000 farmers |  |  |
|  |  | No. of vehicles procured and issued to Subcounties |  | 3 vehicles |  |  |
|  |  | No. of Staff undertaking promotional and refresher courses |  | 100 officers trained |  |  |
|  |  | Amount in Kshs allocated per personal emoluments |  | 197M |  |  |
|  |  | Amount allocated operation and maintenance. |  | 32M |  |  |